## 00_Home
SYNERGY ¦ PROJECT CONTROL TOWER
A decision-led collaboration cockpit for project execution — clean, connected, exception-first.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
CONTROL TOWER NORTH STAR
SEE → CONNECT → DECIDE → ACT
Make the problem visible • connect it to the right owner • quantify the consequence • drive the decision • verify the recovery.
PROJECTS |  | TASKS |  | REVENUE ₹L |  | PROFIT ₹L |  | PIPELINE ₹L |  | RED / AMBER |  | BLOCKED TASKS
100 |  | 600 |  | 18198.5 |  | 4224.6 |  | 3272.7 |  | 74 / 25 |  | 33
HOW TO USE | [6 empty] | DEMO FLOW
1 | Start at Sponsor | Outcome + exception view |  |  |  |  | Sponsor → Project → Risk → Dependency → Person → Decision → Resolution The workbook is deliberately built as a connected operating model, not a static report. Yellow cells are the controlled input layer; dashboard pages are formula-driven.
2 | Open Project 360 | Evidence behind the exception
3 | Open Gantt | Critical timing + dependency
4 | Open Decision Hub | Quantify the decision
5 | Open PM Control | Assign recovery
6 | Return to Sponsor | Verify the portfolio signal

## 01_Sponsor
SYNERGY ¦ SPONSOR COMMAND CENTRE
Executive portfolio view — value, growth, capacity and exceptions first.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
PORTFOLIO REVENUE |  |  | PORTFOLIO PROFIT |  |  | NEW BUSINESS PIPELINE |  |  | RESOURCES DEPLOYED |  |  | RISK EXPOSURE |  |  | PORTFOLIO HEALTH
18198.5 |  |  | 4224.6 |  |  | 3272.7 |  |  | 2187 |  |  | 74 RED ¦ 25 AMBER |  |  | 1 GREEN
VALUE ENGINE ¦ REVENUE / PROFIT / PIPELINE BY FUNCTION | [14 empty] | PORTFOLIO HEALTH
Function | Revenue ₹L | Profit ₹L | Pipeline ₹L | [11 empty] | RAG | Projects
Corporate | 1132.7 | 252.8 | 216.5 | [11 empty] | GREEN | 1
Digital | 1105.2 | 206.5 | 196.6 | [11 empty] | AMBER | 25
ESG | 1755.6 | 404.4 | 288.4 | [11 empty] | RED | 74
Infrastructure | 1545.8 | 354.4 | 286.7
Manufacturing | 2371 | 536.7 | 497.9
Product | 2281.4 | 546.5 | 528.2
Quality | 2052.3 | 492.1 | 297.9
Sales | 2622.1 | 640.3 | 400.2
Supply Chain | 1035.8 | 213.8 | 154.2
LEADERSHIP ATTENTION ¦ TOP EXCEPTIONS | [9 empty] | 6-MONTH VALUE TIMING
Project | RAG | Risk | Profit ₹L | Days Risk | Progress | PM | Next action | Revenue ₹L | Pipeline ₹L | Month | Revenue ₹L | Profit ₹L
Fusion Modernisation | RED | 92 | 44.7 | 8 | 71.3 | Sanjay Kumar | Review critical-path / decision queue | 195.6 | 26.5 | 2026-07-01 | 2183.82 | 506.952
Vector Transformation | RED | 92 | 22.4 | 6 | 84.8 | Sanjay Kumar | Review critical-path / decision queue | 86.3 | 49 | 2026-08-01 | 2729.775 | 633.69
Summit Integration | RED | 91 | 38.8 | 10 | 63.8 | Aditi Menon | Review critical-path / decision queue | 121.1 | 22.9 | 2026-09-01 | 3275.73 | 760.428
Vector Integration | RED | 88 | 44.9 | 17 | 42.8 | Rohit Nair | Review critical-path / decision queue | 227.8 | 64.5 | 2026-10-01 | 3639.7 | 844.92
Nexus Modernisation | RED | 88 | 49.2 | 6 | 81.7 | Meera Joshi | Review critical-path / decision queue | 381.7 | 24.6 | 2026-11-01 | 3275.73 | 760.428
Vertex Modernisation | RED | 87 | 77.9 | 10 | 72.3 | Neha Kapoor | Review critical-path / decision queue | 281.9 | 40.2 | 2026-12-01 | 3093.745 | 718.182
Vector Automation | RED | 86 | 64.4 | 21 | 23.2 | Aditi Menon | Review critical-path / decision queue | 200.7 | 8.8 | [5 empty] | 6-MONTH VALUE TIMING
Pioneer Expansion | RED | 86 | 58.7 | 14 | 47.2 | Meera Joshi | Review critical-path / decision queue | 211.5 | 58.5
Pioneer Automation | RED | 83 | 16.3 | 16 | 39.5 | Priya Shah | Review critical-path / decision queue | 60 | 43.7
Vertex Integration | RED | 83 | 34.2 | 14 | 46.3 | Arjun Mehta | Review critical-path / decision queue | 198.9 | 17.1
PORTFOLIO HEATMAP ¦ RISK × PROGRESS × VALUE
ID | Project | Function | Revenue ₹L | Profit ₹L | Pipeline ₹L | Progress % | Risk | RAG | PM | Sponsor | Region | Resources | Util. | Customer | Budget ₹L | Days Risk | Escalations
P019 | Vector Transformation | ESG | 86.3 | 22.4 | 49 | 84.8 | 92 | RED | Sanjay Kumar | Sponsor D | North | 10 | 97.09% | 87 | 55.4 | 6 | 3
P088 | Fusion Modernisation | Product | 195.6 | 44.7 | 26.5 | 71.3 | 92 | RED | Sanjay Kumar | Sponsor A | West | 33 | 64.27% | 76 | 85.8 | 8 | 3
P053 | Summit Integration | Manufacturing | 121.1 | 38.8 | 22.9 | 63.8 | 91 | RED | Aditi Menon | Sponsor E | South | 31 | 103.9% | 64 | 67.9 | 10 | 3
P059 | Vector Integration | Product | 227.8 | 44.9 | 64.5 | 42.8 | 88 | RED | Rohit Nair | Sponsor C | West | 28 | 67.9% | 89 | 155.6 | 17 | 3
P089 | Nexus Modernisation | Digital | 381.7 | 49.2 | 24.6 | 81.7 | 88 | RED | Meera Joshi | Sponsor B | North | 11 | 104.4% | 84 | 179.6 | 6 | 3
P085 | Vertex Modernisation | Sales | 281.9 | 77.9 | 40.2 | 72.3 | 87 | RED | Neha Kapoor | Sponsor E | South | 35 | 93.52% | 95 | 147.8 | 10 | 3
P035 | Pioneer Expansion | Sales | 211.5 | 58.7 | 58.5 | 47.2 | 86 | RED | Meera Joshi | Sponsor C | North | 24 | 77.37% | 58 | 110.1 | 14 | 3
P079 | Vector Automation | Infrastructure | 200.7 | 64.4 | 8.8 | 23.2 | 86 | RED | Aditi Menon | Sponsor E | South | 6 | 95.56% | 89 | 86.2 | 21 | 3
P045 | Vertex Integration | Technology | 198.9 | 34.2 | 17.1 | 46.3 | 83 | RED | Arjun Mehta | Sponsor B | North | 31 | 96.39% | 73 | 83.4 | 14 | 3
P075 | Pioneer Automation | Corporate | 60 | 16.3 | 43.7 | 39.5 | 83 | RED | Priya Shah | Sponsor B | North | 27 | 79.51% | 82 | 38.7 | 16 | 3
P015 | Pioneer Transformation | Digital | 178.7 | 22.8 | 47.3 | 81.2 | 81 | RED | Sanjay Kumar | Sponsor A | North | 34 | 64.59% | 58 | 91.4 | 6 | 3
P054 | Quantum Integration | Quality | 116 | 36.1 | 29.5 | 85 | 81 | RED | Rohit Nair | Sponsor A | East | 23 | 62.98% | 66 | 81.5 | 5 | 3
P011 | Helix Transformation | ESG | 236.2 | 53.7 | 12.3 | 88 | 80 | RED | Karan Rao | Sponsor A | South | 17 | 99.11% | 82 | 114.1 | 2 | 0
P024 | Orion Expansion | Manufacturing | 224 | 75.9 | 19.8 | 40 | 79 | RED | Karan Rao | Sponsor B | South | 26 | 96.63% | 98 | 100.8 | 19 | 3
P096 | Matrix Modernisation | Manufacturing | 113.4 | 26.9 | 10.3 | 28 | 79 | RED | Sanjay Kumar | Sponsor B | North | 33 | 69.46% | 76 | 60.7 | 19 | 3
P071 | Helix Automation | Technology | 146.4 | 30.3 | 43.7 | 88 | 78 | RED | Priya Shah | Sponsor D | West | 6 | 74.94% | 95 | 61.5 | 5 | 0
P086 | Pulse Modernisation | Digital | 105.2 | 24.2 | 21.7 | 47.2 | 78 | RED | Neha Kapoor | Sponsor E | West | 17 | 96.46% | 74 | 57.7 | 12 | 1
P087 | Horizon Modernisation | Product | 223.4 | 66.3 | 52.8 | 71 | 77 | RED | Arjun Mehta | Sponsor C | East | 23 | 95.09% | 96 | 139.8 | 9 | 0
P084 | Orion Modernisation | Sales | 271.7 | 56.8 | 18.6 | 75.3 | 76 | RED | Arjun Mehta | Sponsor A | Central | 15 | 68.7% | 69 | 152.7 | 5 | 0
P091 | Helix Modernisation | Infrastructure | 132.9 | 30.1 | 46.7 | 28.2 | 76 | RED | Sanjay Kumar | Sponsor C | West | 33 | 95.47% | 72 | 68.6 | 19 | 3
P098 | Voyage Modernisation | Supply Chain | 175.8 | 23.4 | 6.2 | 94.8 | 76 | RED | Sanjay Kumar | Sponsor B | North | 38 | 79.18% | 69 | 76.9 | 1 | 0
P040 | Synergy Expansion | Sales | 100.8 | 30.1 | 6.4 | 47.2 | 75 | RED | Meera Joshi | Sponsor E | East | 10 | 91.76% | 61 | 67.5 | 12 | 1
P007 | Horizon Transformation | Technology | 187.9 | 61.8 | 47.7 | 35.7 | 74 | RED | Arjun Mehta | Sponsor A | West | 8 | 87.01% | 58 | 116.8 | 17 | 3
P044 | Orion Integration | Technology | 266.6 | 80.4 | 8.6 | 47 | 72 | RED | Sanjay Kumar | Sponsor E | North | 36 | 62.78% | 95 | 111.7 | 15 | 1
P069 | Nexus Automation | Quality | 233.5 | 67.8 | 7.6 | 80.2 | 72 | RED | Aditi Menon | Sponsor D | West | 13 | 79.31% | 60 | 179.8 | 4 | 0
P072 | Velocity Automation | Supply Chain | 70.1 | 18.2 | 8.6 | 29.8 | 71 | RED | Ananya Iyer | Sponsor B | Central | 10 | 62.92% | 90 | 45.6 | 19 | 3
P083 | Nova Modernisation | Quality | 194.1 | 39.4 | 6.3 | 46 | 69 | RED | Arjun Mehta | Sponsor D | South | 24 | 90.31% | 91 | 91.6 | 14 | 1
P012 | Velocity Transformation | Manufacturing | 136.1 | 17.1 | 8 | 36.2 | 68 | RED | Arjun Mehta | Sponsor D | East | 38 | 91.77% | 72 | 102.8 | 17 | 3
P057 | Elevate Integration | Product | 132.2 | 23.6 | 14.7 | 58.2 | 67 | RED | Neha Kapoor | Sponsor E | North | 24 | 88.27% | 84 | 88.9 | 8 | 0
P048 | Fusion Integration | Manufacturing | 275 | 43.8 | 51.1 | 62.5 | 64 | RED | Arjun Mehta | Sponsor B | North | 16 | 91.99% | 74 | 133.1 | 8 | 0
P010 | Catalyst Transformation | Product | 113.8 | 36 | 34 | 77.7 | 61 | RED | Rohit Nair | Sponsor A | East | 25 | 79.46% | 57 | 54 | 4 | 0
P031 | Helix Expansion | Digital | 136.9 | 37.6 | 26.3 | 70.3 | 59 | RED | Sanjay Kumar | Sponsor D | South | 29 | 99.75% | 62 | 96.2 | 6 | 0
P034 | Quantum Expansion | Technology | 144.9 | 30.4 | 43.9 | 88.3 | 58 | RED | Ananya Iyer | Sponsor B | South | 19 | 68.22% | 55 | 123.8 | 2 | 0
P042 | Atlas Integration | Product | 101.8 | 17.8 | 27.6 | 36 | 58 | RED | Karan Rao | Sponsor A | North | 15 | 93.05% | 74 | 72.8 | 13 | 0
P097 | Elevate Modernisation | Sales | 168.8 | 39.6 | 25.9 | 45 | 57 | RED | Aditi Menon | Sponsor C | South | 27 | 105.7% | 55 | 120 | 11 | 0
P009 | Nexus Transformation | Quality | 54.1 | 16.1 | 19 | 22.2 | 56 | RED | Ananya Iyer | Sponsor E | East | 28 | 63.05% | 68 | 40.6 | 16 | 0
P050 | Catalyst Integration | Technology | 263.8 | 64.1 | 48.1 | 52.3 | 54 | RED | Neha Kapoor | Sponsor E | Central | 7 | 75.43% | 55 | 114.9 | 10 | 0
P081 | Aurora Modernisation | ESG | 236.9 | 43.9 | 15.3 | 42.7 | 54 | RED | Neha Kapoor | Sponsor E | East | 10 | 78.37% | 85 | 99.3 | 11 | 0
P006 | Pulse Transformation | Manufacturing | 241.9 | 56.4 | 13 | 60 | 53 | RED | Arjun Mehta | Sponsor E | South | 13 | 66.3% | 80 | 113.4 | 8 | 0
P017 | Elevate Transformation | Technology | 171.2 | 34.1 | 12.7 | 57 | 52 | RED | Arjun Mehta | Sponsor C | North | 30 | 82.33% | 69 | 113.3 | 9 | 0
P061 | Aurora Automation | Sales | 249.8 | 64.2 | 13.4 | 28 | 52 | RED | Neha Kapoor | Sponsor E | North | 22 | 97.15% | 67 | 131.7 | 14 | 0
P066 | Pulse Automation | Product | 239.6 | 69.8 | 46.2 | 50.7 | 52 | RED | Vivek Singh | Sponsor B | Central | 30 | 64.38% | 64 | 135.4 | 10 | 0
P063 | Nova Automation | Technology | 217.8 | 69.6 | 23.4 | 49.7 | 51 | RED | Arjun Mehta | Sponsor E | West | 26 | 73.62% | 57 | 174.6 | 10 | 0
P082 | Atlas Modernisation | Corporate | 308.8 | 97.1 | 13.7 | 37 | 50 | RED | Ananya Iyer | Sponsor B | North | 38 | 96.08% | 80 | 140.8 | 13 | 0
P093 | Summit Modernisation | Infrastructure | 298 | 37.7 | 30.9 | 30.8 | 46 | RED | Arjun Mehta | Sponsor C | West | 10 | 85.09% | 58 | 178.7 | 14 | 0
P004 | Orion Transformation | Sales | 141.7 | 19.8 | 44.7 | 19.8 | 43 | RED | Karan Rao | Sponsor A | West | 30 | 73.8% | 56 | 121.4 | 16 | 0
P049 | Nexus Integration | Manufacturing | 76.6 | 19.3 | 62.4 | 42 | 43 | RED | Priya Shah | Sponsor D | West | 6 | 65.34% | 80 | 53.1 | 12 | 0
P058 | Voyage Integration | ESG | 62.6 | 16 | 11.9 | 59.8 | 43 | RED | Karan Rao | Sponsor E | Central | 19 | 85.88% | 94 | 36.4 | 10 | 0
P002 | Atlas Transformation | Manufacturing | 239.3 | 51.6 | 35.6 | 45.3 | 42 | RED | Ananya Iyer | Sponsor C | West | 19 | 92.22% | 90 | 161.2 | 12 | 0
P027 | Horizon Expansion | Manufacturing | 244.7 | 55.3 | 21.3 | 43 | 42 | RED | Vivek Singh | Sponsor E | West | 8 | 72.45% | 70 | 152.2 | 11 | 0
P064 | Orion Automation | Quality | 101.3 | 31.3 | 38.1 | 43.8 | 42 | RED | Karan Rao | Sponsor D | West | 36 | 85.55% | 59 | 50.6 | 11 | 0
P060 | Synergy Integration | ESG | 285.3 | 96.7 | 44.2 | 21 | 40 | RED | Sanjay Kumar | Sponsor D | West | 29 | 71.85% | 64 | 157 | 16 | 0
P055 | Pioneer Integration | ESG | 239.3 | 43.7 | 46.8 | 50.7 | 39 | RED | Rohit Nair | Sponsor E | South | 20 | 82.9% | 95 | 147.4 | 12 | 0
P014 | Quantum Transformation | Product | 149 | 28 | 14.8 | 31 | 38 | RED | Ananya Iyer | Sponsor B | West | 11 | 95.66% | 91 | 111.5 | 15 | 0
P070 | Catalyst Automation | Digital | 95.1 | 13.7 | 47.1 | 35.2 | 35 | RED | Meera Joshi | Sponsor A | Central | 21 | 78.79% | 61 | 41.3 | 13 | 0
P065 | Vertex Automation | Sales | 208.5 | 55.6 | 13.6 | 36.8 | 32 | RED | Karan Rao | Sponsor B | North | 27 | 94.31% | 64 | 169.4 | 13 | 0
P021 | Aurora Expansion | Manufacturing | 83 | 16.9 | 63.5 | 44.2 | 31 | RED | Karan Rao | Sponsor A | North | 19 | 94.92% | 82 | 66.2 | 11 | 0
P036 | Matrix Expansion | Technology | 96.7 | 16.5 | 63.3 | 46.8 | 31 | RED | Arjun Mehta | Sponsor B | Central | 36 | 68.93% | 67 | 56.6 | 11 | 0
P062 | Atlas Automation | Sales | 415.6 | 122.9 | 50.2 | 40.3 | 31 | RED | Vivek Singh | Sponsor B | Central | 10 | 84.96% | 64 | 174 | 12 | 0
P051 | Helix Integration | ESG | 102.6 | 18.3 | 35.5 | 24.5 | 30 | RED | Aditi Menon | Sponsor E | Central | 13 | 100.2% | 73 | 66.7 | 15 | 0
P029 | Nexus Expansion | Manufacturing | 140.7 | 28.6 | 48.8 | 45.7 | 28 | RED | Rohit Nair | Sponsor C | West | 17 | 62.3% | 55 | 99.4 | 11 | 0
P092 | Velocity Modernisation | Infrastructure | 189.6 | 33.4 | 6 | 78.7 | 28 | RED | Sanjay Kumar | Sponsor C | North | 14 | 106.3% | 61 | 97.7 | 4 | 0
P022 | Atlas Expansion | Quality | 200.3 | 26.8 | 14.9 | 25 | 23 | RED | Karan Rao | Sponsor E | West | 7 | 73.69% | 97 | 120.2 | 18 | 0
P003 | Nova Transformation | Quality | 129.4 | 28.9 | 40.3 | 64 | 22 | RED | Sanjay Kumar | Sponsor A | East | 15 | 92.37% | 58 | 56 | 7 | 0
P025 | Vertex Expansion | Infrastructure | 245.2 | 59.9 | 37.5 | 66.7 | 19 | RED | Sanjay Kumar | Sponsor A | East | 12 | 72.39% | 57 | 114.4 | 7 | 0
P056 | Matrix Integration | Sales | 72.2 | 11.5 | 30.7 | 56 | 19 | RED | Sanjay Kumar | Sponsor C | North | 31 | 69.73% | 98 | 38.3 | 12 | 0
P052 | Velocity Integration | Infrastructure | 100.9 | 22.1 | 53 | 90.5 | 18 | RED | Rohit Nair | Sponsor D | West | 34 | 67.87% | 63 | 46.4 | 2 | 0
P028 | Fusion Expansion | Corporate | 328.8 | 67.3 | 34.6 | 67.8 | 17 | RED | Karan Rao | Sponsor D | South | 22 | 73.31% | 60 | 145.5 | 6 | 0
P032 | Velocity Expansion | Digital | 207.6 | 59 | 29.6 | 22 | 17 | RED | Neha Kapoor | Sponsor A | West | 8 | 73.11% | 85 | 159.9 | 16 | 0
P041 | Aurora Integration | Corporate | 306.6 | 39.6 | 62.2 | 34.8 | 17 | RED | Meera Joshi | Sponsor A | Central | 27 | 94.87% | 64 | 154.7 | 13 | 0
P100 | Synergy Modernisation | Product | 101.5 | 30 | 60.6 | 67.8 | 16 | RED | Sanjay Kumar | Sponsor E | South | 17 | 74.87% | 62 | 51.8 | 6 | 0
P033 | Summit Expansion | Product | 220.5 | 55.2 | 33 | 40.5 | 15 | RED | Aditi Menon | Sponsor B | North | 22 | 77.78% | 85 | 136.9 | 12 | 0
P080 | Synergy Automation | Product | 64.7 | 17.5 | 8.9 | 81.2 | 15 | RED | Ananya Iyer | Sponsor A | East | 11 | 74.99% | 60 | 46.9 | 4 | 0
P099 | Vector Modernisation | Supply Chain | 167.9 | 49.2 | 11 | 28.8 | 12 | RED | Rohit Nair | Sponsor D | North | 35 | 103.3% | 75 | 105.6 | 14 | 0
P095 | Pioneer Modernisation | Product | 129.2 | 21.3 | 27.7 | 88.5 | 42 | GREEN | Vivek Singh | Sponsor B | North | 33 | 68.82% | 80 | 60.8 | 2 | 0
P020 | Synergy Transformation | Quality | 281.4 | 43.6 | 11.6 | 73 | 72 | AMBER | Vivek Singh | Sponsor E | North | 19 | 98.44% | 91 | 142.5 | 7 | 0
P043 | Nova Integration | Corporate | 128.5 | 32.5 | 62.3 | 72.8 | 71 | AMBER | Aditi Menon | Sponsor E | West | 33 | 87.87% | 72 | 88.9 | 5 | 0
P001 | Aurora Transformation | Manufacturing | 119.4 | 32.1 | 45.6 | 65.2 | 69 | AMBER | Arjun Mehta | Sponsor E | South | 36 | 97.42% | 67 | 103.5 | 7 | 0
P037 | Elevate Expansion | Product | 166.5 | 52.1 | 47.9 | 74.8 | 66 | AMBER | Vivek Singh | Sponsor B | West | 33 | 91.51% | 88 | 88.7 | 6 | 0
P077 | Elevate Automation | Supply Chain | 208.7 | 35.9 | 59.3 | 75.8 | 65 | AMBER | Vivek Singh | Sponsor D | Central | 11 | 75.31% | 91 | 107.5 | 6 | 0
P074 | Quantum Automation | Technology | 84.6 | 16.5 | 32.1 | 63.5 | 60 | AMBER | Aditi Menon | Sponsor E | West | 27 | 73.74% | 70 | 62 | 7 | 0
P018 | Voyage Transformation | Sales | 162.7 | 25.3 | 54.5 | 79.3 | 59 | AMBER | Priya Shah | Sponsor B | West | 17 | 86.21% | 97 | 104.1 | 7 | 0
P047 | Horizon Integration | ESG | 128.4 | 16.1 | 18.2 | 78.3 | 59 | AMBER | Sanjay Kumar | Sponsor A | South | 30 | 70.32% | 75 | 81.9 | 4 | 0
P023 | Nova Expansion | ESG | 66.1 | 15.1 | 34.3 | 81.2 | 58 | AMBER | Meera Joshi | Sponsor B | Central | 14 | 95.94% | 71 | 35.3 | 4 | 0
P039 | Vector Expansion | Quality | 269.8 | 74.1 | 53.6 | 75.2 | 55 | AMBER | Aditi Menon | Sponsor B | East | 16 | 98.09% | 79 | 133.4 | 5 | 0
P038 | Voyage Expansion | Technology | 242.5 | 57.6 | 42.9 | 75.8 | 51 | AMBER | Sanjay Kumar | Sponsor A | West | 20 | 67.05% | 81 | 104.7 | 5 | 0
P030 | Catalyst Expansion | Manufacturing | 89.4 | 20.8 | 14.9 | 79.7 | 49 | AMBER | Meera Joshi | Sponsor E | Central | 9 | 66.28% | 82 | 77.1 | 4 | 0
P076 | Matrix Automation | Supply Chain | 173.1 | 40.1 | 37 | 88 | 49 | AMBER | Priya Shah | Sponsor E | West | 9 | 64.58% | 77 | 119.1 | 2 | 0
P016 | Matrix Transformation | Supply Chain | 240.2 | 47 | 32.1 | 88.8 | 48 | AMBER | Sanjay Kumar | Sponsor D | Central | 37 | 102.7% | 76 | 172.5 | 2 | 0
P067 | Horizon Automation | Sales | 336.9 | 77.9 | 43.5 | 91.2 | 42 | AMBER | Sanjay Kumar | Sponsor D | East | 23 | 72.94% | 65 | 178.7 | 2 | 0
P073 | Summit Automation | Infrastructure | 199.3 | 54.6 | 56.9 | 88 | 41 | AMBER | Arjun Mehta | Sponsor A | East | 26 | 91.55% | 98 | 155.2 | 6 | 0
P046 | Pulse Integration | Manufacturing | 101.9 | 26.6 | 46.6 | 82.8 | 37 | AMBER | Sanjay Kumar | Sponsor E | North | 24 | 104.8% | 82 | 73.2 | 3 | 0
P068 | Fusion Automation | ESG | 311.9 | 78.5 | 20.9 | 87 | 35 | AMBER | Sanjay Kumar | Sponsor B | East | 16 | 103.5% | 78 | 131.9 | 3 | 0
P005 | Vertex Transformation | Product | 110.7 | 23.8 | 5.6 | 85.3 | 33 | AMBER | Rohit Nair | Sponsor C | West | 31 | 71.17% | 80 | 53.4 | 3 | 0
P026 | Pulse Expansion | Manufacturing | 164.5 | 26.6 | 34.1 | 86.5 | 33 | AMBER | Rohit Nair | Sponsor A | East | 18 | 98.08% | 90 | 135.2 | 4 | 0
P090 | Catalyst Modernisation | Technology | 275.3 | 81.6 | 22.6 | 83 | 31 | AMBER | Vivek Singh | Sponsor A | West | 18 | 91.95% | 80 | 158.7 | 3 | 0
P013 | Summit Transformation | Quality | 161.1 | 43.7 | 34.5 | 64.3 | 24 | AMBER | Meera Joshi | Sponsor C | South | 18 | 93.06% | 66 | 138.9 | 7 | 0
P008 | Fusion Transformation | Quality | 311.3 | 84.3 | 42.5 | 83.2 | 15 | AMBER | Sanjay Kumar | Sponsor B | Central | 27 | 100.2% | 82 | 167 | 3 | 0
P078 | Voyage Automation | Infrastructure | 179.2 | 52.2 | 46.9 | 75.8 | 15 | AMBER | Aditi Menon | Sponsor C | West | 26 | 82.51% | 87 | 96.5 | 5 | 0
P094 | Quantum Modernisation | Product | 105.1 | 15.5 | 63.4 | 85.3 | 12 | AMBER | Arjun Mehta | Sponsor A | South | 31 | 80.45% | 97 | 66.2 | 6 | 0

## 02_Program_Head
SYNERGY ¦ PROGRAM HEAD COCKPIT
Eight intervention lenses — each score is traceable to portfolio data.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
SCHEDULE |  |  |  | COST BASELINE |  |  |  | RISK |  |  |  | RESOURCE
90.71 |  |  |  | 76.8545 |  |  |  | 47.99 |  |  |  | 83.5564
90.71 |  |  |  | 76.8545 |  |  |  | 47.99 |  |  |  | 83.5564
CUSTOMER |  |  |  | PROFITABILITY |  |  |  | EXECUTION |  |  |  | DECISION
75.15 |  |  |  | 23.1455 |  |  |  | 59.1633 |  |  |  | 13
75.15 |  |  |  | 23.1455 |  |  |  | 59.1633 |  |  |  | 13
PORTFOLIO INTERVENTION MATRIX
Function | Projects | Avg Progress | Avg Risk | Avg Customer | Revenue ₹L | Profit ₹L | Red | Amber | Green
Corporate | 5 | 50.4 | 47.6 | 71.6 | 1132.7 | 252.8 | 4 | 1 | 0
Digital | 6 | 56.25 | 59.6667 | 70.6667 | 1105.2 | 206.5 | 6 | 0 | 0
ESG | 10 | 61.8 | 53 | 80.4 | 1755.6 | 404.4 | 7 | 3 | 0
Infrastructure | 8 | 60.2292 | 41.125 | 73.125 | 1545.8 | 354.4 | 6 | 2 | 0
Manufacturing | 15 | 54.9889 | 53.8667 | 77.4667 | 2371 | 536.7 | 11 | 4 | 0
Product | 15 | 64.1444 | 48.8 | 78.8667 | 2281.4 | 546.5 | 11 | 3 | 1
Quality | 11 | 60.1667 | 48.2727 | 74.2727 | 2052.3 | 492.1 | 7 | 4 | 0
Sales | 12 | 53.2083 | 54.9167 | 70.75 | 2622.1 | 640.3 | 10 | 2 | 0
Supply Chain | 6 | 67.6944 | 53.5 | 79.6667 | 1035.8 | 213.8 | 3 | 3 | 0
Technology | 12 | 61.125 | 57.9167 | 71.25 | 2296.6 | 577.1 | 9 | 3 | 0

## 03_Project_360
SYNERGY ¦ PROJECT 360
Select one project — the page becomes the evidence layer behind the executive exception.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
SELECT PROJECT | P001
PROJECT NAME |  |  | SPONSOR |  |  | PROJECT MANAGER |  |  | RAG
Aurora Transformation |  |  | Sponsor E |  |  | Arjun Mehta |  |  | AMBER
REVENUE ₹L |  | PROFIT ₹L |  | PIPELINE ₹L |  | PROGRESS % |  | RISK |  | CUSTOMER
119.4 |  | 32.1 |  | 45.6 |  | 65.1667 |  | 69 |  | 67
WHY THIS PROJECT IS ON THE RADAR
RAG: AMBER • Risk score: 69 • Days risk: 7 • Blocked tasks: 1 • Escalations: 0
TOP TASKS / BLOCKERS | [8 empty] | DECISION + DEPENDENCY SIGNAL
Task | Owner | Priority | Status | Progress | Blocker | Escalation | Due | Hours Used | Executive signal
Requirements & scope freeze | Rahul | High | In Progress | 63 |  | NO | 2026-07-23 | 78 | Decision required when risk, dependency and due-date signals converge. Start with the highest-priority open task, identify its support owner, then quantify the schedule / commercial consequence before escalating.
Design / solution | Karan | High | In Progress | 68 |  | NO | 2026-08-04 | 83
BOM / commercial approval | Meera | Critical | In Progress | 71 |  | NO | 2026-08-14 | 22
Build / execution | Vivek | Critical | In Progress | 69 |  | NO | 2026-09-05 | 105
Testing / validation | Ritu | Critical | In Progress | 48 | Awaiting clarification | NO | 2026-09-06 | 31
Customer acceptance | Sanjay | Medium | In Progress | 72 |  | NO | 2026-10-01 | 22

## 04_PM_Control
SYNERGY ¦ PROJECT MANAGER CONTROL
Detect → Assign → Escalate → Decide → Replan → Verify.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
SELECT PROJECT | P001
OPEN BLOCKERS |  |  | ESCALATIONS |  |  | OVERDUE |  |  | AVG PROGRESS
1 |  |  | 0 |  |  | 5 |  |  | 65.1667
ACTION QUEUE
Task | Owner | Support | Priority | Due | Progress | Blocker | Escalation | Hours Planned | Hours Used | Variance | Recommended action | Status | Last update
Requirements & scope freeze | Rahul | Vivek | High | 2026-07-23 | 63 |  | NO | 21 | 78 | 57 | RECOVER DATE | In Progress | 2026-09-09
Design / solution | Karan | Ritu | High | 2026-08-04 | 68 |  | NO | 80 | 83 | 3 | RECOVER DATE | In Progress | 2026-09-09
BOM / commercial approval | Meera | Sanjay | Critical | 2026-08-14 | 71 |  | NO | 42 | 22 | -20 | RECOVER DATE | In Progress | 2026-09-09
Build / execution | Vivek | Anil | Critical | 2026-09-05 | 69 |  | NO | 25 | 105 | 80 | RECOVER DATE | In Progress | 2026-09-09
Testing / validation | Ritu | Kavya | Critical | 2026-09-06 | 48 | Awaiting clarification | NO | 42 | 31 | -11 | RESOLVE BLOCKER | In Progress | 2026-09-09
Customer acceptance | Sanjay | Rohan | Medium | 2026-10-01 | 72 |  | NO | 83 | 22 | -61 | CONTINUE | In Progress | 2026-09-09
[10 empty] | 0 | RECOVER DATE
[10 empty] | 0 | RECOVER DATE
[10 empty] | 0 | RECOVER DATE
[10 empty] | 0 | RECOVER DATE
Formulas:
TASKS = IF([DECISIONS]="YES","ESCALATE",IF([GANTT]<>"","RESOLVE BLOCKER",IF([PM CONTROL]<TODAY(),"RECOVER DATE","CONTINUE")))

## 05_Team_Command
SYNERGY ¦ TEAM COMMAND
Make the next action explicit: priority, owner, support, due date and escalation.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
FOCUS OWNER | Amit
OPEN TASKS |  |  | CRITICAL / HIGH |  |  | BLOCKERS |  |  | ESCALATIONS
46 |  |  | 18 |  |  | 12 |  |  | 6
MY PRIORITY QUEUE
Project | Task | Priority | Due | Progress | Support | Blocker | Escalation | Status | Hours Used | Last Update | Next action | Project RAG | Days Risk
P006 | Customer acceptance | Medium | 2026-10-05 | 79 | Karan |  | NO | In Progress | 77 | 2026-09-09 | EXECUTE | RED | 8
P007 | Testing / validation | Low | 2026-09-24 | 47 | Karan | Supplier / cross-functional dependency | YES | Blocked | 62 | 2026-09-09 | GET SUPPORT | RED | 17
P008 | Build / execution | Medium | 2026-09-09 | 68 | Karan |  | NO | In Progress | 69 | 2026-09-09 | EXECUTE | AMBER | 3
P009 | BOM / commercial approval | Low | 2026-08-17 | 33 | Karan |  | NO | In Progress | 65 | 2026-09-09 | RECOVER | RED | 16
P010 | Design / solution | Low | 2026-08-12 | 96 | Karan |  | NO | In Progress | 27 | 2026-09-09 | RECOVER | RED | 4
P011 | Requirements & scope freeze | Low | 2026-08-02 | 91 | Karan |  | NO | In Progress | 91 | 2026-09-09 | RECOVER | RED | 2
P018 | Customer acceptance | Low | 2026-10-08 | 74 | Karan |  | NO | In Progress | 68 | 2026-09-09 | EXECUTE | AMBER | 7
P019 | Testing / validation | High | 2026-10-07 | 83 | Karan |  | YES | In Progress | 42 | 2026-09-09 | ESCALATE | RED | 6
P020 | Build / execution | High | 2026-09-24 | 71 | Karan | Awaiting clarification | NO | In Progress | 101 | 2026-09-09 | GET SUPPORT | AMBER | 7
P021 | BOM / commercial approval | Critical | 2026-08-30 | 25 | Karan |  | NO | In Progress | 72 | 2026-09-09 | RECOVER | RED | 11
Formulas:
TASKS = IF([GANTT]<>"","GET SUPPORT",IF([DECISIONS]="YES","ESCALATE",IF([PROJECT 360]<TODAY(),"RECOVER","EXECUTE")))

## 06_Gantt
SYNERGY ¦ GANTT COMMAND VIEW
A fully populated portfolio timeline + selected-project task Gantt. Bars are date-driven from the task/project data.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
PORTFOLIO GANTT — 100 PROJECTS
ID | Project | Function | PM | RAG | Progress % | Risk | Start | Finish | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30
P001 | Aurora Transformation | Manufacturing | Arjun Mehta | AMBER | 65.2 | 69 | 2026-07-01 | 2026-09-30 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P002 | Atlas Transformation | Manufacturing | Ananya Iyer | RED | 45.3 | 42 | 2026-07-02 | 2026-09-23 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P003 | Nova Transformation | Quality | Sanjay Kumar | RED | 64 | 22 | 2026-07-03 | 2026-10-25 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P004 | Orion Transformation | Sales | Karan Rao | RED | 19.8 | 43 | 2026-07-04 | 2026-10-15 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P005 | Vertex Transformation | Product | Rohit Nair | AMBER | 85.3 | 33 | 2026-07-05 | 2026-11-09 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P006 | Pulse Transformation | Manufacturing | Arjun Mehta | RED | 60 | 53 | 2026-07-06 | 2026-09-28 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P007 | Horizon Transformation | Technology | Arjun Mehta | RED | 35.7 | 74 | 2026-07-07 | 2026-10-03 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P008 | Fusion Transformation | Quality | Sanjay Kumar | AMBER | 83.2 | 15 | 2026-07-08 | 2026-11-25 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P009 | Nexus Transformation | Quality | Ananya Iyer | RED | 22.2 | 56 | 2026-07-09 | 2026-10-05 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P010 | Catalyst Transformation | Product | Rohit Nair | RED | 77.7 | 61 | 2026-07-10 | 2026-10-29 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P011 | Helix Transformation | ESG | Karan Rao | RED | 88 | 80 | 2026-07-11 | 2026-12-07 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P012 | Velocity Transformation | Manufacturing | Arjun Mehta | RED | 36.2 | 68 | 2026-07-12 | 2026-09-22 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P013 | Summit Transformation | Quality | Meera Joshi | AMBER | 64.3 | 24 | 2026-07-13 | 2026-10-13 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P014 | Quantum Transformation | Product | Ananya Iyer | RED | 31 | 38 | 2026-07-14 | 2026-10-02 |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P015 | Pioneer Transformation | Digital | Sanjay Kumar | RED | 81.2 | 81 | 2026-07-15 | 2026-09-13 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P016 | Matrix Transformation | Supply Chain | Sanjay Kumar | AMBER | 88.8 | 48 | 2026-07-16 | 2026-12-15 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P017 | Elevate Transformation | Technology | Arjun Mehta | RED | 57 | 52 | 2026-07-17 | 2026-10-22 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P018 | Voyage Transformation | Sales | Priya Shah | AMBER | 79.3 | 59 | 2026-07-18 | 2026-09-26 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P019 | Vector Transformation | ESG | Sanjay Kumar | RED | 84.8 | 92 | 2026-07-19 | 2026-11-19 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P020 | Synergy Transformation | Quality | Vivek Singh | AMBER | 73 | 72 | 2026-07-20 | 2026-11-03 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P021 | Aurora Expansion | Manufacturing | Karan Rao | RED | 44.2 | 31 | 2026-07-21 | 2026-11-23 |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P022 | Atlas Expansion | Quality | Karan Rao | RED | 25 | 23 | 2026-07-22 | 2026-09-20 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P023 | Nova Expansion | ESG | Meera Joshi | AMBER | 81.2 | 58 | 2026-07-23 | 2026-09-21 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P024 | Orion Expansion | Manufacturing | Karan Rao | RED | 40 | 79 | 2026-07-24 | 2026-09-19 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P025 | Vertex Expansion | Infrastructure | Sanjay Kumar | RED | 66.7 | 19 | 2026-07-25 | 2026-10-19 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P026 | Pulse Expansion | Manufacturing | Rohit Nair | AMBER | 86.5 | 33 | 2026-07-26 | 2026-12-10 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P027 | Horizon Expansion | Manufacturing | Vivek Singh | RED | 43 | 42 | 2026-07-27 | 2026-12-22 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P028 | Fusion Expansion | Corporate | Karan Rao | RED | 67.8 | 17 | 2026-07-28 | 2026-09-28 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P029 | Nexus Expansion | Manufacturing | Rohit Nair | RED | 45.7 | 28 | 2026-07-29 | 2026-10-31 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P030 | Catalyst Expansion | Manufacturing | Meera Joshi | AMBER | 79.7 | 49 | 2026-07-30 | 2026-11-03 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P031 | Helix Expansion | Digital | Sanjay Kumar | RED | 70.3 | 59 | 2026-07-31 | 2026-12-05 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P032 | Velocity Expansion | Digital | Neha Kapoor | RED | 22 | 17 | 2026-08-01 | 2026-11-28 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P033 | Summit Expansion | Product | Aditi Menon | RED | 40.5 | 15 | 2026-08-02 | 2026-10-26 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P034 | Quantum Expansion | Technology | Ananya Iyer | RED | 88.3 | 58 | 2026-08-03 | 2026-11-19 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P035 | Pioneer Expansion | Sales | Meera Joshi | RED | 47.2 | 86 | 2026-08-04 | 2026-12-15 |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P036 | Matrix Expansion | Technology | Arjun Mehta | RED | 46.8 | 31 | 2026-08-05 | 2026-11-07 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P037 | Elevate Expansion | Product | Vivek Singh | AMBER | 74.8 | 66 | 2026-08-06 | 2026-12-06 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P038 | Voyage Expansion | Technology | Sanjay Kumar | AMBER | 75.8 | 51 | 2026-08-07 | 2026-12-16 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P039 | Vector Expansion | Quality | Aditi Menon | AMBER | 75.2 | 55 | 2026-08-08 | 2026-10-16 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P040 | Synergy Expansion | Sales | Meera Joshi | RED | 47.2 | 75 | 2026-08-09 | 2026-11-18 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P041 | Aurora Integration | Corporate | Meera Joshi | RED | 34.8 | 17 | 2026-08-10 | 2026-10-08 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P042 | Atlas Integration | Product | Karan Rao | RED | 36 | 58 | 2026-08-11 | 2026-10-23 | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P043 | Nova Integration | Corporate | Aditi Menon | AMBER | 72.8 | 71 | 2026-08-12 | 2027-01-08 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P044 | Orion Integration | Technology | Sanjay Kumar | RED | 47 | 72 | 2026-08-13 | 2026-11-17 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P045 | Vertex Integration | Technology | Arjun Mehta | RED | 46.3 | 83 | 2026-08-14 | 2026-12-24 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P046 | Pulse Integration | Manufacturing | Sanjay Kumar | AMBER | 82.8 | 37 | 2026-08-15 | 2027-01-17 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P047 | Horizon Integration | ESG | Sanjay Kumar | AMBER | 78.3 | 59 | 2026-08-16 | 2026-10-20 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P048 | Fusion Integration | Manufacturing | Arjun Mehta | RED | 62.5 | 64 | 2026-08-17 | 2027-01-02 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P049 | Nexus Integration | Manufacturing | Priya Shah | RED | 42 | 43 | 2026-08-18 | 2026-10-20 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P050 | Catalyst Integration | Technology | Neha Kapoor | RED | 52.3 | 54 | 2026-08-19 | 2027-01-05 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P051 | Helix Integration | ESG | Aditi Menon | RED | 24.5 | 30 | 2026-08-20 | 2026-10-23 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P052 | Velocity Integration | Infrastructure | Rohit Nair | RED | 90.5 | 18 | 2026-08-21 | 2026-12-15 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P053 | Summit Integration | Manufacturing | Aditi Menon | RED | 63.8 | 91 | 2026-08-22 | 2026-12-10 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P054 | Quantum Integration | Quality | Rohit Nair | RED | 85 | 81 | 2026-08-23 | 2026-12-27 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P055 | Pioneer Integration | ESG | Rohit Nair | RED | 50.7 | 39 | 2026-08-24 | 2027-01-16 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P056 | Matrix Integration | Sales | Sanjay Kumar | RED | 56 | 19 | 2026-08-25 | 2026-11-21 | [7 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P057 | Elevate Integration | Product | Neha Kapoor | RED | 58.2 | 67 | 2026-08-26 | 2026-11-04 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P058 | Voyage Integration | ESG | Karan Rao | RED | 59.8 | 43 | 2026-08-27 | 2026-11-18 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P059 | Vector Integration | Product | Rohit Nair | RED | 42.8 | 88 | 2026-08-28 | 2026-12-02 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P060 | Synergy Integration | ESG | Sanjay Kumar | RED | 21 | 40 | 2026-08-29 | 2027-01-17 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P061 | Aurora Automation | Sales | Neha Kapoor | RED | 28 | 52 | 2026-08-30 | 2026-10-26 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P062 | Atlas Automation | Sales | Vivek Singh | RED | 40.3 | 31 | 2026-08-31 | 2026-12-27 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P063 | Nova Automation | Technology | Arjun Mehta | RED | 49.7 | 51 | 2026-09-01 | 2027-02-02 | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P064 | Orion Automation | Quality | Karan Rao | RED | 43.8 | 42 | 2026-09-02 | 2027-01-21 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P065 | Vertex Automation | Sales | Karan Rao | RED | 36.8 | 32 | 2026-09-03 | 2026-12-21 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P066 | Pulse Automation | Product | Vivek Singh | RED | 50.7 | 52 | 2026-09-04 | 2027-01-15 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P067 | Horizon Automation | Sales | Sanjay Kumar | AMBER | 91.2 | 42 | 2026-09-05 | 2027-02-02 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P068 | Fusion Automation | ESG | Sanjay Kumar | AMBER | 87 | 35 | 2026-09-06 | 2026-11-08 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P069 | Nexus Automation | Quality | Aditi Menon | RED | 80.2 | 72 | 2026-09-07 | 2027-01-01 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P070 | Catalyst Automation | Digital | Meera Joshi | RED | 35.2 | 35 | 2026-09-08 | 2026-11-19 | [9 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P071 | Helix Automation | Technology | Priya Shah | RED | 88 | 78 | 2026-09-09 | 2026-12-02 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P072 | Velocity Automation | Supply Chain | Ananya Iyer | RED | 29.8 | 71 | 2026-09-10 | 2026-11-06 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P073 | Summit Automation | Infrastructure | Arjun Mehta | AMBER | 88 | 41 | 2026-09-11 | 2027-01-08 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P074 | Quantum Automation | Technology | Aditi Menon | AMBER | 63.5 | 60 | 2026-09-12 | 2026-12-08 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P075 | Pioneer Automation | Corporate | Priya Shah | RED | 39.5 | 83 | 2026-09-13 | 2026-11-29 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P076 | Matrix Automation | Supply Chain | Priya Shah | AMBER | 88 | 49 | 2026-09-14 | 2026-12-29 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P077 | Elevate Automation | Supply Chain | Vivek Singh | AMBER | 75.8 | 65 | 2026-09-15 | 2026-12-17 | [10 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P078 | Voyage Automation | Infrastructure | Aditi Menon | AMBER | 75.8 | 15 | 2026-09-16 | 2027-02-02 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P079 | Vector Automation | Infrastructure | Aditi Menon | RED | 23.2 | 86 | 2026-09-17 | 2026-11-15 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P080 | Synergy Automation | Product | Ananya Iyer | RED | 81.2 | 15 | 2026-09-18 | 2026-12-13 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P081 | Aurora Modernisation | ESG | Neha Kapoor | RED | 42.7 | 54 | 2026-09-19 | 2027-01-15 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P082 | Atlas Modernisation | Corporate | Ananya Iyer | RED | 37 | 50 | 2026-09-20 | 2026-12-10 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P083 | Nova Modernisation | Quality | Arjun Mehta | RED | 46 | 69 | 2026-09-21 | 2027-02-21 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P084 | Orion Modernisation | Sales | Arjun Mehta | RED | 75.3 | 76 | 2026-09-22 | 2026-12-02 | [11 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P085 | Vertex Modernisation | Sales | Neha Kapoor | RED | 72.3 | 87 | 2026-09-23 | 2027-02-23 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P086 | Pulse Modernisation | Digital | Neha Kapoor | RED | 47.2 | 78 | 2026-09-24 | 2026-12-07 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P087 | Horizon Modernisation | Product | Arjun Mehta | RED | 71 | 77 | 2026-09-25 | 2026-11-28 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P088 | Fusion Modernisation | Product | Sanjay Kumar | RED | 71.3 | 92 | 2026-09-26 | 2027-02-26 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P089 | Nexus Modernisation | Digital | Meera Joshi | RED | 81.7 | 88 | 2026-09-27 | 2026-11-28 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P090 | Catalyst Modernisation | Technology | Vivek Singh | AMBER | 83 | 31 | 2026-09-28 | 2026-12-17 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P091 | Helix Modernisation | Infrastructure | Sanjay Kumar | RED | 28.2 | 76 | 2026-09-29 | 2027-01-14 | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P092 | Velocity Modernisation | Infrastructure | Sanjay Kumar | RED | 78.7 | 28 | 2026-09-30 | 2026-12-17 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P093 | Summit Modernisation | Infrastructure | Arjun Mehta | RED | 30.8 | 46 | 2026-10-01 | 2026-12-01 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P094 | Quantum Modernisation | Product | Arjun Mehta | AMBER | 85.3 | 12 | 2026-10-02 | 2027-03-05 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P095 | Pioneer Modernisation | Product | Vivek Singh | GREEN | 88.5 | 42 | 2026-10-03 | 2027-02-22 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P096 | Matrix Modernisation | Manufacturing | Sanjay Kumar | RED | 28 | 79 | 2026-10-04 | 2026-12-20 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P097 | Elevate Modernisation | Sales | Aditi Menon | RED | 45 | 57 | 2026-10-05 | 2027-01-07 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P098 | Voyage Modernisation | Supply Chain | Sanjay Kumar | RED | 94.8 | 76 | 2026-10-06 | 2026-12-10 | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P099 | Vector Modernisation | Supply Chain | Rohit Nair | RED | 28.8 | 12 | 2026-10-07 | 2026-12-19 | [14 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
P100 | Synergy Modernisation | Product | Sanjay Kumar | RED | 67.8 | 16 | 2026-10-08 | 2026-12-23 | [14 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
SELECTED PROJECT TASK GANTT |  | Project ID | P001
Task | Owner | Priority | Status | Progress % | Start | Due | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30
Requirements & scope freeze | Rahul | High | In Progress | 63 | 2026-07-01 | 2026-07-23 | ■ | ■ | ■ | ■
Design / solution | Karan | High | In Progress | 68 | 2026-07-15 | 2026-08-04 |  |  | ■ | ■ | ■
BOM / commercial approval | Meera | Critical | In Progress | 71 | 2026-07-29 | 2026-08-14 |  |  |  |  | ■ | ■ | ■
Build / execution | Vivek | Critical | In Progress | 69 | 2026-08-12 | 2026-09-05 | [6 empty] | ■ | ■ | ■ | ■
Testing / validation | Ritu | Critical | In Progress | 48 | 2026-08-26 | 2026-09-06 | [8 empty] | ■ | ■
Customer acceptance | Sanjay | Medium | In Progress | 72 | 2026-09-09 | 2026-10-01 | [10 empty] | ■ | ■ | ■ | ■
Legend | GREEN = healthy | AMBER = watch | RED = intervention

## 07_Decision_Hub
SYNERGY ¦ DECISION HUB
Turn blockers and dependencies into quantified decisions with an owner and due date.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
ID | Project | Decision / Issue | Decision Owner | Need By | Status | Time Impact d | Cost Impact ₹L | Revenue at Risk ₹L | Recommended Option | Decision | Date | Escalation | Evidence
D001 | P001 | Testing / validation — intervention required | Arjun Mehta | 2026-09-06 | Pending | 3 | 2.1 | 3.6 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D002 | P002 | Requirements & scope freeze — intervention required | Ananya Iyer | 2026-07-22 | Pending | 49 | 3.2 | 7.2 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D003 | P003 | Requirements & scope freeze — intervention required | Sanjay Kumar | 2026-07-24 | Pending | 47 | 1.1 | 3.9 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D004 | P003 | BOM / commercial approval — intervention required | Sanjay Kumar | 2026-08-14 | Pending | 26 | 1.1 | 3.9 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D005 | P004 | Customer acceptance — intervention required | Karan Rao | 2026-09-24 | Pending | 1 | 2.4 | 4.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D006 | P005 | Design / solution — intervention required | Rohit Nair | 2026-08-01 | Pending | 39 | 1.1 | 3.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D007 | P005 | Testing / validation — intervention required | Rohit Nair | 2026-09-23 | Pending | 1 | 1.1 | 3.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D008 | P006 | Requirements & scope freeze — intervention required | Arjun Mehta | 2026-07-30 | Pending | 41 | 2.3 | 7.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D009 | P006 | Design / solution — intervention required | Arjun Mehta | 2026-08-01 | Pending | 39 | 2.3 | 7.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D010 | P006 | Testing / validation — intervention required | Arjun Mehta | 2026-09-20 | Pending | 1 | 2.3 | 7.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D011 | P007 | Build / execution — intervention required | Arjun Mehta | 2026-09-04 | Pending | 5 | 2.3 | 5.6 | Resolve owner/support interface | Pending |  | YES | Supplier / cross-functional dependency
D012 | P007 | Testing / validation — intervention required | Arjun Mehta | 2026-09-24 | Pending | 1 | 2.3 | 5.6 | Resolve owner/support interface | Pending |  | YES | Supplier / cross-functional dependency
D013 | P007 | Customer acceptance — intervention required | Arjun Mehta | 2026-09-27 | Pending | 1 | 2.3 | 5.6 | Resolve owner/support interface | Pending |  | YES | Supplier / cross-functional dependency
D014 | P008 | BOM / commercial approval — intervention required | Sanjay Kumar | 2026-08-25 | Pending | 15 | 3.3 | 9.3 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D015 | P009 | Design / solution — intervention required | Ananya Iyer | 2026-08-02 | Pending | 38 | 0.8 | 1.6 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D016 | P009 | Customer acceptance — intervention required | Ananya Iyer | 2026-09-30 | Pending | 1 | 0.8 | 1.6 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D017 | P010 | Build / execution — intervention required | Rohit Nair | 2026-09-05 | Pending | 4 | 1.1 | 3.4 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D018 | P011 | Design / solution — intervention required | Karan Rao | 2026-08-12 | Pending | 28 | 2.3 | 7.1 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D019 | P011 | Build / execution — intervention required | Karan Rao | 2026-09-09 | Pending | 1 | 2.3 | 7.1 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification
D020 | P012 | BOM / commercial approval — intervention required | Arjun Mehta | 2026-08-23 | Pending | 17 | 2.1 | 4.1 | Resolve owner/support interface | Pending |  | NO | Awaiting clarification

## 08_Dependency_Radar
SYNERGY ¦ DEPENDENCY RADAR
Cross-functional interfaces: who is waiting, who owns the handoff, and what is exposed.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
ID | Project | Dependency / Interface | From | To / Owner | Due | Status | Impact | Days Waiting | Critical Path | Action | Last Update
DP001 | P001 | Requirements & scope freeze | Rahul | Vivek | 2026-07-23 | Open | Schedule / handoff | 48 | YES | Confirm handoff + response | 2026-09-09
DP002 | P001 | Design / solution | Karan | Ritu | 2026-08-04 | Open | Schedule / handoff | 36 | YES | Confirm handoff + response | 2026-09-09
DP003 | P001 | BOM / commercial approval | Meera | Sanjay | 2026-08-14 | Open | Schedule / handoff | 26 | YES | Confirm handoff + response | 2026-09-09
DP004 | P001 | Build / execution | Vivek | Anil | 2026-09-05 | Open | Schedule / handoff | 4 | YES | Confirm handoff + response | 2026-09-09
DP005 | P001 | Testing / validation | Ritu | Kavya | 2026-09-06 | Open | Schedule / handoff | 3 | YES | Confirm handoff + response | 2026-09-09
DP006 | P001 | Customer acceptance | Sanjay | Rohan | 2026-10-01 | Open | Schedule / handoff | 0 | NO | Confirm handoff + response | 2026-09-09
DP007 | P002 | Requirements & scope freeze | Karan | Ritu | 2026-07-22 | Open | Schedule / handoff | 49 | YES | Confirm handoff + response | 2026-09-09
DP008 | P002 | Design / solution | Meera | Sanjay | 2026-08-09 | Open | Schedule / handoff | 31 | YES | Confirm handoff + response | 2026-09-09
DP009 | P002 | BOM / commercial approval | Vivek | Anil | 2026-08-10 | Open | Schedule / handoff | 30 | YES | Confirm handoff + response | 2026-09-09
DP010 | P002 | Build / execution | Ritu | Kavya | 2026-08-28 | Open | Schedule / handoff | 12 | YES | Confirm handoff + response | 2026-09-09
DP011 | P002 | Testing / validation | Sanjay | Rohan | 2026-09-16 | Open | Schedule / handoff | 0 | YES | Confirm handoff + response | 2026-09-09
DP012 | P002 | Customer acceptance | Anil | Deepa | 2026-09-25 | Open | Schedule / handoff | 0 | NO | Confirm handoff + response | 2026-09-09
DP013 | P003 | Requirements & scope freeze | Meera | Sanjay | 2026-07-24 | Open | Schedule / handoff | 47 | YES | Confirm handoff + response | 2026-09-09
DP014 | P003 | Design / solution | Vivek | Anil | 2026-07-27 | Open | Schedule / handoff | 44 | YES | Confirm handoff + response | 2026-09-09
DP015 | P003 | BOM / commercial approval | Ritu | Kavya | 2026-08-14 | Open | Schedule / handoff | 26 | NO | Confirm handoff + response | 2026-09-09
DP016 | P003 | Build / execution | Sanjay | Rohan | 2026-09-07 | Open | Schedule / handoff | 2 | YES | Confirm handoff + response | 2026-09-09
DP017 | P003 | Testing / validation | Anil | Deepa | 2026-09-06 | Open | Schedule / handoff | 3 | YES | Confirm handoff + response | 2026-09-09
DP018 | P003 | Customer acceptance | Kavya | Amit | 2026-10-01 | Open | Schedule / handoff | 0 | NO | Confirm handoff + response | 2026-09-09
DP019 | P004 | Requirements & scope freeze | Vivek | Anil | 2026-07-19 | Open | Schedule / handoff | 52 | YES | Confirm handoff + response | 2026-09-09
DP020 | P004 | Design / solution | Ritu | Kavya | 2026-07-29 | Open | Schedule / handoff | 42 | NO | Confirm handoff + response | 2026-09-09
DP021 | P004 | BOM / commercial approval | Sanjay | Rohan | 2026-08-22 | Open | Schedule / handoff | 18 | NO | Confirm handoff + response | 2026-09-09
DP022 | P004 | Build / execution | Anil | Deepa | 2026-09-05 | Open | Schedule / handoff | 4 | NO | Confirm handoff + response | 2026-09-09
DP023 | P004 | Testing / validation | Kavya | Amit | 2026-09-16 | Open | Schedule / handoff | 0 | YES | Confirm handoff + response | 2026-09-09
DP024 | P004 | Customer acceptance | Rohan | Priya | 2026-09-24 | Open | Schedule / handoff | 0 | NO | Confirm handoff + response | 2026-09-09
DP025 | P005 | Requirements & scope freeze | Ritu | Kavya | 2026-07-29 | Open | Schedule / handoff | 42 | NO | Confirm handoff + response | 2026-09-09
DP026 | P005 | Design / solution | Sanjay | Rohan | 2026-08-01 | Open | Schedule / handoff | 39 | YES | Confirm handoff + response | 2026-09-09
DP027 | P005 | BOM / commercial approval | Anil | Deepa | 2026-08-13 | Open | Schedule / handoff | 27 | YES | Confirm handoff + response | 2026-09-09
DP028 | P005 | Build / execution | Kavya | Amit | 2026-09-01 | Open | Schedule / handoff | 8 | YES | Confirm handoff + response | 2026-09-09
DP029 | P005 | Testing / validation | Rohan | Priya | 2026-09-23 | Open | Schedule / handoff | 0 | YES | Confirm handoff + response | 2026-09-09
DP030 | P005 | Customer acceptance | Deepa | Rahul | 2026-09-26 | Open | Schedule / handoff | 0 | NO | Confirm handoff + response | 2026-09-09

## 09_Change_Control
SYNERGY ¦ CHANGE CONTROL
Make scope change visible before it becomes rework, overload or deadline pressure.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
ID | Project | Change Request | Owner | Raised | Urgency | Scope Δ % | Resource Δ | Days Δ | Cost Δ ₹L | Decision | Status
CH001 | P019 | Scope / priority recalibration | Sanjay Kumar | 2026-09-09 | High | 2 | 1 | 4 | 0.6 | Pending | Open
CH002 | P088 | Scope / priority recalibration | Sanjay Kumar | 2026-09-09 | High | 3.6 | 1.7 | 5 | 0.9 | Pending | Open
CH003 | P053 | Scope / priority recalibration | Aditi Menon | 2026-09-09 | High | 4.5 | 1.6 | 6 | 0.7 | Pending | Open
CH004 | P059 | Scope / priority recalibration | Rohit Nair | 2026-09-09 | High | 7.2 | 1.4 | 9 | 1.6 | Pending | Open
CH005 | P089 | Scope / priority recalibration | Meera Joshi | 2026-09-09 | High | 2.3 | 1 | 4 | 1.8 | Pending | Open
CH006 | P085 | Scope / priority recalibration | Neha Kapoor | 2026-09-09 | High | 3.5 | 1.8 | 6 | 1.5 | Pending | Open
CH007 | P035 | Scope / priority recalibration | Meera Joshi | 2026-09-09 | High | 6.6 | 1.2 | 8 | 1.1 | Pending | Open
CH008 | P079 | Scope / priority recalibration | Aditi Menon | 2026-09-09 | High | 9.6 | 1 | 11 | 0.9 | Pending | Open
CH009 | P045 | Scope / priority recalibration | Arjun Mehta | 2026-09-09 | High | 6.7 | 1.6 | 8 | 0.8 | Pending | Open
CH010 | P075 | Scope / priority recalibration | Priya Shah | 2026-09-09 | High | 7.6 | 1.4 | 9 | 0.4 | Pending | Open
CH011 | P015 | Scope / priority recalibration | Sanjay Kumar | 2026-09-09 | High | 2.3 | 1.7 | 4 | 0.9 | Pending | Open
CH012 | P054 | Scope / priority recalibration | Rohit Nair | 2026-09-09 | High | 2 | 1.2 | 3 | 0.8 | Pending | Open
CH013 | P011 | Scope / priority recalibration | Karan Rao | 2026-09-09 | High | 2 | 1 | 2 | 1.1 | Pending | Open
CH014 | P024 | Scope / priority recalibration | Karan Rao | 2026-09-09 | High | 7.5 | 1.3 | 10 | 1 | Pending | Open
CH015 | P096 | Scope / priority recalibration | Sanjay Kumar | 2026-09-09 | High | 9 | 1.7 | 10 | 0.6 | Pending | Open
CH016 | P071 | Scope / priority recalibration | Priya Shah | 2026-09-09 | High | 2 | 1 | 3 | 0.6 | Pending | Open
CH017 | P086 | Scope / priority recalibration | Neha Kapoor | 2026-09-09 | High | 6.6 | 1 | 7 | 0.6 | Pending | Open
CH018 | P087 | Scope / priority recalibration | Arjun Mehta | 2026-09-09 | High | 3.6 | 1.2 | 5 | 1.4 | Pending | Open
CH019 | P084 | Scope / priority recalibration | Arjun Mehta | 2026-09-09 | High | 3.1 | 1 | 3 | 1.5 | Pending | Open
CH020 | P091 | Scope / priority recalibration | Sanjay Kumar | 2026-09-09 | High | 9 | 1.7 | 10 | 0.7 | Pending | Open

## 10_Project_Data
DATA ENGINE ¦ PROJECT MASTER | [24 empty] | DATA QUALITY HELPER
100 project records • calculated operational roll-ups • yellow cells are baseline/planning inputs. | [24 empty] | Duplicate flag: 1 when an ID repeats.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
Project ID | Project Name | Function | Program | Region | Sponsor | Project Manager | Budget ₹L | Start | Finish | Revenue ₹L | Profit ₹L | Pipeline ₹L | Resources | Utilization % | Risk Score | Customer Health | Strategic Type | Margin % | Progress % | Blocked Tasks | Open Escalations | Days Risk | Overall RAG | Data Check | Duplicate ID Flag
P001 | Aurora Transformation | Manufacturing | Growth | South | Sponsor E | Arjun Mehta | 103.5 | 2026-07-01 | 2026-09-30 | 119.4 | 32.1 | 45.6 | 36 | 97.42% | 69 | 67 | Growth | 26.88% | 6517% | 1 | 0 | 7 | AMBER | PASS | 0
P002 | Atlas Transformation | Manufacturing | Run | West | Sponsor C | Ananya Iyer | 161.2 | 2026-07-02 | 2026-09-23 | 239.3 | 51.6 | 35.6 | 19 | 92.22% | 42 | 90 | Mandatory | 21.55% | 4533% | 1 | 0 | 12 | RED | PASS | 0
P003 | Nova Transformation | Quality | Transformation | East | Sponsor A | Sanjay Kumar | 56 | 2026-07-03 | 2026-10-25 | 129.4 | 28.9 | 40.3 | 15 | 92.37% | 22 | 58 | Strategic | 22.34% | 6400% | 2 | 0 | 7 | RED | PASS | 0
P004 | Orion Transformation | Sales | Compliance | West | Sponsor A | Karan Rao | 121.4 | 2026-07-04 | 2026-10-15 | 141.7 | 19.8 | 44.7 | 30 | 73.8% | 43 | 56 | Growth | 14% | 1983% | 1 | 0 | 16 | RED | PASS | 0
P005 | Vertex Transformation | Product | Transformation | West | Sponsor C | Rohit Nair | 53.4 | 2026-07-05 | 2026-11-09 | 110.7 | 23.8 | 5.6 | 31 | 71.17% | 33 | 80 | Operational | 21.49% | 8533% | 2 | 0 | 3 | AMBER | PASS | 0
P006 | Pulse Transformation | Manufacturing | Transformation | South | Sponsor E | Arjun Mehta | 113.4 | 2026-07-06 | 2026-09-28 | 241.9 | 56.4 | 13 | 13 | 66.3% | 53 | 80 | Strategic | 23.3% | 6000% | 3 | 0 | 8 | RED | PASS | 0
P007 | Horizon Transformation | Technology | Innovation | West | Sponsor A | Arjun Mehta | 116.8 | 2026-07-07 | 2026-10-03 | 187.9 | 61.8 | 47.7 | 8 | 87.01% | 74 | 58 | Growth | 32.88% | 3567% | 6 | 3 | 17 | RED | PASS | 0
P008 | Fusion Transformation | Quality | Innovation | Central | Sponsor B | Sanjay Kumar | 167 | 2026-07-08 | 2026-11-25 | 311.3 | 84.3 | 42.5 | 27 | 100.2% | 15 | 82 | Growth | 27.08% | 8317% | 1 | 0 | 3 | AMBER | PASS | 0
P009 | Nexus Transformation | Quality | Transformation | East | Sponsor E | Ananya Iyer | 40.6 | 2026-07-09 | 2026-10-05 | 54.1 | 16.1 | 19 | 28 | 63.05% | 56 | 68 | Operational | 29.85% | 2217% | 2 | 0 | 16 | RED | PASS | 0
P010 | Catalyst Transformation | Product | Innovation | East | Sponsor A | Rohit Nair | 54 | 2026-07-10 | 2026-10-29 | 113.8 | 36 | 34 | 25 | 79.46% | 61 | 57 | Mandatory | 31.65% | 7767% | 1 | 0 | 4 | RED | PASS | 0
P011 | Helix Transformation | ESG | Run | South | Sponsor A | Karan Rao | 114.1 | 2026-07-11 | 2026-12-07 | 236.2 | 53.7 | 12.3 | 17 | 99.11% | 80 | 82 | Growth | 22.71% | 8800% | 2 | 0 | 2 | RED | PASS | 0
P012 | Velocity Transformation | Manufacturing | Innovation | East | Sponsor D | Arjun Mehta | 102.8 | 2026-07-12 | 2026-09-22 | 136.1 | 17.1 | 8 | 38 | 91.77% | 68 | 72 | Strategic | 12.58% | 3617% | 7 | 3 | 17 | RED | PASS | 0
P013 | Summit Transformation | Quality | Innovation | South | Sponsor C | Meera Joshi | 138.9 | 2026-07-13 | 2026-10-13 | 161.1 | 43.7 | 34.5 | 18 | 93.06% | 24 | 66 | Strategic | 27.1% | 6433% | 1 | 0 | 7 | AMBER | PASS | 0
P014 | Quantum Transformation | Product | Compliance | West | Sponsor B | Ananya Iyer | 111.5 | 2026-07-14 | 2026-10-02 | 149 | 28 | 14.8 | 11 | 95.66% | 38 | 91 | Growth | 18.81% | 3100% | 3 | 0 | 15 | RED | PASS | 0
P015 | Pioneer Transformation | Digital | Growth | North | Sponsor A | Sanjay Kumar | 91.4 | 2026-07-15 | 2026-09-13 | 178.7 | 22.8 | 47.3 | 34 | 64.59% | 81 | 58 | Growth | 12.78% | 8117% | 2 | 3 | 6 | RED | PASS | 0
P016 | Matrix Transformation | Supply Chain | Compliance | Central | Sponsor D | Sanjay Kumar | 172.5 | 2026-07-16 | 2026-12-15 | 240.2 | 47 | 32.1 | 37 | 102.7% | 48 | 76 | Growth | 19.58% | 8883% | 2 | 0 | 2 | AMBER | PASS | 0
P017 | Elevate Transformation | Technology | Innovation | North | Sponsor C | Arjun Mehta | 113.3 | 2026-07-17 | 2026-10-22 | 171.2 | 34.1 | 12.7 | 30 | 82.33% | 52 | 69 | Strategic | 19.91% | 5700% | 2 | 0 | 9 | RED | PASS | 0
P018 | Voyage Transformation | Sales | Transformation | West | Sponsor B | Priya Shah | 104.1 | 2026-07-18 | 2026-09-26 | 162.7 | 25.3 | 54.5 | 17 | 86.21% | 59 | 97 | Operational | 15.53% | 7933% | 1 | 0 | 7 | AMBER | PASS | 0
P019 | Vector Transformation | ESG | Customer | North | Sponsor D | Sanjay Kumar | 55.4 | 2026-07-19 | 2026-11-19 | 86.3 | 22.4 | 49 | 10 | 97.09% | 92 | 87 | Growth | 25.96% | 8483% | 1 | 3 | 6 | RED | PASS | 0
P020 | Synergy Transformation | Quality | Run | North | Sponsor E | Vivek Singh | 142.5 | 2026-07-20 | 2026-11-03 | 281.4 | 43.6 | 11.6 | 19 | 98.44% | 72 | 91 | Strategic | 15.48% | 7300% | 2 | 0 | 7 | AMBER | PASS | 0
P021 | Aurora Expansion | Manufacturing | Run | North | Sponsor A | Karan Rao | 66.2 | 2026-07-21 | 2026-11-23 | 83 | 16.9 | 63.5 | 19 | 94.92% | 31 | 82 | Growth | 20.4% | 4417% | 3 | 0 | 11 | RED | PASS | 0
P022 | Atlas Expansion | Quality | Run | West | Sponsor E | Karan Rao | 120.2 | 2026-07-22 | 2026-09-20 | 200.3 | 26.8 | 14.9 | 7 | 73.69% | 23 | 97 | Strategic | 13.36% | 2500% | 3 | 0 | 18 | RED | PASS | 0
P023 | Nova Expansion | ESG | Growth | Central | Sponsor B | Meera Joshi | 35.3 | 2026-07-23 | 2026-09-21 | 66.1 | 15.1 | 34.3 | 14 | 95.94% | 58 | 71 | Strategic | 22.89% | 8117% | 0 | 0 | 4 | AMBER | PASS | 0
P024 | Orion Expansion | Manufacturing | Compliance | South | Sponsor B | Karan Rao | 100.8 | 2026-07-24 | 2026-09-19 | 224 | 75.9 | 19.8 | 26 | 96.63% | 79 | 98 | Strategic | 33.88% | 4000% | 6 | 3 | 19 | RED | PASS | 0
P025 | Vertex Expansion | Infrastructure | Compliance | East | Sponsor A | Sanjay Kumar | 114.4 | 2026-07-25 | 2026-10-19 | 245.2 | 59.9 | 37.5 | 12 | 72.39% | 19 | 57 | Mandatory | 24.43% | 6667% | 1 | 0 | 7 | RED | PASS | 0
P026 | Pulse Expansion | Manufacturing | Transformation | East | Sponsor A | Rohit Nair | 135.2 | 2026-07-26 | 2026-12-10 | 164.5 | 26.6 | 34.1 | 18 | 98.08% | 33 | 90 | Growth | 16.14% | 8650% | 2 | 0 | 4 | AMBER | PASS | 0
P027 | Horizon Expansion | Manufacturing | Growth | West | Sponsor E | Vivek Singh | 152.2 | 2026-07-27 | 2026-12-22 | 244.7 | 55.3 | 21.3 | 8 | 72.45% | 42 | 70 | Strategic | 22.58% | 4300% | 2 | 0 | 11 | RED | PASS | 0
P028 | Fusion Expansion | Corporate | Transformation | South | Sponsor D | Karan Rao | 145.5 | 2026-07-28 | 2026-09-28 | 328.8 | 67.3 | 34.6 | 22 | 73.31% | 17 | 60 | Operational | 20.47% | 6783% | 4 | 0 | 6 | RED | PASS | 0
P029 | Nexus Expansion | Manufacturing | Transformation | West | Sponsor C | Rohit Nair | 99.4 | 2026-07-29 | 2026-10-31 | 140.7 | 28.6 | 48.8 | 17 | 62.3% | 28 | 55 | Growth | 20.31% | 4567% | 2 | 0 | 11 | RED | PASS | 0
P030 | Catalyst Expansion | Manufacturing | Compliance | Central | Sponsor E | Meera Joshi | 77.1 | 2026-07-30 | 2026-11-03 | 89.4 | 20.8 | 14.9 | 9 | 66.28% | 49 | 82 | Growth | 23.26% | 7967% | 1 | 0 | 4 | AMBER | PASS | 0
P031 | Helix Expansion | Digital | Transformation | South | Sponsor D | Sanjay Kumar | 96.2 | 2026-07-31 | 2026-12-05 | 136.9 | 37.6 | 26.3 | 29 | 99.75% | 59 | 62 | Mandatory | 27.46% | 7033% | 1 | 0 | 6 | RED | PASS | 0
P032 | Velocity Expansion | Digital | Compliance | West | Sponsor A | Neha Kapoor | 159.9 | 2026-08-01 | 2026-11-28 | 207.6 | 59 | 29.6 | 8 | 73.11% | 17 | 85 | Strategic | 28.42% | 2200% | 0 | 0 | 16 | RED | PASS | 0
P033 | Summit Expansion | Product | Growth | North | Sponsor B | Aditi Menon | 136.9 | 2026-08-02 | 2026-10-26 | 220.5 | 55.2 | 33 | 22 | 77.78% | 15 | 85 | Mandatory | 25.02% | 4050% | 1 | 0 | 12 | RED | PASS | 0
P034 | Quantum Expansion | Technology | Transformation | South | Sponsor B | Ananya Iyer | 123.8 | 2026-08-03 | 2026-11-19 | 144.9 | 30.4 | 43.9 | 19 | 68.22% | 58 | 55 | Growth | 20.99% | 8833% | 1 | 0 | 2 | RED | PASS | 0
P035 | Pioneer Expansion | Sales | Transformation | North | Sponsor C | Meera Joshi | 110.1 | 2026-08-04 | 2026-12-15 | 211.5 | 58.7 | 58.5 | 24 | 77.37% | 86 | 58 | Strategic | 27.74% | 4717% | 3 | 3 | 14 | RED | PASS | 0
P036 | Matrix Expansion | Technology | Innovation | Central | Sponsor B | Arjun Mehta | 56.6 | 2026-08-05 | 2026-11-07 | 96.7 | 16.5 | 63.3 | 36 | 68.93% | 31 | 67 | Operational | 17.04% | 4683% | 1 | 0 | 11 | RED | PASS | 0
P037 | Elevate Expansion | Product | Compliance | West | Sponsor B | Vivek Singh | 88.7 | 2026-08-06 | 2026-12-06 | 166.5 | 52.1 | 47.9 | 33 | 91.51% | 66 | 88 | Growth | 31.32% | 7483% | 2 | 0 | 6 | AMBER | PASS | 0
P038 | Voyage Expansion | Technology | Transformation | West | Sponsor A | Sanjay Kumar | 104.7 | 2026-08-07 | 2026-12-16 | 242.5 | 57.6 | 42.9 | 20 | 67.05% | 51 | 81 | Strategic | 23.74% | 7583% | 4 | 0 | 5 | AMBER | PASS | 0
P039 | Vector Expansion | Quality | Transformation | East | Sponsor B | Aditi Menon | 133.4 | 2026-08-08 | 2026-10-16 | 269.8 | 74.1 | 53.6 | 16 | 98.09% | 55 | 79 | Growth | 27.46% | 7517% | 1 | 0 | 5 | AMBER | PASS | 0
P040 | Synergy Expansion | Sales | Compliance | East | Sponsor E | Meera Joshi | 67.5 | 2026-08-09 | 2026-11-18 | 100.8 | 30.1 | 6.4 | 10 | 91.76% | 75 | 61 | Operational | 29.84% | 4717% | 2 | 1 | 12 | RED | PASS | 0
P041 | Aurora Integration | Corporate | Run | Central | Sponsor A | Meera Joshi | 154.7 | 2026-08-10 | 2026-10-08 | 306.6 | 39.6 | 62.2 | 27 | 94.87% | 17 | 64 | Mandatory | 12.9% | 3483% | 3 | 0 | 13 | RED | PASS | 0
P042 | Atlas Integration | Product | Transformation | North | Sponsor A | Karan Rao | 72.8 | 2026-08-11 | 2026-10-23 | 101.8 | 17.8 | 27.6 | 15 | 93.05% | 58 | 74 | Mandatory | 17.47% | 3600% | 1 | 0 | 13 | RED | PASS | 0
P043 | Nova Integration | Corporate | Innovation | West | Sponsor E | Aditi Menon | 88.9 | 2026-08-12 | 2027-01-08 | 128.5 | 32.5 | 62.3 | 33 | 87.87% | 71 | 72 | Growth | 25.26% | 7283% | 2 | 0 | 5 | AMBER | PASS | 0
P044 | Orion Integration | Technology | Compliance | North | Sponsor E | Sanjay Kumar | 111.7 | 2026-08-13 | 2026-11-17 | 266.6 | 80.4 | 8.6 | 36 | 62.78% | 72 | 95 | Growth | 30.16% | 4700% | 3 | 1 | 15 | RED | PASS | 0
P045 | Vertex Integration | Technology | Compliance | North | Sponsor B | Arjun Mehta | 83.4 | 2026-08-14 | 2026-12-24 | 198.9 | 34.2 | 17.1 | 31 | 96.39% | 83 | 73 | Mandatory | 17.18% | 4633% | 2 | 3 | 14 | RED | PASS | 0
P046 | Pulse Integration | Manufacturing | Transformation | North | Sponsor E | Sanjay Kumar | 73.2 | 2026-08-15 | 2027-01-17 | 101.9 | 26.6 | 46.6 | 24 | 104.8% | 37 | 82 | Growth | 26.06% | 8283% | 2 | 0 | 3 | AMBER | PASS | 0
P047 | Horizon Integration | ESG | Innovation | South | Sponsor A | Sanjay Kumar | 81.9 | 2026-08-16 | 2026-10-20 | 128.4 | 16.1 | 18.2 | 30 | 70.32% | 59 | 75 | Strategic | 12.55% | 7833% | 1 | 0 | 4 | AMBER | PASS | 0
P048 | Fusion Integration | Manufacturing | Compliance | North | Sponsor B | Arjun Mehta | 133.1 | 2026-08-17 | 2027-01-02 | 275 | 43.8 | 51.1 | 16 | 91.99% | 64 | 74 | Operational | 15.94% | 6250% | 1 | 0 | 8 | RED | PASS | 0
P049 | Nexus Integration | Manufacturing | Growth | West | Sponsor D | Priya Shah | 53.1 | 2026-08-18 | 2026-10-20 | 76.6 | 19.3 | 62.4 | 6 | 65.34% | 43 | 80 | Operational | 25.23% | 4200% | 4 | 0 | 12 | RED | PASS | 0
P050 | Catalyst Integration | Technology | Compliance | Central | Sponsor E | Neha Kapoor | 114.9 | 2026-08-19 | 2027-01-05 | 263.8 | 64.1 | 48.1 | 7 | 75.43% | 54 | 55 | Growth | 24.31% | 5233% | 2 | 0 | 10 | RED | PASS | 0
P051 | Helix Integration | ESG | Innovation | Central | Sponsor E | Aditi Menon | 66.7 | 2026-08-20 | 2026-10-23 | 102.6 | 18.3 | 35.5 | 13 | 100.2% | 30 | 73 | Mandatory | 17.79% | 2450% | 1 | 0 | 15 | RED | PASS | 0
P052 | Velocity Integration | Infrastructure | Compliance | West | Sponsor D | Rohit Nair | 46.4 | 2026-08-21 | 2026-12-15 | 100.9 | 22.1 | 53 | 34 | 67.87% | 18 | 63 | Operational | 21.86% | 9050% | 5 | 0 | 2 | RED | PASS | 0
P053 | Summit Integration | Manufacturing | Run | South | Sponsor E | Aditi Menon | 67.9 | 2026-08-22 | 2026-12-10 | 121.1 | 38.8 | 22.9 | 31 | 103.9% | 91 | 64 | Mandatory | 32.01% | 6383% | 3 | 3 | 10 | RED | PASS | 0
P054 | Quantum Integration | Quality | Customer | East | Sponsor A | Rohit Nair | 81.5 | 2026-08-23 | 2026-12-27 | 116 | 36.1 | 29.5 | 23 | 62.98% | 81 | 66 | Growth | 31.09% | 8500% | 0 | 3 | 5 | RED | PASS | 0
P055 | Pioneer Integration | ESG | Growth | South | Sponsor E | Rohit Nair | 147.4 | 2026-08-24 | 2027-01-16 | 239.3 | 43.7 | 46.8 | 20 | 82.9% | 39 | 95 | Operational | 18.25% | 5067% | 1 | 0 | 12 | RED | PASS | 0
P056 | Matrix Integration | Sales | Run | North | Sponsor C | Sanjay Kumar | 38.3 | 2026-08-25 | 2026-11-21 | 72.2 | 11.5 | 30.7 | 31 | 69.73% | 19 | 98 | Operational | 15.87% | 5600% | 1 | 0 | 12 | RED | PASS | 0
P057 | Elevate Integration | Product | Customer | North | Sponsor E | Neha Kapoor | 88.9 | 2026-08-26 | 2026-11-04 | 132.2 | 23.6 | 14.7 | 24 | 88.27% | 67 | 84 | Mandatory | 17.87% | 5817% | 2 | 0 | 8 | RED | PASS | 0
P058 | Voyage Integration | ESG | Innovation | Central | Sponsor E | Karan Rao | 36.4 | 2026-08-27 | 2026-11-18 | 62.6 | 16 | 11.9 | 19 | 85.88% | 43 | 94 | Growth | 25.53% | 5983% | 3 | 0 | 10 | RED | PASS | 0
P059 | Vector Integration | Product | Innovation | West | Sponsor C | Rohit Nair | 155.6 | 2026-08-28 | 2026-12-02 | 227.8 | 44.9 | 64.5 | 28 | 67.9% | 88 | 89 | Mandatory | 19.72% | 4283% | 6 | 3 | 17 | RED | PASS | 0
P060 | Synergy Integration | ESG | Innovation | West | Sponsor D | Sanjay Kumar | 157 | 2026-08-29 | 2027-01-17 | 285.3 | 96.7 | 44.2 | 29 | 71.85% | 40 | 64 | Operational | 33.91% | 2100% | 1 | 0 | 16 | RED | PASS | 0
P061 | Aurora Automation | Sales | Growth | North | Sponsor E | Neha Kapoor | 131.7 | 2026-08-30 | 2026-10-26 | 249.8 | 64.2 | 13.4 | 22 | 97.15% | 52 | 67 | Strategic | 25.7% | 2800% | 1 | 0 | 14 | RED | PASS | 0
P062 | Atlas Automation | Sales | Customer | Central | Sponsor B | Vivek Singh | 174 | 2026-08-31 | 2026-12-27 | 415.6 | 122.9 | 50.2 | 10 | 84.96% | 31 | 64 | Operational | 29.57% | 4033% | 2 | 0 | 12 | RED | PASS | 0
P063 | Nova Automation | Technology | Innovation | West | Sponsor E | Arjun Mehta | 174.6 | 2026-09-01 | 2027-02-02 | 217.8 | 69.6 | 23.4 | 26 | 73.62% | 51 | 57 | Growth | 31.94% | 4967% | 0 | 0 | 10 | RED | PASS | 0
P064 | Orion Automation | Quality | Compliance | West | Sponsor D | Karan Rao | 50.6 | 2026-09-02 | 2027-01-21 | 101.3 | 31.3 | 38.1 | 36 | 85.55% | 42 | 59 | Strategic | 30.92% | 4383% | 3 | 0 | 11 | RED | PASS | 0
P065 | Vertex Automation | Sales | Innovation | North | Sponsor B | Karan Rao | 169.4 | 2026-09-03 | 2026-12-21 | 208.5 | 55.6 | 13.6 | 27 | 94.31% | 32 | 64 | Mandatory | 26.68% | 3683% | 1 | 0 | 13 | RED | PASS | 0
P066 | Pulse Automation | Product | Innovation | Central | Sponsor B | Vivek Singh | 135.4 | 2026-09-04 | 2027-01-15 | 239.6 | 69.8 | 46.2 | 30 | 64.38% | 52 | 64 | Strategic | 29.14% | 5067% | 3 | 0 | 10 | RED | PASS | 0
P067 | Horizon Automation | Sales | Growth | East | Sponsor D | Sanjay Kumar | 178.7 | 2026-09-05 | 2027-02-02 | 336.9 | 77.9 | 43.5 | 23 | 72.94% | 42 | 65 | Mandatory | 23.14% | 9117% | 3 | 0 | 2 | AMBER | PASS | 0
P068 | Fusion Automation | ESG | Run | East | Sponsor B | Sanjay Kumar | 131.9 | 2026-09-06 | 2026-11-08 | 311.9 | 78.5 | 20.9 | 16 | 103.5% | 35 | 78 | Growth | 25.17% | 8700% | 5 | 0 | 3 | AMBER | PASS | 0
P069 | Nexus Automation | Quality | Transformation | West | Sponsor D | Aditi Menon | 179.8 | 2026-09-07 | 2027-01-01 | 233.5 | 67.8 | 7.6 | 13 | 79.31% | 72 | 60 | Growth | 29.02% | 8017% | 0 | 0 | 4 | RED | PASS | 0
P070 | Catalyst Automation | Digital | Transformation | Central | Sponsor A | Meera Joshi | 41.3 | 2026-09-08 | 2026-11-19 | 95.1 | 13.7 | 47.1 | 21 | 78.79% | 35 | 61 | Operational | 14.38% | 3517% | 0 | 0 | 13 | RED | PASS | 0
P071 | Helix Automation | Technology | Innovation | West | Sponsor D | Priya Shah | 61.5 | 2026-09-09 | 2026-12-02 | 146.4 | 30.3 | 43.7 | 6 | 74.94% | 78 | 95 | Growth | 20.71% | 8800% | 2 | 0 | 5 | RED | PASS | 0
P072 | Velocity Automation | Supply Chain | Innovation | Central | Sponsor B | Ananya Iyer | 45.6 | 2026-09-10 | 2026-11-06 | 70.1 | 18.2 | 8.6 | 10 | 62.92% | 71 | 90 | Mandatory | 25.98% | 2983% | 7 | 3 | 19 | RED | PASS | 0
P073 | Summit Automation | Infrastructure | Growth | East | Sponsor A | Arjun Mehta | 155.2 | 2026-09-11 | 2027-01-08 | 199.3 | 54.6 | 56.9 | 26 | 91.55% | 41 | 98 | Growth | 27.41% | 8800% | 3 | 0 | 6 | AMBER | PASS | 0
P074 | Quantum Automation | Technology | Customer | West | Sponsor E | Aditi Menon | 62 | 2026-09-12 | 2026-12-08 | 84.6 | 16.5 | 32.1 | 27 | 73.74% | 60 | 70 | Strategic | 19.45% | 6350% | 0 | 0 | 7 | AMBER | PASS | 0
P075 | Pioneer Automation | Corporate | Customer | North | Sponsor B | Priya Shah | 38.7 | 2026-09-13 | 2026-11-29 | 60 | 16.3 | 43.7 | 27 | 79.51% | 83 | 82 | Operational | 27.18% | 3950% | 7 | 3 | 16 | RED | PASS | 0
P076 | Matrix Automation | Supply Chain | Customer | West | Sponsor E | Priya Shah | 119.1 | 2026-09-14 | 2026-12-29 | 173.1 | 40.1 | 37 | 9 | 64.58% | 49 | 77 | Operational | 23.14% | 8800% | 1 | 0 | 2 | AMBER | PASS | 0
P077 | Elevate Automation | Supply Chain | Run | Central | Sponsor D | Vivek Singh | 107.5 | 2026-09-15 | 2026-12-17 | 208.7 | 35.9 | 59.3 | 11 | 75.31% | 65 | 91 | Operational | 17.18% | 7583% | 0 | 0 | 6 | AMBER | PASS | 0
P078 | Voyage Automation | Infrastructure | Customer | West | Sponsor C | Aditi Menon | 96.5 | 2026-09-16 | 2027-02-02 | 179.2 | 52.2 | 46.9 | 26 | 82.51% | 15 | 87 | Mandatory | 29.12% | 7583% | 2 | 0 | 5 | AMBER | PASS | 0
P079 | Vector Automation | Infrastructure | Customer | South | Sponsor E | Aditi Menon | 86.2 | 2026-09-17 | 2026-11-15 | 200.7 | 64.4 | 8.8 | 6 | 95.56% | 86 | 89 | Growth | 32.07% | 2317% | 6 | 3 | 21 | RED | PASS | 0
P080 | Synergy Automation | Product | Growth | East | Sponsor A | Ananya Iyer | 46.9 | 2026-09-18 | 2026-12-13 | 64.7 | 17.5 | 8.9 | 11 | 74.99% | 15 | 60 | Strategic | 27.01% | 8117% | 0 | 0 | 4 | RED | PASS | 0
P081 | Aurora Modernisation | ESG | Growth | East | Sponsor E | Neha Kapoor | 99.3 | 2026-09-19 | 2027-01-15 | 236.9 | 43.9 | 15.3 | 10 | 78.37% | 54 | 85 | Operational | 18.55% | 4267% | 1 | 0 | 11 | RED | PASS | 0
P082 | Atlas Modernisation | Corporate | Innovation | North | Sponsor B | Ananya Iyer | 140.8 | 2026-09-20 | 2026-12-10 | 308.8 | 97.1 | 13.7 | 38 | 96.08% | 50 | 80 | Growth | 31.44% | 3700% | 1 | 0 | 13 | RED | PASS | 0
P083 | Nova Modernisation | Quality | Transformation | South | Sponsor D | Arjun Mehta | 91.6 | 2026-09-21 | 2027-02-21 | 194.1 | 39.4 | 6.3 | 24 | 90.31% | 69 | 91 | Strategic | 20.28% | 4600% | 4 | 1 | 14 | RED | PASS | 0
P084 | Orion Modernisation | Sales | Innovation | Central | Sponsor A | Arjun Mehta | 152.7 | 2026-09-22 | 2026-12-02 | 271.7 | 56.8 | 18.6 | 15 | 68.7% | 76 | 69 | Operational | 20.91% | 7533% | 2 | 0 | 5 | RED | PASS | 0
P085 | Vertex Modernisation | Sales | Innovation | South | Sponsor E | Neha Kapoor | 147.8 | 2026-09-23 | 2027-02-23 | 281.9 | 77.9 | 40.2 | 35 | 93.52% | 87 | 95 | Growth | 27.62% | 7233% | 1 | 3 | 10 | RED | PASS | 0
P086 | Pulse Modernisation | Digital | Transformation | West | Sponsor E | Neha Kapoor | 57.7 | 2026-09-24 | 2026-12-07 | 105.2 | 24.2 | 21.7 | 17 | 96.46% | 78 | 74 | Strategic | 23.05% | 4717% | 5 | 1 | 12 | RED | PASS | 0
P087 | Horizon Modernisation | Product | Customer | East | Sponsor C | Arjun Mehta | 139.8 | 2026-09-25 | 2026-11-28 | 223.4 | 66.3 | 52.8 | 23 | 95.09% | 77 | 96 | Operational | 29.69% | 7100% | 0 | 0 | 9 | RED | PASS | 0
P088 | Fusion Modernisation | Product | Growth | West | Sponsor A | Sanjay Kumar | 85.8 | 2026-09-26 | 2027-02-26 | 195.6 | 44.7 | 26.5 | 33 | 64.27% | 92 | 76 | Strategic | 22.85% | 7133% | 0 | 3 | 8 | RED | PASS | 0
P089 | Nexus Modernisation | Digital | Customer | North | Sponsor B | Meera Joshi | 179.6 | 2026-09-27 | 2026-11-28 | 381.7 | 49.2 | 24.6 | 11 | 104.4% | 88 | 84 | Operational | 12.89% | 8167% | 2 | 3 | 6 | RED | PASS | 0
P090 | Catalyst Modernisation | Technology | Run | West | Sponsor A | Vivek Singh | 158.7 | 2026-09-28 | 2026-12-17 | 275.3 | 81.6 | 22.6 | 18 | 91.95% | 31 | 80 | Growth | 29.64% | 8300% | 0 | 0 | 3 | AMBER | PASS | 0
P091 | Helix Modernisation | Infrastructure | Compliance | West | Sponsor C | Sanjay Kumar | 68.6 | 2026-09-29 | 2027-01-14 | 132.9 | 30.1 | 46.7 | 33 | 95.47% | 76 | 72 | Growth | 22.65% | 2817% | 6 | 3 | 19 | RED | PASS | 0
P092 | Velocity Modernisation | Infrastructure | Innovation | North | Sponsor C | Sanjay Kumar | 97.7 | 2026-09-30 | 2026-12-17 | 189.6 | 33.4 | 6 | 14 | 106.3% | 28 | 61 | Growth | 17.6% | 7867% | 1 | 0 | 4 | RED | PASS | 0
P093 | Summit Modernisation | Infrastructure | Innovation | West | Sponsor C | Arjun Mehta | 178.7 | 2026-10-01 | 2026-12-01 | 298 | 37.7 | 30.9 | 10 | 85.09% | 46 | 58 | Operational | 12.66% | 3083% | 1 | 0 | 14 | RED | PASS | 0
P094 | Quantum Modernisation | Product | Transformation | South | Sponsor A | Arjun Mehta | 66.2 | 2026-10-02 | 2027-03-05 | 105.1 | 15.5 | 63.4 | 31 | 80.45% | 12 | 97 | Operational | 14.78% | 8533% | 2 | 0 | 6 | AMBER | PASS | 0
P095 | Pioneer Modernisation | Product | Innovation | North | Sponsor B | Vivek Singh | 60.8 | 2026-10-03 | 2027-02-22 | 129.2 | 21.3 | 27.7 | 33 | 68.82% | 42 | 80 | Operational | 16.49% | 8850% | 3 | 0 | 2 | GREEN | PASS | 0
P096 | Matrix Modernisation | Manufacturing | Transformation | North | Sponsor B | Sanjay Kumar | 60.7 | 2026-10-04 | 2026-12-20 | 113.4 | 26.9 | 10.3 | 33 | 69.46% | 79 | 76 | Growth | 23.69% | 2800% | 6 | 3 | 19 | RED | PASS | 0
P097 | Elevate Modernisation | Sales | Transformation | South | Sponsor C | Aditi Menon | 120 | 2026-10-05 | 2027-01-07 | 168.8 | 39.6 | 25.9 | 27 | 105.7% | 57 | 55 | Operational | 23.47% | 4500% | 1 | 0 | 11 | RED | PASS | 0
P098 | Voyage Modernisation | Supply Chain | Growth | North | Sponsor B | Sanjay Kumar | 76.9 | 2026-10-06 | 2026-12-10 | 175.8 | 23.4 | 6.2 | 38 | 79.18% | 76 | 69 | Strategic | 13.31% | 9483% | 0 | 0 | 1 | RED | PASS | 0
P099 | Vector Modernisation | Supply Chain | Growth | North | Sponsor D | Rohit Nair | 105.6 | 2026-10-07 | 2026-12-19 | 167.9 | 49.2 | 11 | 35 | 103.3% | 12 | 75 | Growth | 29.33% | 2883% | 2 | 0 | 14 | RED | PASS | 0
P100 | Synergy Modernisation | Product | Customer | South | Sponsor E | Sanjay Kumar | 51.8 | 2026-10-08 | 2026-12-23 | 101.5 | 30 | 60.6 | 17 | 74.87% | 16 | 62 | Mandatory | 29.55% | 6783% | 3 | 0 | 6 | RED | PASS | 0

## 11_Task_Data
OPERATIONAL ENGINE ¦ TASK REGISTER | [17 empty] | DATA QUALITY HELPER
600 task records • edit yellow cells only • changes roll upward into project health. | [17 empty] | Duplicate flag: 1 when an ID repeats.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
Project ID | Task ID | Task | Owner | Support | Priority | Start | Due | Progress % | Status | Blocker | Escalation | Hours Planned | Hours Used | Last Update | Task Key | Open Task Key | Owner Task Key | Duplicate ID Flag
P001 | P001-T1 | Requirements & scope freeze | Rahul | Vivek | High | 2026-07-01 | 2026-07-23 | 63 | In Progress |  | NO | 21 | 78 | 2026-09-09 | P00101 | P001O1 | RahulO1 | 0
P001 | P001-T2 | Design / solution | Karan | Ritu | High | 2026-07-15 | 2026-08-04 | 68 | In Progress |  | NO | 80 | 83 | 2026-09-09 | P00102 | P001O2 | KaranO1 | 0
P001 | P001-T3 | BOM / commercial approval | Meera | Sanjay | Critical | 2026-07-29 | 2026-08-14 | 71 | In Progress |  | NO | 42 | 22 | 2026-09-09 | P00103 | P001O3 | MeeraO1 | 0
P001 | P001-T4 | Build / execution | Vivek | Anil | Critical | 2026-08-12 | 2026-09-05 | 69 | In Progress |  | NO | 25 | 105 | 2026-09-09 | P00104 | P001O4 | VivekO1 | 0
P001 | P001-T5 | Testing / validation | Ritu | Kavya | Critical | 2026-08-26 | 2026-09-06 | 48 | In Progress | Awaiting clarification | NO | 42 | 31 | 2026-09-09 | P00105 | P001O5 | RituO1 | 0
P001 | P001-T6 | Customer acceptance | Sanjay | Rohan | Medium | 2026-09-09 | 2026-10-01 | 72 | In Progress |  | NO | 83 | 22 | 2026-09-09 | P00106 | P001O6 | SanjayO1 | 0
P002 | P002-T1 | Requirements & scope freeze | Karan | Ritu | High | 2026-07-02 | 2026-07-22 | 45 | In Progress | Awaiting clarification | NO | 46 | 31 | 2026-09-09 | P00201 | P002O1 | KaranO2 | 0
P002 | P002-T2 | Design / solution | Meera | Sanjay | High | 2026-07-16 | 2026-08-09 | 61 | In Progress |  | NO | 62 | 16 | 2026-09-09 | P00202 | P002O2 | MeeraO2 | 0
P002 | P002-T3 | BOM / commercial approval | Vivek | Anil | Critical | 2026-07-30 | 2026-08-10 | 53 | In Progress |  | NO | 76 | 77 | 2026-09-09 | P00203 | P002O3 | VivekO2 | 0
P002 | P002-T4 | Build / execution | Ritu | Kavya | High | 2026-08-13 | 2026-08-28 | 41 | In Progress |  | NO | 55 | 86 | 2026-09-09 | P00204 | P002O4 | RituO2 | 0
P002 | P002-T5 | Testing / validation | Sanjay | Rohan | High | 2026-08-27 | 2026-09-16 | 35 | In Progress |  | NO | 86 | 76 | 2026-09-09 | P00205 | P002O5 | SanjayO2 | 0
P002 | P002-T6 | Customer acceptance | Anil | Deepa | Low | 2026-09-10 | 2026-09-25 | 37 | In Progress |  | NO | 81 | 102 | 2026-09-09 | P00206 | P002O6 | AnilO1 | 0
P003 | P003-T1 | Requirements & scope freeze | Meera | Sanjay | High | 2026-07-03 | 2026-07-24 | 61 | In Progress | Awaiting clarification | NO | 58 | 63 | 2026-09-09 | P00301 | P003O1 | MeeraO3 | 0
P003 | P003-T2 | Design / solution | Vivek | Anil | High | 2026-07-17 | 2026-07-27 | 66 | In Progress |  | NO | 78 | 43 | 2026-09-09 | P00302 | P003O2 | VivekO3 | 0
P003 | P003-T3 | BOM / commercial approval | Ritu | Kavya | Medium | 2026-07-31 | 2026-08-14 | 76 | In Progress | Awaiting clarification | NO | 24 | 23 | 2026-09-09 | P00303 | P003O3 | RituO3 | 0
P003 | P003-T4 | Build / execution | Sanjay | Rohan | High | 2026-08-14 | 2026-09-07 | 62 | In Progress |  | NO | 36 | 42 | 2026-09-09 | P00304 | P003O4 | SanjayO3 | 0
P003 | P003-T5 | Testing / validation | Anil | Deepa | Critical | 2026-08-28 | 2026-09-06 | 51 | In Progress |  | NO | 77 | 92 | 2026-09-09 | P00305 | P003O5 | AnilO2 | 0
P003 | P003-T6 | Customer acceptance | Kavya | Amit | Low | 2026-09-11 | 2026-10-01 | 68 | In Progress |  | NO | 28 | 16 | 2026-09-09 | P00306 | P003O6 | KavyaO1 | 0
P004 | P004-T1 | Requirements & scope freeze | Vivek | Anil | Critical | 2026-07-04 | 2026-07-19 | 29 | In Progress |  | NO | 28 | 71 | 2026-09-09 | P00401 | P004O1 | VivekO4 | 0
P004 | P004-T2 | Design / solution | Ritu | Kavya | Medium | 2026-07-18 | 2026-07-29 | 20 | In Progress |  | NO | 80 | 58 | 2026-09-09 | P00402 | P004O2 | RituO4 | 0
P004 | P004-T3 | BOM / commercial approval | Sanjay | Rohan | Low | 2026-08-01 | 2026-08-22 | 4 | In Progress |  | NO | 61 | 41 | 2026-09-09 | P00403 | P004O3 | SanjayO4 | 0
P004 | P004-T4 | Build / execution | Anil | Deepa | Medium | 2026-08-15 | 2026-09-05 | 12 | In Progress |  | NO | 56 | 28 | 2026-09-09 | P00404 | P004O4 | AnilO3 | 0
P004 | P004-T5 | Testing / validation | Kavya | Amit | Critical | 2026-08-29 | 2026-09-16 | 33 | In Progress |  | NO | 57 | 43 | 2026-09-09 | P00405 | P004O5 | KavyaO2 | 0
P004 | P004-T6 | Customer acceptance | Rohan | Priya | Medium | 2026-09-12 | 2026-09-24 | 21 | In Progress | Awaiting clarification | NO | 33 | 40 | 2026-09-09 | P00406 | P004O6 | RohanO1 | 0
P005 | P005-T1 | Requirements & scope freeze | Ritu | Kavya | Medium | 2026-07-05 | 2026-07-29 | 72 | In Progress |  | NO | 100 | 32 | 2026-09-09 | P00501 | P005O1 | RituO5 | 0
P005 | P005-T2 | Design / solution | Sanjay | Rohan | Critical | 2026-07-19 | 2026-08-01 | 78 | In Progress | Awaiting clarification | NO | 63 | 19 | 2026-09-09 | P00502 | P005O2 | SanjayO5 | 0
P005 | P005-T3 | BOM / commercial approval | Anil | Deepa | High | 2026-08-02 | 2026-08-13 | 91 | In Progress |  | NO | 66 | 44 | 2026-09-09 | P00503 | P005O3 | AnilO4 | 0
P005 | P005-T4 | Build / execution | Kavya | Amit | High | 2026-08-16 | 2026-09-01 | 80 | In Progress |  | NO | 86 | 26 | 2026-09-09 | P00504 | P005O4 | KavyaO3 | 0
P005 | P005-T5 | Testing / validation | Rohan | Priya | Critical | 2026-08-30 | 2026-09-23 | 95 | In Progress | Awaiting clarification | NO | 78 | 54 | 2026-09-09 | P00505 | P005O5 | RohanO2 | 0
P005 | P005-T6 | Customer acceptance | Deepa | Rahul | Low | 2026-09-13 | 2026-09-26 | 96 | In Progress |  | NO | 80 | 73 | 2026-09-09 | P00506 | P005O6 | DeepaO1 | 0
P006 | P006-T1 | Requirements & scope freeze | Sanjay | Rohan | Medium | 2026-07-06 | 2026-07-30 | 49 | In Progress | Awaiting clarification | NO | 42 | 15 | 2026-09-09 | P00601 | P006O1 | SanjayO6 | 0
P006 | P006-T2 | Design / solution | Anil | Deepa | Low | 2026-07-20 | 2026-08-01 | 42 | In Progress | Awaiting clarification | NO | 63 | 64 | 2026-09-09 | P00602 | P006O2 | AnilO5 | 0
P006 | P006-T3 | BOM / commercial approval | Kavya | Amit | Critical | 2026-08-03 | 2026-08-26 | 65 | In Progress |  | NO | 22 | 101 | 2026-09-09 | P00603 | P006O3 | KavyaO4 | 0
P006 | P006-T4 | Build / execution | Rohan | Priya | Critical | 2026-08-17 | 2026-08-31 | 54 | In Progress |  | NO | 79 | 68 | 2026-09-09 | P00604 | P006O4 | RohanO3 | 0
P006 | P006-T5 | Testing / validation | Deepa | Rahul | Critical | 2026-08-31 | 2026-09-20 | 71 | In Progress | Awaiting clarification | NO | 32 | 39 | 2026-09-09 | P00605 | P006O5 | DeepaO2 | 0
P006 | P006-T6 | Customer acceptance | Amit | Karan | Medium | 2026-09-14 | 2026-10-05 | 79 | In Progress |  | NO | 95 | 77 | 2026-09-09 | P00606 | P006O6 | AmitO1 | 0
P007 | P007-T1 | Requirements & scope freeze | Anil | Deepa | Medium | 2026-07-07 | 2026-07-26 | 21 | In Progress |  | NO | 62 | 93 | 2026-09-09 | P00701 | P007O1 | AnilO6 | 0
P007 | P007-T2 | Design / solution | Kavya | Amit | High | 2026-07-21 | 2026-08-11 | 40 | In Progress |  | NO | 91 | 69 | 2026-09-09 | P00702 | P007O2 | KavyaO5 | 0
P007 | P007-T3 | BOM / commercial approval | Rohan | Priya | Medium | 2026-08-04 | 2026-08-18 | 34 | In Progress |  | NO | 52 | 26 | 2026-09-09 | P00703 | P007O3 | RohanO4 | 0
P007 | P007-T4 | Build / execution | Deepa | Rahul | Medium | 2026-08-18 | 2026-09-04 | 46 | Blocked | Supplier / cross-functional dependency | YES | 98 | 105 | 2026-09-09 | P00704 | P007O4 | DeepaO3 | 0
P007 | P007-T5 | Testing / validation | Amit | Karan | Low | 2026-09-01 | 2026-09-24 | 47 | Blocked | Supplier / cross-functional dependency | YES | 47 | 62 | 2026-09-09 | P00705 | P007O5 | AmitO2 | 0
P007 | P007-T6 | Customer acceptance | Priya | Meera | Low | 2026-09-15 | 2026-09-27 | 26 | Blocked | Supplier / cross-functional dependency | YES | 26 | 73 | 2026-09-09 | P00706 | P007O6 | PriyaO1 | 0
P008 | P008-T1 | Requirements & scope freeze | Kavya | Amit | High | 2026-07-08 | 2026-07-22 | 98 | In Progress |  | NO | 88 | 74 | 2026-09-09 | P00801 | P008O1 | KavyaO6 | 0
P008 | P008-T2 | Design / solution | Rohan | Priya | Medium | 2026-07-22 | 2026-08-13 | 72 | In Progress |  | NO | 92 | 48 | 2026-09-09 | P00802 | P008O2 | RohanO5 | 0
P008 | P008-T3 | BOM / commercial approval | Deepa | Rahul | Critical | 2026-08-05 | 2026-08-25 | 78 | In Progress | Awaiting clarification | NO | 44 | 61 | 2026-09-09 | P00803 | P008O3 | DeepaO4 | 0
P008 | P008-T4 | Build / execution | Amit | Karan | Medium | 2026-08-19 | 2026-09-09 | 68 | In Progress |  | NO | 58 | 69 | 2026-09-09 | P00804 | P008O4 | AmitO3 | 0
P008 | P008-T5 | Testing / validation | Priya | Meera | High | 2026-09-02 | 2026-09-11 | 83 | In Progress |  | NO | 81 | 42 | 2026-09-09 | P00805 | P008O5 | PriyaO2 | 0
P008 | P008-T6 | Customer acceptance | Rahul | Vivek | Low | 2026-09-16 | 2026-10-03 | 100 | Completed |  | NO | 32 | 87 | 2026-09-09 | P00806 |  |  | 0
P009 | P009-T1 | Requirements & scope freeze | Rohan | Priya | Critical | 2026-07-09 | 2026-07-25 | 13 | In Progress |  | NO | 68 | 23 | 2026-09-09 | P00901 | P009O1 | RohanO6 | 0
P009 | P009-T2 | Design / solution | Deepa | Rahul | Critical | 2026-07-23 | 2026-08-02 | 17 | In Progress | Awaiting clarification | NO | 80 | 84 | 2026-09-09 | P00902 | P009O2 | DeepaO5 | 0
P009 | P009-T3 | BOM / commercial approval | Amit | Karan | Low | 2026-08-06 | 2026-08-17 | 33 | In Progress |  | NO | 83 | 65 | 2026-09-09 | P00903 | P009O3 | AmitO4 | 0
P009 | P009-T4 | Build / execution | Priya | Meera | Medium | 2026-08-20 | 2026-08-30 | 21 | In Progress |  | NO | 41 | 79 | 2026-09-09 | P00904 | P009O4 | PriyaO3 | 0
P009 | P009-T5 | Testing / validation | Rahul | Vivek | Low | 2026-09-03 | 2026-09-20 | 34 | In Progress |  | NO | 72 | 32 | 2026-09-09 | P00905 | P009O5 | RahulO2 | 0
P009 | P009-T6 | Customer acceptance | Karan | Ritu | Low | 2026-09-17 | 2026-09-30 | 15 | In Progress | Awaiting clarification | NO | 47 | 60 | 2026-09-09 | P00906 | P009O6 | KaranO3 | 0
P010 | P010-T1 | Requirements & scope freeze | Deepa | Rahul | Low | 2026-07-10 | 2026-07-27 | 83 | In Progress |  | NO | 51 | 28 | 2026-09-09 | P01001 | P010O1 | DeepaO6 | 0
P010 | P010-T2 | Design / solution | Amit | Karan | Low | 2026-07-24 | 2026-08-12 | 96 | In Progress |  | NO | 64 | 27 | 2026-09-09 | P01002 | P010O2 | AmitO5 | 0
P010 | P010-T3 | BOM / commercial approval | Priya | Meera | Medium | 2026-08-07 | 2026-08-16 | 76 | In Progress |  | NO | 80 | 78 | 2026-09-09 | P01003 | P010O3 | PriyaO4 | 0
P010 | P010-T4 | Build / execution | Rahul | Vivek | Low | 2026-08-21 | 2026-09-05 | 71 | In Progress | Awaiting clarification | NO | 90 | 24 | 2026-09-09 | P01004 | P010O4 | RahulO3 | 0
P010 | P010-T5 | Testing / validation | Karan | Ritu | Critical | 2026-09-04 | 2026-09-18 | 65 | In Progress |  | NO | 81 | 43 | 2026-09-09 | P01005 | P010O5 | KaranO4 | 0
P010 | P010-T6 | Customer acceptance | Meera | Sanjay | Critical | 2026-09-18 | 2026-09-30 | 75 | In Progress |  | NO | 70 | 19 | 2026-09-09 | P01006 | P010O6 | MeeraO4 | 0
P011 | P011-T1 | Requirements & scope freeze | Amit | Karan | Low | 2026-07-11 | 2026-08-02 | 91 | In Progress |  | NO | 84 | 91 | 2026-09-09 | P01101 | P011O1 | AmitO6 | 0
P011 | P011-T2 | Design / solution | Priya | Meera | Critical | 2026-07-25 | 2026-08-12 | 78 | In Progress | Awaiting clarification | NO | 56 | 40 | 2026-09-09 | P01102 | P011O2 | PriyaO5 | 0
P011 | P011-T3 | BOM / commercial approval | Rahul | Vivek | Low | 2026-08-08 | 2026-08-23 | 81 | In Progress |  | NO | 97 | 101 | 2026-09-09 | P01103 | P011O3 | RahulO4 | 0
P011 | P011-T4 | Build / execution | Karan | Ritu | Low | 2026-08-22 | 2026-09-09 | 90 | In Progress | Awaiting clarification | NO | 45 | 94 | 2026-09-09 | P01104 | P011O4 | KaranO5 | 0
P011 | P011-T5 | Testing / validation | Meera | Sanjay | Medium | 2026-09-05 | 2026-09-23 | 91 | In Progress |  | NO | 34 | 46 | 2026-09-09 | P01105 | P011O5 | MeeraO5 | 0
P011 | P011-T6 | Customer acceptance | Vivek | Anil | Low | 2026-09-19 | 2026-10-02 | 97 | In Progress |  | NO | 29 | 74 | 2026-09-09 | P01106 | P011O6 | VivekO5 | 0
P012 | P012-T1 | Requirements & scope freeze | Priya | Meera | Low | 2026-07-12 | 2026-07-27 | 22 | In Progress |  | NO | 76 | 63 | 2026-09-09 | P01201 | P012O1 | PriyaO6 | 0
P012 | P012-T2 | Design / solution | Rahul | Vivek | High | 2026-07-26 | 2026-08-16 | 58 | In Progress |  | NO | 65 | 75 | 2026-09-09 | P01202 | P012O2 | RahulO5 | 0
P012 | P012-T3 | BOM / commercial approval | Karan | Ritu | Critical | 2026-08-09 | 2026-08-23 | 35 | In Progress | Awaiting clarification | NO | 44 | 47 | 2026-09-09 | P01203 | P012O3 | KaranO6 | 0
P012 | P012-T4 | Build / execution | Meera | Sanjay | High | 2026-08-23 | 2026-09-01 | 44 | Blocked | Supplier / cross-functional dependency | YES | 51 | 93 | 2026-09-09 | P01204 | P012O4 | MeeraO6 | 0
P012 | P012-T5 | Testing / validation | Vivek | Anil | High | 2026-09-06 | 2026-09-16 | 29 | Blocked | Supplier / cross-functional dependency | YES | 72 | 63 | 2026-09-09 | P01205 | P012O5 | VivekO6 | 0
P012 | P012-T6 | Customer acceptance | Ritu | Kavya | Medium | 2026-09-20 | 2026-10-09 | 29 | Blocked | Supplier / cross-functional dependency | YES | 70 | 42 | 2026-09-09 | P01206 | P012O6 | RituO6 | 0
P013 | P013-T1 | Requirements & scope freeze | Rahul | Vivek | High | 2026-07-13 | 2026-07-29 | 62 | In Progress | Awaiting clarification | NO | 91 | 88 | 2026-09-09 | P01301 | P013O1 | RahulO6 | 0
P013 | P013-T2 | Design / solution | Karan | Ritu | High | 2026-07-27 | 2026-08-20 | 61 | In Progress |  | NO | 68 | 43 | 2026-09-09 | P01302 | P013O2 | KaranO7 | 0
P013 | P013-T3 | BOM / commercial approval | Meera | Sanjay | Low | 2026-08-10 | 2026-09-03 | 67 | In Progress |  | NO | 36 | 83 | 2026-09-09 | P01303 | P013O3 | MeeraO7 | 0
P013 | P013-T4 | Build / execution | Vivek | Anil | Medium | 2026-08-24 | 2026-09-09 | 57 | In Progress |  | NO | 64 | 50 | 2026-09-09 | P01304 | P013O4 | VivekO7 | 0
P013 | P013-T5 | Testing / validation | Ritu | Kavya | Low | 2026-09-07 | 2026-09-26 | 80 | In Progress |  | NO | 53 | 69 | 2026-09-09 | P01305 | P013O5 | RituO7 | 0
P013 | P013-T6 | Customer acceptance | Sanjay | Rohan | High | 2026-09-21 | 2026-10-13 | 59 | In Progress |  | NO | 33 | 100 | 2026-09-09 | P01306 | P013O6 | SanjayO7 | 0
P014 | P014-T1 | Requirements & scope freeze | Karan | Ritu | Medium | 2026-07-14 | 2026-08-01 | 17 | In Progress |  | NO | 89 | 38 | 2026-09-09 | P01401 | P014O1 | KaranO8 | 0
P014 | P014-T2 | Design / solution | Meera | Sanjay | Medium | 2026-07-28 | 2026-08-13 | 32 | In Progress | Awaiting clarification | NO | 26 | 86 | 2026-09-09 | P01402 | P014O2 | MeeraO8 | 0
P014 | P014-T3 | BOM / commercial approval | Vivek | Anil | Critical | 2026-08-11 | 2026-08-26 | 51 | In Progress |  | NO | 68 | 22 | 2026-09-09 | P01403 | P014O3 | VivekO8 | 0
P014 | P014-T4 | Build / execution | Ritu | Kavya | Low | 2026-08-25 | 2026-09-08 | 23 | In Progress | Awaiting clarification | NO | 67 | 34 | 2026-09-09 | P01404 | P014O4 | RituO8 | 0
P014 | P014-T5 | Testing / validation | Sanjay | Rohan | High | 2026-09-08 | 2026-09-18 | 31 | In Progress |  | NO | 41 | 29 | 2026-09-09 | P01405 | P014O5 | SanjayO8 | 0
P014 | P014-T6 | Customer acceptance | Anil | Deepa | High | 2026-09-22 | 2026-10-11 | 32 | In Progress | Awaiting clarification | NO | 42 | 55 | 2026-09-09 | P01406 | P014O6 | AnilO7 | 0
P015 | P015-T1 | Requirements & scope freeze | Meera | Sanjay | High | 2026-07-15 | 2026-07-26 | 91 | In Progress | Awaiting clarification | NO | 71 | 22 | 2026-09-09 | P01501 | P015O1 | MeeraO9 | 0
P015 | P015-T2 | Design / solution | Vivek | Anil | Medium | 2026-07-29 | 2026-08-11 | 92 | In Progress |  | NO | 56 | 26 | 2026-09-09 | P01502 | P015O2 | VivekO9 | 0
P015 | P015-T3 | BOM / commercial approval | Ritu | Kavya | Critical | 2026-08-12 | 2026-08-25 | 68 | In Progress |  | NO | 89 | 16 | 2026-09-09 | P01503 | P015O3 | RituO9 | 0
P015 | P015-T4 | Build / execution | Sanjay | Rohan | Low | 2026-08-26 | 2026-09-13 | 95 | In Progress | Awaiting clarification | YES | 97 | 37 | 2026-09-09 | P01504 | P015O4 | SanjayO9 | 0
P015 | P015-T5 | Testing / validation | Anil | Deepa | Medium | 2026-09-09 | 2026-09-26 | 72 | In Progress |  | YES | 21 | 94 | 2026-09-09 | P01505 | P015O5 | AnilO8 | 0
P015 | P015-T6 | Customer acceptance | Kavya | Amit | High | 2026-09-23 | 2026-10-12 | 69 | In Progress |  | YES | 32 | 32 | 2026-09-09 | P01506 | P015O6 | KavyaO7 | 0
P016 | P016-T1 | Requirements & scope freeze | Vivek | Anil | Critical | 2026-07-16 | 2026-07-26 | 87 | In Progress | Awaiting clarification | NO | 78 | 38 | 2026-09-09 | P01601 | P016O1 | VivekO10 | 0
P016 | P016-T2 | Design / solution | Ritu | Kavya | High | 2026-07-30 | 2026-08-21 | 100 | Completed |  | NO | 93 | 36 | 2026-09-09 | P01602 |  |  | 0
P016 | P016-T3 | BOM / commercial approval | Sanjay | Rohan | Low | 2026-08-13 | 2026-08-29 | 74 | In Progress |  | NO | 87 | 85 | 2026-09-09 | P01603 | P016O2 | SanjayO10 | 0
P016 | P016-T4 | Build / execution | Anil | Deepa | Medium | 2026-08-27 | 2026-09-20 | 98 | In Progress | Awaiting clarification | NO | 52 | 72 | 2026-09-09 | P01604 | P016O3 | AnilO9 | 0
P016 | P016-T5 | Testing / validation | Kavya | Amit | High | 2026-09-10 | 2026-09-19 | 74 | In Progress |  | NO | 80 | 54 | 2026-09-09 | P01605 | P016O4 | KavyaO8 | 0
P016 | P016-T6 | Customer acceptance | Rohan | Priya | Critical | 2026-09-24 | 2026-10-11 | 100 | Completed |  | NO | 86 | 84 | 2026-09-09 | P01606 |  |  | 0
P017 | P017-T1 | Requirements & scope freeze | Ritu | Kavya | Critical | 2026-07-17 | 2026-08-02 | 57 | In Progress |  | NO | 62 | 19 | 2026-09-09 | P01701 | P017O1 | RituO10 | 0
P017 | P017-T2 | Design / solution | Sanjay | Rohan | Low | 2026-07-31 | 2026-08-13 | 59 | In Progress |  | NO | 75 | 81 | 2026-09-09 | P01702 | P017O2 | SanjayO11 | 0
P017 | P017-T3 | BOM / commercial approval | Anil | Deepa | High | 2026-08-14 | 2026-08-30 | 47 | In Progress |  | NO | 50 | 86 | 2026-09-09 | P01703 | P017O3 | AnilO10 | 0
P017 | P017-T4 | Build / execution | Kavya | Amit | Critical | 2026-08-28 | 2026-09-10 | 53 | In Progress |  | NO | 93 | 47 | 2026-09-09 | P01704 | P017O4 | KavyaO9 | 0
P017 | P017-T5 | Testing / validation | Rohan | Priya | Critical | 2026-09-11 | 2026-09-23 | 49 | In Progress | Awaiting clarification | NO | 23 | 105 | 2026-09-09 | P01705 | P017O5 | RohanO7 | 0
P017 | P017-T6 | Customer acceptance | Deepa | Rahul | Medium | 2026-09-25 | 2026-10-18 | 77 | In Progress | Awaiting clarification | NO | 90 | 89 | 2026-09-09 | P01706 | P017O6 | DeepaO7 | 0
P018 | P018-T1 | Requirements & scope freeze | Sanjay | Rohan | Critical | 2026-07-18 | 2026-08-03 | 80 | In Progress |  | NO | 40 | 15 | 2026-09-09 | P01801 | P018O1 | SanjayO12 | 0
P018 | P018-T2 | Design / solution | Anil | Deepa | Medium | 2026-08-01 | 2026-08-19 | 88 | In Progress |  | NO | 85 | 29 | 2026-09-09 | P01802 | P018O2 | AnilO11 | 0
P018 | P018-T3 | BOM / commercial approval | Kavya | Amit | Critical | 2026-08-15 | 2026-08-25 | 65 | In Progress |  | NO | 80 | 60 | 2026-09-09 | P01803 | P018O3 | KavyaO10 | 0
P018 | P018-T4 | Build / execution | Rohan | Priya | High | 2026-08-29 | 2026-09-08 | 91 | In Progress | Awaiting clarification | NO | 99 | 72 | 2026-09-09 | P01804 | P018O4 | RohanO8 | 0
P018 | P018-T5 | Testing / validation | Deepa | Rahul | Low | 2026-09-12 | 2026-10-01 | 78 | In Progress |  | NO | 85 | 76 | 2026-09-09 | P01805 | P018O5 | DeepaO8 | 0
P018 | P018-T6 | Customer acceptance | Amit | Karan | Low | 2026-09-26 | 2026-10-08 | 74 | In Progress |  | NO | 68 | 68 | 2026-09-09 | P01806 | P018O6 | AmitO7 | 0
P019 | P019-T1 | Requirements & scope freeze | Anil | Deepa | Critical | 2026-07-19 | 2026-07-29 | 85 | In Progress |  | NO | 52 | 49 | 2026-09-09 | P01901 | P019O1 | AnilO12 | 0
P019 | P019-T2 | Design / solution | Kavya | Amit | Critical | 2026-08-02 | 2026-08-22 | 77 | In Progress |  | NO | 61 | 72 | 2026-09-09 | P01902 | P019O2 | KavyaO11 | 0
P019 | P019-T3 | BOM / commercial approval | Rohan | Priya | Critical | 2026-08-16 | 2026-08-31 | 81 | In Progress | Awaiting clarification | NO | 54 | 58 | 2026-09-09 | P01903 | P019O3 | RohanO9 | 0
P019 | P019-T4 | Build / execution | Deepa | Rahul | Medium | 2026-08-30 | 2026-09-22 | 87 | In Progress |  | YES | 54 | 86 | 2026-09-09 | P01904 | P019O4 | DeepaO9 | 0
P019 | P019-T5 | Testing / validation | Amit | Karan | High | 2026-09-13 | 2026-10-07 | 83 | In Progress |  | YES | 34 | 42 | 2026-09-09 | P01905 | P019O5 | AmitO8 | 0
P019 | P019-T6 | Customer acceptance | Priya | Meera | High | 2026-09-27 | 2026-10-17 | 96 | In Progress |  | YES | 36 | 23 | 2026-09-09 | P01906 | P019O6 | PriyaO7 | 0
P020 | P020-T1 | Requirements & scope freeze | Kavya | Amit | Low | 2026-07-20 | 2026-07-31 | 80 | In Progress | Awaiting clarification | NO | 28 | 26 | 2026-09-09 | P02001 | P020O1 | KavyaO12 | 0
P020 | P020-T2 | Design / solution | Rohan | Priya | High | 2026-08-03 | 2026-08-15 | 74 | In Progress |  | NO | 63 | 49 | 2026-09-09 | P02002 | P020O2 | RohanO10 | 0
P020 | P020-T3 | BOM / commercial approval | Deepa | Rahul | Medium | 2026-08-17 | 2026-09-09 | 72 | In Progress |  | NO | 41 | 44 | 2026-09-09 | P02003 | P020O3 | DeepaO10 | 0
P020 | P020-T4 | Build / execution | Amit | Karan | High | 2026-08-31 | 2026-09-24 | 71 | In Progress | Awaiting clarification | NO | 94 | 101 | 2026-09-09 | P02004 | P020O4 | AmitO9 | 0
P020 | P020-T5 | Testing / validation | Priya | Meera | Critical | 2026-09-14 | 2026-10-06 | 66 | In Progress |  | NO | 78 | 64 | 2026-09-09 | P02005 | P020O5 | PriyaO8 | 0
P020 | P020-T6 | Customer acceptance | Rahul | Vivek | Low | 2026-09-28 | 2026-10-15 | 75 | In Progress |  | NO | 72 | 92 | 2026-09-09 | P02006 | P020O6 | RahulO7 | 0
P021 | P021-T1 | Requirements & scope freeze | Rohan | Priya | Medium | 2026-07-21 | 2026-08-08 | 39 | In Progress |  | NO | 31 | 76 | 2026-09-09 | P02101 | P021O1 | RohanO11 | 0
P021 | P021-T2 | Design / solution | Deepa | Rahul | Low | 2026-08-04 | 2026-08-23 | 57 | In Progress | Awaiting clarification | NO | 36 | 25 | 2026-09-09 | P02102 | P021O2 | DeepaO11 | 0
P021 | P021-T3 | BOM / commercial approval | Amit | Karan | Critical | 2026-08-18 | 2026-08-30 | 25 | In Progress |  | NO | 49 | 72 | 2026-09-09 | P02103 | P021O3 | AmitO10 | 0
P021 | P021-T4 | Build / execution | Priya | Meera | Low | 2026-09-01 | 2026-09-24 | 51 | In Progress | Awaiting clarification | NO | 90 | 27 | 2026-09-09 | P02104 | P021O4 | PriyaO9 | 0
P021 | P021-T5 | Testing / validation | Rahul | Vivek | High | 2026-09-15 | 2026-10-05 | 57 | In Progress |  | NO | 62 | 23 | 2026-09-09 | P02105 | P021O5 | RahulO8 | 0
P021 | P021-T6 | Customer acceptance | Karan | Ritu | Medium | 2026-09-29 | 2026-10-18 | 36 | In Progress | Awaiting clarification | NO | 27 | 85 | 2026-09-09 | P02106 | P021O6 | KaranO9 | 0
P022 | P022-T1 | Requirements & scope freeze | Deepa | Rahul | Medium | 2026-07-22 | 2026-08-03 | 19 | In Progress | Awaiting clarification | NO | 44 | 76 | 2026-09-09 | P02201 | P022O1 | DeepaO12 | 0
P022 | P022-T2 | Design / solution | Amit | Karan | Medium | 2026-08-05 | 2026-08-14 | 28 | In Progress |  | NO | 46 | 29 | 2026-09-09 | P02202 | P022O2 | AmitO11 | 0
P022 | P022-T3 | BOM / commercial approval | Priya | Meera | High | 2026-08-19 | 2026-08-28 | 29 | In Progress | Awaiting clarification | NO | 45 | 57 | 2026-09-09 | P02203 | P022O3 | PriyaO10 | 0
P022 | P022-T4 | Build / execution | Rahul | Vivek | Low | 2026-09-02 | 2026-09-15 | 23 | In Progress |  | NO | 24 | 87 | 2026-09-09 | P02204 | P022O4 | RahulO9 | 0
P022 | P022-T5 | Testing / validation | Karan | Ritu | Critical | 2026-09-16 | 2026-10-05 | 23 | In Progress | Awaiting clarification | NO | 87 | 79 | 2026-09-09 | P02205 | P022O5 | KaranO10 | 0
P022 | P022-T6 | Customer acceptance | Meera | Sanjay | Low | 2026-09-30 | 2026-10-20 | 28 | In Progress |  | NO | 48 | 74 | 2026-09-09 | P02206 | P022O6 | MeeraO10 | 0
P023 | P023-T1 | Requirements & scope freeze | Amit | Karan | Low | 2026-07-23 | 2026-08-08 | 86 | In Progress |  | NO | 65 | 61 | 2026-09-09 | P02301 | P023O1 | AmitO12 | 0
P023 | P023-T2 | Design / solution | Priya | Meera | Medium | 2026-08-06 | 2026-08-18 | 88 | In Progress |  | NO | 62 | 76 | 2026-09-09 | P02302 | P023O2 | PriyaO11 | 0
P023 | P023-T3 | BOM / commercial approval | Rahul | Vivek | Low | 2026-08-20 | 2026-08-29 | 82 | In Progress |  | NO | 93 | 103 | 2026-09-09 | P02303 | P023O3 | RahulO10 | 0
P023 | P023-T4 | Build / execution | Karan | Ritu | Low | 2026-09-03 | 2026-09-17 | 69 | In Progress |  | NO | 93 | 23 | 2026-09-09 | P02304 | P023O4 | KaranO11 | 0
P023 | P023-T5 | Testing / validation | Meera | Sanjay | Medium | 2026-09-17 | 2026-10-07 | 80 | In Progress |  | NO | 36 | 82 | 2026-09-09 | P02305 | P023O5 | MeeraO11 | 0
P023 | P023-T6 | Customer acceptance | Vivek | Anil | Critical | 2026-10-01 | 2026-10-21 | 82 | In Progress |  | NO | 68 | 103 | 2026-09-09 | P02306 | P023O6 | VivekO11 | 0
P024 | P024-T1 | Requirements & scope freeze | Priya | Meera | Critical | 2026-07-24 | 2026-08-06 | 44 | In Progress |  | NO | 43 | 72 | 2026-09-09 | P02401 | P024O1 | PriyaO12 | 0
P024 | P024-T2 | Design / solution | Rahul | Vivek | Low | 2026-08-07 | 2026-08-26 | 38 | In Progress |  | NO | 26 | 63 | 2026-09-09 | P02402 | P024O2 | RahulO11 | 0
P024 | P024-T3 | BOM / commercial approval | Karan | Ritu | High | 2026-08-21 | 2026-09-03 | 46 | In Progress |  | NO | 47 | 92 | 2026-09-09 | P02403 | P024O3 | KaranO12 | 0
P024 | P024-T4 | Build / execution | Meera | Sanjay | Critical | 2026-09-04 | 2026-09-13 | 34 | Blocked | Supplier / cross-functional dependency | YES | 37 | 50 | 2026-09-09 | P02404 | P024O4 | MeeraO12 | 0
P024 | P024-T5 | Testing / validation | Vivek | Anil | Critical | 2026-09-18 | 2026-10-11 | 44 | Blocked | Supplier / cross-functional dependency | YES | 29 | 49 | 2026-09-09 | P02405 | P024O5 | VivekO12 | 0
P024 | P024-T6 | Customer acceptance | Ritu | Kavya | High | 2026-10-02 | 2026-10-19 | 34 | Blocked | Supplier / cross-functional dependency | YES | 22 | 15 | 2026-09-09 | P02406 | P024O6 | RituO11 | 0
P025 | P025-T1 | Requirements & scope freeze | Rahul | Vivek | Critical | 2026-07-25 | 2026-08-10 | 63 | In Progress |  | NO | 94 | 52 | 2026-09-09 | P02501 | P025O1 | RahulO12 | 0
P025 | P025-T2 | Design / solution | Karan | Ritu | Medium | 2026-08-08 | 2026-09-01 | 50 | In Progress |  | NO | 43 | 49 | 2026-09-09 | P02502 | P025O2 | KaranO13 | 0
P025 | P025-T3 | BOM / commercial approval | Meera | Sanjay | Low | 2026-08-22 | 2026-09-03 | 78 | In Progress |  | NO | 28 | 25 | 2026-09-09 | P02503 | P025O3 | MeeraO13 | 0
P025 | P025-T4 | Build / execution | Vivek | Anil | Medium | 2026-09-05 | 2026-09-15 | 55 | In Progress |  | NO | 48 | 73 | 2026-09-09 | P02504 | P025O4 | VivekO13 | 0
P025 | P025-T5 | Testing / validation | Ritu | Kavya | Low | 2026-09-19 | 2026-10-11 | 83 | In Progress | Awaiting clarification | NO | 35 | 102 | 2026-09-09 | P02505 | P025O5 | RituO12 | 0
P025 | P025-T6 | Customer acceptance | Sanjay | Rohan | Critical | 2026-10-03 | 2026-10-19 | 71 | In Progress |  | NO | 45 | 57 | 2026-09-09 | P02506 | P025O6 | SanjayO13 | 0
P026 | P026-T1 | Requirements & scope freeze | Karan | Ritu | Critical | 2026-07-26 | 2026-08-16 | 84 | In Progress |  | NO | 56 | 102 | 2026-09-09 | P02601 | P026O1 | KaranO14 | 0
P026 | P026-T2 | Design / solution | Meera | Sanjay | High | 2026-08-09 | 2026-08-21 | 75 | In Progress | Awaiting clarification | NO | 64 | 41 | 2026-09-09 | P02602 | P026O2 | MeeraO14 | 0
P026 | P026-T3 | BOM / commercial approval | Vivek | Anil | High | 2026-08-23 | 2026-09-05 | 84 | In Progress |  | NO | 77 | 77 | 2026-09-09 | P02603 | P026O3 | VivekO14 | 0
P026 | P026-T4 | Build / execution | Ritu | Kavya | Low | 2026-09-06 | 2026-09-30 | 99 | In Progress |  | NO | 49 | 75 | 2026-09-09 | P02604 | P026O4 | RituO13 | 0
P026 | P026-T5 | Testing / validation | Sanjay | Rohan | Medium | 2026-09-20 | 2026-10-10 | 77 | In Progress |  | NO | 67 | 44 | 2026-09-09 | P02605 | P026O5 | SanjayO14 | 0
P026 | P026-T6 | Customer acceptance | Anil | Deepa | High | 2026-10-04 | 2026-10-28 | 100 | Completed | Awaiting clarification | NO | 88 | 69 | 2026-09-09 | P02606 |  |  | 0
P027 | P027-T1 | Requirements & scope freeze | Meera | Sanjay | Critical | 2026-07-27 | 2026-08-17 | 33 | In Progress | Awaiting clarification | NO | 30 | 86 | 2026-09-09 | P02701 | P027O1 | MeeraO15 | 0
P027 | P027-T2 | Design / solution | Vivek | Anil | High | 2026-08-10 | 2026-08-21 | 31 | In Progress |  | NO | 45 | 85 | 2026-09-09 | P02702 | P027O2 | VivekO15 | 0
P027 | P027-T3 | BOM / commercial approval | Ritu | Kavya | Critical | 2026-08-24 | 2026-09-15 | 42 | In Progress | Awaiting clarification | NO | 59 | 91 | 2026-09-09 | P02703 | P027O3 | RituO14 | 0
P027 | P027-T4 | Build / execution | Sanjay | Rohan | Low | 2026-09-07 | 2026-09-25 | 59 | In Progress |  | NO | 97 | 48 | 2026-09-09 | P02704 | P027O4 | SanjayO15 | 0
P027 | P027-T5 | Testing / validation | Anil | Deepa | Critical | 2026-09-21 | 2026-10-08 | 30 | In Progress |  | NO | 56 | 90 | 2026-09-09 | P02705 | P027O5 | AnilO13 | 0
P027 | P027-T6 | Customer acceptance | Kavya | Amit | Medium | 2026-10-05 | 2026-10-25 | 63 | In Progress |  | NO | 97 | 43 | 2026-09-09 | P02706 | P027O6 | KavyaO13 | 0
P028 | P028-T1 | Requirements & scope freeze | Vivek | Anil | Medium | 2026-07-28 | 2026-08-13 | 67 | In Progress | Awaiting clarification | NO | 76 | 65 | 2026-09-09 | P02801 | P028O1 | VivekO16 | 0
P028 | P028-T2 | Design / solution | Ritu | Kavya | Low | 2026-08-11 | 2026-08-24 | 60 | In Progress | Awaiting clarification | NO | 64 | 68 | 2026-09-09 | P02802 | P028O2 | RituO15 | 0
P028 | P028-T3 | BOM / commercial approval | Sanjay | Rohan | High | 2026-08-25 | 2026-09-03 | 59 | In Progress | Awaiting clarification | NO | 39 | 48 | 2026-09-09 | P02803 | P028O3 | SanjayO16 | 0
P028 | P028-T4 | Build / execution | Anil | Deepa | High | 2026-09-08 | 2026-09-21 | 59 | In Progress |  | NO | 39 | 96 | 2026-09-09 | P02804 | P028O4 | AnilO14 | 0
P028 | P028-T5 | Testing / validation | Kavya | Amit | Critical | 2026-09-22 | 2026-10-14 | 79 | In Progress |  | NO | 56 | 23 | 2026-09-09 | P02805 | P028O5 | KavyaO14 | 0
P028 | P028-T6 | Customer acceptance | Rohan | Priya | Critical | 2026-10-06 | 2026-10-17 | 83 | In Progress | Awaiting clarification | NO | 49 | 37 | 2026-09-09 | P02806 | P028O6 | RohanO12 | 0
P029 | P029-T1 | Requirements & scope freeze | Ritu | Kavya | Critical | 2026-07-29 | 2026-08-13 | 36 | In Progress |  | NO | 39 | 79 | 2026-09-09 | P02901 | P029O1 | RituO16 | 0
P029 | P029-T2 | Design / solution | Sanjay | Rohan | Low | 2026-08-12 | 2026-08-24 | 58 | In Progress |  | NO | 31 | 36 | 2026-09-09 | P02902 | P029O2 | SanjayO17 | 0
P029 | P029-T3 | BOM / commercial approval | Anil | Deepa | High | 2026-08-26 | 2026-09-04 | 53 | In Progress | Awaiting clarification | NO | 42 | 45 | 2026-09-09 | P02903 | P029O3 | AnilO15 | 0
P029 | P029-T4 | Build / execution | Kavya | Amit | Critical | 2026-09-09 | 2026-10-03 | 43 | In Progress | Awaiting clarification | NO | 37 | 78 | 2026-09-09 | P02904 | P029O4 | KavyaO15 | 0
P029 | P029-T5 | Testing / validation | Rohan | Priya | Medium | 2026-09-23 | 2026-10-09 | 35 | In Progress |  | NO | 53 | 65 | 2026-09-09 | P02905 | P029O5 | RohanO13 | 0
P029 | P029-T6 | Customer acceptance | Deepa | Rahul | High | 2026-10-07 | 2026-10-20 | 49 | In Progress |  | NO | 22 | 17 | 2026-09-09 | P02906 | P029O6 | DeepaO13 | 0
P030 | P030-T1 | Requirements & scope freeze | Sanjay | Rohan | Medium | 2026-07-30 | 2026-08-10 | 67 | In Progress |  | NO | 92 | 88 | 2026-09-09 | P03001 | P030O1 | SanjayO18 | 0
P030 | P030-T2 | Design / solution | Anil | Deepa | Critical | 2026-08-13 | 2026-08-26 | 91 | In Progress |  | NO | 32 | 66 | 2026-09-09 | P03002 | P030O2 | AnilO16 | 0
P030 | P030-T3 | BOM / commercial approval | Kavya | Amit | Low | 2026-08-27 | 2026-09-16 | 91 | In Progress |  | NO | 56 | 88 | 2026-09-09 | P03003 | P030O3 | KavyaO16 | 0
P030 | P030-T4 | Build / execution | Rohan | Priya | Medium | 2026-09-10 | 2026-09-28 | 90 | In Progress | Awaiting clarification | NO | 41 | 63 | 2026-09-09 | P03004 | P030O4 | RohanO14 | 0
P030 | P030-T5 | Testing / validation | Deepa | Rahul | Medium | 2026-09-24 | 2026-10-04 | 73 | In Progress |  | NO | 60 | 89 | 2026-09-09 | P03005 | P030O5 | DeepaO14 | 0
P030 | P030-T6 | Customer acceptance | Amit | Karan | Medium | 2026-10-08 | 2026-10-28 | 66 | In Progress |  | NO | 51 | 27 | 2026-09-09 | P03006 | P030O6 | AmitO13 | 0
P031 | P031-T1 | Requirements & scope freeze | Anil | Deepa | Medium | 2026-07-31 | 2026-08-11 | 79 | In Progress | Awaiting clarification | NO | 98 | 96 | 2026-09-09 | P03101 | P031O1 | AnilO17 | 0
P031 | P031-T2 | Design / solution | Kavya | Amit | High | 2026-08-14 | 2026-09-01 | 67 | In Progress |  | NO | 99 | 97 | 2026-09-09 | P03102 | P031O2 | KavyaO17 | 0
P031 | P031-T3 | BOM / commercial approval | Rohan | Priya | High | 2026-08-28 | 2026-09-11 | 52 | In Progress |  | NO | 39 | 61 | 2026-09-09 | P03103 | P031O3 | RohanO15 | 0
P031 | P031-T4 | Build / execution | Deepa | Rahul | Critical | 2026-09-11 | 2026-09-22 | 80 | In Progress |  | NO | 29 | 15 | 2026-09-09 | P03104 | P031O4 | DeepaO15 | 0
P031 | P031-T5 | Testing / validation | Amit | Karan | Medium | 2026-09-25 | 2026-10-16 | 67 | In Progress |  | NO | 50 | 85 | 2026-09-09 | P03105 | P031O5 | AmitO14 | 0
P031 | P031-T6 | Customer acceptance | Priya | Meera | High | 2026-10-09 | 2026-10-27 | 77 | In Progress |  | NO | 54 | 19 | 2026-09-09 | P03106 | P031O6 | PriyaO13 | 0
P032 | P032-T1 | Requirements & scope freeze | Kavya | Amit | Medium | 2026-08-01 | 2026-08-16 | 27 | In Progress |  | NO | 48 | 47 | 2026-09-09 | P03201 | P032O1 | KavyaO18 | 0
P032 | P032-T2 | Design / solution | Rohan | Priya | Medium | 2026-08-15 | 2026-09-07 | 15 | In Progress |  | NO | 76 | 20 | 2026-09-09 | P03202 | P032O2 | RohanO16 | 0
P032 | P032-T3 | BOM / commercial approval | Deepa | Rahul | Critical | 2026-08-29 | 2026-09-12 | 17 | In Progress |  | NO | 61 | 80 | 2026-09-09 | P03203 | P032O3 | DeepaO16 | 0
P032 | P032-T4 | Build / execution | Amit | Karan | High | 2026-09-12 | 2026-09-21 | 26 | In Progress |  | NO | 20 | 81 | 2026-09-09 | P03204 | P032O4 | AmitO15 | 0
P032 | P032-T5 | Testing / validation | Priya | Meera | Medium | 2026-09-26 | 2026-10-14 | 26 | In Progress |  | NO | 51 | 75 | 2026-09-09 | P03205 | P032O5 | PriyaO14 | 0
P032 | P032-T6 | Customer acceptance | Rahul | Vivek | Low | 2026-10-10 | 2026-10-24 | 21 | In Progress |  | NO | 80 | 86 | 2026-09-09 | P03206 | P032O6 | RahulO13 | 0
P033 | P033-T1 | Requirements & scope freeze | Rohan | Priya | High | 2026-08-02 | 2026-08-15 | 26 | In Progress | Awaiting clarification | NO | 85 | 46 | 2026-09-09 | P03301 | P033O1 | RohanO17 | 0
P033 | P033-T2 | Design / solution | Deepa | Rahul | Medium | 2026-08-16 | 2026-09-09 | 54 | In Progress |  | NO | 82 | 91 | 2026-09-09 | P03302 | P033O2 | DeepaO17 | 0
P033 | P033-T3 | BOM / commercial approval | Amit | Karan | Critical | 2026-08-30 | 2026-09-12 | 31 | In Progress |  | NO | 99 | 31 | 2026-09-09 | P03303 | P033O3 | AmitO16 | 0
P033 | P033-T4 | Build / execution | Priya | Meera | Low | 2026-09-13 | 2026-09-24 | 50 | In Progress |  | NO | 42 | 101 | 2026-09-09 | P03304 | P033O4 | PriyaO15 | 0
P033 | P033-T5 | Testing / validation | Rahul | Vivek | Critical | 2026-09-27 | 2026-10-21 | 55 | In Progress |  | NO | 28 | 32 | 2026-09-09 | P03305 | P033O5 | RahulO14 | 0
P033 | P033-T6 | Customer acceptance | Karan | Ritu | Medium | 2026-10-11 | 2026-11-04 | 27 | In Progress |  | NO | 81 | 75 | 2026-09-09 | P03306 | P033O6 | KaranO15 | 0
P034 | P034-T1 | Requirements & scope freeze | Deepa | Rahul | Medium | 2026-08-03 | 2026-08-19 | 94 | In Progress |  | NO | 37 | 73 | 2026-09-09 | P03401 | P034O1 | DeepaO18 | 0
P034 | P034-T2 | Design / solution | Amit | Karan | Low | 2026-08-17 | 2026-08-31 | 81 | In Progress |  | NO | 85 | 52 | 2026-09-09 | P03402 | P034O2 | AmitO17 | 0
P034 | P034-T3 | BOM / commercial approval | Priya | Meera | High | 2026-08-31 | 2026-09-18 | 87 | In Progress |  | NO | 90 | 52 | 2026-09-09 | P03403 | P034O3 | PriyaO16 | 0
P034 | P034-T4 | Build / execution | Rahul | Vivek | High | 2026-09-14 | 2026-09-28 | 92 | In Progress |  | NO | 63 | 48 | 2026-09-09 | P03404 | P034O4 | RahulO15 | 0
P034 | P034-T5 | Testing / validation | Karan | Ritu | Low | 2026-09-28 | 2026-10-19 | 98 | In Progress | Awaiting clarification | NO | 99 | 17 | 2026-09-09 | P03405 | P034O5 | KaranO16 | 0
P034 | P034-T6 | Customer acceptance | Meera | Sanjay | Low | 2026-10-12 | 2026-11-02 | 78 | In Progress |  | NO | 87 | 68 | 2026-09-09 | P03406 | P034O6 | MeeraO16 | 0
P035 | P035-T1 | Requirements & scope freeze | Amit | Karan | Low | 2026-08-04 | 2026-08-23 | 41 | In Progress |  | NO | 57 | 56 | 2026-09-09 | P03501 | P035O1 | AmitO18 | 0
P035 | P035-T2 | Design / solution | Priya | Meera | High | 2026-08-18 | 2026-09-05 | 39 | In Progress |  | NO | 34 | 66 | 2026-09-09 | P03502 | P035O2 | PriyaO17 | 0
P035 | P035-T3 | BOM / commercial approval | Rahul | Vivek | Medium | 2026-09-01 | 2026-09-13 | 62 | In Progress |  | NO | 100 | 100 | 2026-09-09 | P03503 | P035O3 | RahulO16 | 0
P035 | P035-T4 | Build / execution | Karan | Ritu | Medium | 2026-09-15 | 2026-10-09 | 36 | Blocked | Supplier / cross-functional dependency | YES | 69 | 18 | 2026-09-09 | P03504 | P035O4 | KaranO17 | 0
P035 | P035-T5 | Testing / validation | Meera | Sanjay | Critical | 2026-09-29 | 2026-10-12 | 52 | In Progress | Awaiting clarification | YES | 60 | 53 | 2026-09-09 | P03505 | P035O5 | MeeraO17 | 0
P035 | P035-T6 | Customer acceptance | Vivek | Anil | High | 2026-10-13 | 2026-10-23 | 53 | In Progress |  | YES | 53 | 97 | 2026-09-09 | P03506 | P035O6 | VivekO17 | 0
P036 | P036-T1 | Requirements & scope freeze | Priya | Meera | Critical | 2026-08-05 | 2026-08-24 | 59 | In Progress |  | NO | 69 | 55 | 2026-09-09 | P03601 | P036O1 | PriyaO18 | 0
P036 | P036-T2 | Design / solution | Rahul | Vivek | Critical | 2026-08-19 | 2026-08-30 | 32 | In Progress |  | NO | 64 | 28 | 2026-09-09 | P03602 | P036O2 | RahulO17 | 0
P036 | P036-T3 | BOM / commercial approval | Karan | Ritu | High | 2026-09-02 | 2026-09-14 | 47 | In Progress |  | NO | 25 | 84 | 2026-09-09 | P03603 | P036O3 | KaranO18 | 0
P036 | P036-T4 | Build / execution | Meera | Sanjay | High | 2026-09-16 | 2026-09-30 | 44 | In Progress |  | NO | 51 | 23 | 2026-09-09 | P03604 | P036O4 | MeeraO18 | 0
P036 | P036-T5 | Testing / validation | Vivek | Anil | Critical | 2026-09-30 | 2026-10-16 | 62 | In Progress | Awaiting clarification | NO | 20 | 100 | 2026-09-09 | P03605 | P036O5 | VivekO18 | 0
P036 | P036-T6 | Customer acceptance | Ritu | Kavya | High | 2026-10-14 | 2026-10-31 | 37 | In Progress |  | NO | 26 | 89 | 2026-09-09 | P03606 | P036O6 | RituO17 | 0
P037 | P037-T1 | Requirements & scope freeze | Rahul | Vivek | Low | 2026-08-06 | 2026-08-29 | 59 | In Progress |  | NO | 73 | 43 | 2026-09-09 | P03701 | P037O1 | RahulO18 | 0
P037 | P037-T2 | Design / solution | Karan | Ritu | Critical | 2026-08-20 | 2026-09-06 | 74 | In Progress | Awaiting clarification | NO | 46 | 93 | 2026-09-09 | P03702 | P037O2 | KaranO19 | 0
P037 | P037-T3 | BOM / commercial approval | Meera | Sanjay | High | 2026-09-03 | 2026-09-24 | 86 | In Progress | Awaiting clarification | NO | 22 | 49 | 2026-09-09 | P03703 | P037O3 | MeeraO19 | 0
P037 | P037-T4 | Build / execution | Vivek | Anil | High | 2026-09-17 | 2026-09-30 | 93 | In Progress |  | NO | 74 | 67 | 2026-09-09 | P03704 | P037O4 | VivekO19 | 0
P037 | P037-T5 | Testing / validation | Ritu | Kavya | Critical | 2026-10-01 | 2026-10-16 | 75 | In Progress |  | NO | 50 | 68 | 2026-09-09 | P03705 | P037O5 | RituO18 | 0
P037 | P037-T6 | Customer acceptance | Sanjay | Rohan | Critical | 2026-10-15 | 2026-10-30 | 62 | In Progress |  | NO | 26 | 84 | 2026-09-09 | P03706 | P037O6 | SanjayO19 | 0
P038 | P038-T1 | Requirements & scope freeze | Karan | Ritu | High | 2026-08-07 | 2026-08-16 | 95 | In Progress | Awaiting clarification | NO | 77 | 29 | 2026-09-09 | P03801 | P038O1 | KaranO20 | 0
P038 | P038-T2 | Design / solution | Meera | Sanjay | Critical | 2026-08-21 | 2026-09-14 | 86 | In Progress | Awaiting clarification | NO | 73 | 72 | 2026-09-09 | P03802 | P038O2 | MeeraO20 | 0
P038 | P038-T3 | BOM / commercial approval | Vivek | Anil | Low | 2026-09-04 | 2026-09-24 | 65 | In Progress | Awaiting clarification | NO | 57 | 27 | 2026-09-09 | P03803 | P038O3 | VivekO20 | 0
P038 | P038-T4 | Build / execution | Ritu | Kavya | High | 2026-09-18 | 2026-09-30 | 68 | In Progress | Awaiting clarification | NO | 38 | 47 | 2026-09-09 | P03804 | P038O4 | RituO19 | 0
P038 | P038-T5 | Testing / validation | Sanjay | Rohan | Low | 2026-10-02 | 2026-10-17 | 75 | In Progress |  | NO | 56 | 56 | 2026-09-09 | P03805 | P038O5 | SanjayO20 | 0
P038 | P038-T6 | Customer acceptance | Anil | Deepa | Low | 2026-10-16 | 2026-10-26 | 66 | In Progress |  | NO | 63 | 57 | 2026-09-09 | P03806 | P038O6 | AnilO18 | 0
P039 | P039-T1 | Requirements & scope freeze | Meera | Sanjay | High | 2026-08-08 | 2026-09-01 | 92 | In Progress |  | NO | 69 | 71 | 2026-09-09 | P03901 | P039O1 | MeeraO21 | 0
P039 | P039-T2 | Design / solution | Vivek | Anil | Low | 2026-08-22 | 2026-09-13 | 63 | In Progress |  | NO | 86 | 33 | 2026-09-09 | P03902 | P039O2 | VivekO21 | 0
P039 | P039-T3 | BOM / commercial approval | Ritu | Kavya | High | 2026-09-05 | 2026-09-27 | 67 | In Progress |  | NO | 35 | 64 | 2026-09-09 | P03903 | P039O3 | RituO20 | 0
P039 | P039-T4 | Build / execution | Sanjay | Rohan | High | 2026-09-19 | 2026-10-01 | 88 | In Progress |  | NO | 83 | 16 | 2026-09-09 | P03904 | P039O4 | SanjayO21 | 0
P039 | P039-T5 | Testing / validation | Anil | Deepa | Critical | 2026-10-03 | 2026-10-18 | 76 | In Progress | Awaiting clarification | NO | 82 | 26 | 2026-09-09 | P03905 | P039O5 | AnilO19 | 0
P039 | P039-T6 | Customer acceptance | Kavya | Amit | Low | 2026-10-17 | 2026-10-31 | 65 | In Progress |  | NO | 45 | 56 | 2026-09-09 | P03906 | P039O6 | KavyaO19 | 0
P040 | P040-T1 | Requirements & scope freeze | Vivek | Anil | Low | 2026-08-09 | 2026-08-25 | 48 | In Progress |  | NO | 78 | 55 | 2026-09-09 | P04001 | P040O1 | VivekO22 | 0
P040 | P040-T2 | Design / solution | Ritu | Kavya | Critical | 2026-08-23 | 2026-09-14 | 47 | In Progress |  | NO | 30 | 51 | 2026-09-09 | P04002 | P040O2 | RituO21 | 0
P040 | P040-T3 | BOM / commercial approval | Sanjay | Rohan | Critical | 2026-09-06 | 2026-09-27 | 43 | In Progress |  | NO | 23 | 17 | 2026-09-09 | P04003 | P040O3 | SanjayO22 | 0
P040 | P040-T4 | Build / execution | Anil | Deepa | High | 2026-09-20 | 2026-10-06 | 52 | In Progress |  | NO | 72 | 21 | 2026-09-09 | P04004 | P040O4 | AnilO20 | 0
P040 | P040-T5 | Testing / validation | Kavya | Amit | High | 2026-10-04 | 2026-10-24 | 34 | Blocked | Supplier / cross-functional dependency | YES | 62 | 63 | 2026-09-09 | P04005 | P040O5 | KavyaO20 | 0
P040 | P040-T6 | Customer acceptance | Rohan | Priya | Medium | 2026-10-18 | 2026-11-04 | 59 | In Progress |  | NO | 44 | 81 | 2026-09-09 | P04006 | P040O6 | RohanO18 | 0
P041 | P041-T1 | Requirements & scope freeze | Ritu | Kavya | Medium | 2026-08-10 | 2026-08-22 | 18 | In Progress |  | NO | 43 | 79 | 2026-09-09 | P04101 | P041O1 | RituO22 | 0
P041 | P041-T2 | Design / solution | Sanjay | Rohan | High | 2026-08-24 | 2026-09-10 | 35 | In Progress |  | NO | 77 | 72 | 2026-09-09 | P04102 | P041O2 | SanjayO23 | 0
P041 | P041-T3 | BOM / commercial approval | Anil | Deepa | Critical | 2026-09-07 | 2026-10-01 | 45 | In Progress |  | NO | 74 | 92 | 2026-09-09 | P04103 | P041O3 | AnilO21 | 0
P041 | P041-T4 | Build / execution | Kavya | Amit | High | 2026-09-21 | 2026-10-08 | 49 | In Progress | Awaiting clarification | NO | 85 | 78 | 2026-09-09 | P04104 | P041O4 | KavyaO21 | 0
P041 | P041-T5 | Testing / validation | Rohan | Priya | Critical | 2026-10-05 | 2026-10-27 | 42 | In Progress | Awaiting clarification | NO | 94 | 57 | 2026-09-09 | P04105 | P041O5 | RohanO19 | 0
P041 | P041-T6 | Customer acceptance | Deepa | Rahul | Critical | 2026-10-19 | 2026-10-29 | 20 | In Progress | Awaiting clarification | NO | 87 | 85 | 2026-09-09 | P04106 | P041O6 | DeepaO19 | 0
P042 | P042-T1 | Requirements & scope freeze | Sanjay | Rohan | High | 2026-08-11 | 2026-08-28 | 38 | In Progress |  | NO | 36 | 53 | 2026-09-09 | P04201 | P042O1 | SanjayO24 | 0
P042 | P042-T2 | Design / solution | Anil | Deepa | Low | 2026-08-25 | 2026-09-09 | 40 | In Progress |  | NO | 70 | 41 | 2026-09-09 | P04202 | P042O2 | AnilO22 | 0
P042 | P042-T3 | BOM / commercial approval | Kavya | Amit | High | 2026-09-08 | 2026-09-17 | 36 | In Progress | Awaiting clarification | NO | 38 | 60 | 2026-09-09 | P04203 | P042O3 | KavyaO22 | 0
P042 | P042-T4 | Build / execution | Rohan | Priya | High | 2026-09-22 | 2026-10-07 | 19 | In Progress |  | NO | 59 | 91 | 2026-09-09 | P04204 | P042O4 | RohanO20 | 0
P042 | P042-T5 | Testing / validation | Deepa | Rahul | High | 2026-10-06 | 2026-10-20 | 33 | In Progress |  | NO | 97 | 15 | 2026-09-09 | P04205 | P042O5 | DeepaO20 | 0
P042 | P042-T6 | Customer acceptance | Amit | Karan | Low | 2026-10-20 | 2026-11-13 | 50 | In Progress |  | NO | 99 | 86 | 2026-09-09 | P04206 | P042O6 | AmitO19 | 0
P043 | P043-T1 | Requirements & scope freeze | Anil | Deepa | Low | 2026-08-12 | 2026-08-24 | 82 | In Progress |  | NO | 47 | 46 | 2026-09-09 | P04301 | P043O1 | AnilO23 | 0
P043 | P043-T2 | Design / solution | Kavya | Amit | High | 2026-08-26 | 2026-09-11 | 59 | In Progress |  | NO | 34 | 48 | 2026-09-09 | P04302 | P043O2 | KavyaO23 | 0
P043 | P043-T3 | BOM / commercial approval | Rohan | Priya | High | 2026-09-09 | 2026-09-22 | 75 | In Progress | Awaiting clarification | NO | 94 | 84 | 2026-09-09 | P04303 | P043O3 | RohanO21 | 0
P043 | P043-T4 | Build / execution | Deepa | Rahul | Low | 2026-09-23 | 2026-10-08 | 62 | In Progress |  | NO | 62 | 73 | 2026-09-09 | P04304 | P043O4 | DeepaO21 | 0
P043 | P043-T5 | Testing / validation | Amit | Karan | Critical | 2026-10-07 | 2026-10-16 | 75 | In Progress |  | NO | 31 | 71 | 2026-09-09 | P04305 | P043O5 | AmitO20 | 0
P043 | P043-T6 | Customer acceptance | Priya | Meera | Medium | 2026-10-21 | 2026-11-13 | 84 | In Progress | Awaiting clarification | NO | 32 | 54 | 2026-09-09 | P04306 | P043O6 | PriyaO19 | 0
P044 | P044-T1 | Requirements & scope freeze | Kavya | Amit | Critical | 2026-08-13 | 2026-08-22 | 52 | In Progress |  | NO | 26 | 84 | 2026-09-09 | P04401 | P044O1 | KavyaO24 | 0
P044 | P044-T2 | Design / solution | Rohan | Priya | High | 2026-08-27 | 2026-09-13 | 41 | In Progress |  | NO | 63 | 17 | 2026-09-09 | P04402 | P044O2 | RohanO22 | 0
P044 | P044-T3 | BOM / commercial approval | Deepa | Rahul | Medium | 2026-09-10 | 2026-10-02 | 49 | In Progress |  | NO | 57 | 34 | 2026-09-09 | P04403 | P044O3 | DeepaO22 | 0
P044 | P044-T4 | Build / execution | Amit | Karan | High | 2026-09-24 | 2026-10-03 | 37 | Blocked | Supplier / cross-functional dependency | YES | 85 | 80 | 2026-09-09 | P04404 | P044O4 | AmitO21 | 0
P044 | P044-T5 | Testing / validation | Priya | Meera | High | 2026-10-08 | 2026-10-20 | 55 | In Progress |  | NO | 63 | 86 | 2026-09-09 | P04405 | P044O5 | PriyaO20 | 0
P044 | P044-T6 | Customer acceptance | Rahul | Vivek | High | 2026-10-22 | 2026-11-09 | 48 | In Progress | Awaiting clarification | NO | 48 | 102 | 2026-09-09 | P04406 | P044O6 | RahulO19 | 0
P045 | P045-T1 | Requirements & scope freeze | Rohan | Priya | Medium | 2026-08-14 | 2026-09-04 | 55 | In Progress |  | NO | 58 | 36 | 2026-09-09 | P04501 | P045O1 | RohanO23 | 0
P045 | P045-T2 | Design / solution | Deepa | Rahul | High | 2026-08-28 | 2026-09-19 | 29 | In Progress |  | NO | 61 | 67 | 2026-09-09 | P04502 | P045O2 | DeepaO23 | 0
P045 | P045-T3 | BOM / commercial approval | Amit | Karan | Medium | 2026-09-11 | 2026-09-25 | 62 | In Progress |  | NO | 64 | 36 | 2026-09-09 | P04503 | P045O3 | AmitO22 | 0
P045 | P045-T4 | Build / execution | Priya | Meera | Critical | 2026-09-25 | 2026-10-18 | 36 | Blocked | Supplier / cross-functional dependency | YES | 91 | 78 | 2026-09-09 | P04504 | P045O4 | PriyaO21 | 0
P045 | P045-T5 | Testing / validation | Rahul | Vivek | Critical | 2026-10-09 | 2026-11-01 | 48 | In Progress |  | YES | 61 | 28 | 2026-09-09 | P04505 | P045O5 | RahulO20 | 0
P045 | P045-T6 | Customer acceptance | Karan | Ritu | High | 2026-10-23 | 2026-11-11 | 48 | In Progress |  | YES | 78 | 82 | 2026-09-09 | P04506 | P045O6 | KaranO21 | 0
P046 | P046-T1 | Requirements & scope freeze | Deepa | Rahul | High | 2026-08-15 | 2026-08-31 | 95 | In Progress | Awaiting clarification | NO | 66 | 44 | 2026-09-09 | P04601 | P046O1 | DeepaO24 | 0
P046 | P046-T2 | Design / solution | Amit | Karan | High | 2026-08-29 | 2026-09-18 | 79 | In Progress |  | NO | 42 | 31 | 2026-09-09 | P04602 | P046O2 | AmitO23 | 0
P046 | P046-T3 | BOM / commercial approval | Priya | Meera | Low | 2026-09-12 | 2026-10-01 | 81 | In Progress |  | NO | 79 | 72 | 2026-09-09 | P04603 | P046O3 | PriyaO22 | 0
P046 | P046-T4 | Build / execution | Rahul | Vivek | Low | 2026-09-26 | 2026-10-06 | 92 | In Progress | Awaiting clarification | NO | 90 | 88 | 2026-09-09 | P04604 | P046O4 | RahulO21 | 0
P046 | P046-T5 | Testing / validation | Karan | Ritu | High | 2026-10-10 | 2026-10-27 | 73 | In Progress |  | NO | 88 | 17 | 2026-09-09 | P04605 | P046O5 | KaranO22 | 0
P046 | P046-T6 | Customer acceptance | Meera | Sanjay | Critical | 2026-10-24 | 2026-11-17 | 77 | In Progress |  | NO | 22 | 45 | 2026-09-09 | P04606 | P046O6 | MeeraO22 | 0
P047 | P047-T1 | Requirements & scope freeze | Amit | Karan | Low | 2026-08-16 | 2026-08-25 | 58 | In Progress |  | NO | 74 | 74 | 2026-09-09 | P04701 | P047O1 | AmitO24 | 0
P047 | P047-T2 | Design / solution | Priya | Meera | Critical | 2026-08-30 | 2026-09-23 | 82 | In Progress |  | NO | 25 | 69 | 2026-09-09 | P04702 | P047O2 | PriyaO23 | 0
P047 | P047-T3 | BOM / commercial approval | Rahul | Vivek | Low | 2026-09-13 | 2026-10-02 | 71 | In Progress |  | NO | 76 | 17 | 2026-09-09 | P04703 | P047O3 | RahulO22 | 0
P047 | P047-T4 | Build / execution | Karan | Ritu | Low | 2026-09-27 | 2026-10-06 | 85 | In Progress |  | NO | 53 | 73 | 2026-09-09 | P04704 | P047O4 | KaranO23 | 0
P047 | P047-T5 | Testing / validation | Meera | Sanjay | Critical | 2026-10-11 | 2026-10-29 | 87 | In Progress |  | NO | 97 | 30 | 2026-09-09 | P04705 | P047O5 | MeeraO23 | 0
P047 | P047-T6 | Customer acceptance | Vivek | Anil | High | 2026-10-25 | 2026-11-17 | 87 | In Progress | Awaiting clarification | NO | 86 | 75 | 2026-09-09 | P04706 | P047O6 | VivekO23 | 0
P048 | P048-T1 | Requirements & scope freeze | Priya | Meera | High | 2026-08-17 | 2026-08-31 | 60 | In Progress |  | NO | 82 | 41 | 2026-09-09 | P04801 | P048O1 | PriyaO24 | 0
P048 | P048-T2 | Design / solution | Rahul | Vivek | Critical | 2026-08-31 | 2026-09-22 | 71 | In Progress | Awaiting clarification | NO | 65 | 72 | 2026-09-09 | P04802 | P048O2 | RahulO23 | 0
P048 | P048-T3 | BOM / commercial approval | Karan | Ritu | Critical | 2026-09-14 | 2026-10-06 | 47 | In Progress |  | NO | 44 | 34 | 2026-09-09 | P04803 | P048O3 | KaranO24 | 0
P048 | P048-T4 | Build / execution | Meera | Sanjay | Critical | 2026-09-28 | 2026-10-12 | 83 | In Progress |  | NO | 61 | 44 | 2026-09-09 | P04804 | P048O4 | MeeraO24 | 0
P048 | P048-T5 | Testing / validation | Vivek | Anil | High | 2026-10-12 | 2026-10-23 | 48 | In Progress |  | NO | 38 | 30 | 2026-09-09 | P04805 | P048O5 | VivekO24 | 0
P048 | P048-T6 | Customer acceptance | Ritu | Kavya | Medium | 2026-10-26 | 2026-11-19 | 66 | In Progress |  | NO | 95 | 86 | 2026-09-09 | P04806 | P048O6 | RituO23 | 0
P049 | P049-T1 | Requirements & scope freeze | Rahul | Vivek | High | 2026-08-18 | 2026-09-04 | 33 | In Progress | Awaiting clarification | NO | 73 | 80 | 2026-09-09 | P04901 | P049O1 | RahulO24 | 0
P049 | P049-T2 | Design / solution | Karan | Ritu | Medium | 2026-09-01 | 2026-09-20 | 43 | In Progress | Awaiting clarification | NO | 31 | 95 | 2026-09-09 | P04902 | P049O2 | KaranO25 | 0
P049 | P049-T3 | BOM / commercial approval | Meera | Sanjay | Critical | 2026-09-15 | 2026-10-02 | 61 | In Progress | Awaiting clarification | NO | 55 | 90 | 2026-09-09 | P04903 | P049O3 | MeeraO25 | 0
P049 | P049-T4 | Build / execution | Vivek | Anil | Medium | 2026-09-29 | 2026-10-18 | 43 | In Progress |  | NO | 81 | 83 | 2026-09-09 | P04904 | P049O4 | VivekO25 | 0
P049 | P049-T5 | Testing / validation | Ritu | Kavya | Medium | 2026-10-13 | 2026-10-23 | 23 | In Progress |  | NO | 89 | 81 | 2026-09-09 | P04905 | P049O5 | RituO24 | 0
P049 | P049-T6 | Customer acceptance | Sanjay | Rohan | Critical | 2026-10-27 | 2026-11-05 | 49 | In Progress | Awaiting clarification | NO | 27 | 39 | 2026-09-09 | P04906 | P049O6 | SanjayO25 | 0
P050 | P050-T1 | Requirements & scope freeze | Karan | Ritu | Low | 2026-08-19 | 2026-09-06 | 61 | In Progress |  | NO | 31 | 88 | 2026-09-09 | P05001 | P050O1 | KaranO26 | 0
P050 | P050-T2 | Design / solution | Meera | Sanjay | Critical | 2026-09-02 | 2026-09-22 | 36 | In Progress |  | NO | 91 | 90 | 2026-09-09 | P05002 | P050O2 | MeeraO26 | 0
P050 | P050-T3 | BOM / commercial approval | Vivek | Anil | Medium | 2026-09-16 | 2026-10-03 | 51 | In Progress |  | NO | 56 | 72 | 2026-09-09 | P05003 | P050O3 | VivekO26 | 0
P050 | P050-T4 | Build / execution | Ritu | Kavya | Low | 2026-09-30 | 2026-10-18 | 64 | In Progress | Awaiting clarification | NO | 44 | 100 | 2026-09-09 | P05004 | P050O4 | RituO25 | 0
P050 | P050-T5 | Testing / validation | Sanjay | Rohan | High | 2026-10-14 | 2026-11-01 | 60 | In Progress |  | NO | 27 | 95 | 2026-09-09 | P05005 | P050O5 | SanjayO26 | 0
P050 | P050-T6 | Customer acceptance | Anil | Deepa | High | 2026-10-28 | 2026-11-13 | 42 | In Progress | Awaiting clarification | NO | 44 | 76 | 2026-09-09 | P05006 | P050O6 | AnilO24 | 0
P051 | P051-T1 | Requirements & scope freeze | Meera | Sanjay | Critical | 2026-08-20 | 2026-09-11 | 10 | In Progress | Awaiting clarification | NO | 35 | 88 | 2026-09-09 | P05101 | P051O1 | MeeraO27 | 0
P051 | P051-T2 | Design / solution | Vivek | Anil | High | 2026-09-03 | 2026-09-16 | 17 | In Progress |  | NO | 63 | 99 | 2026-09-09 | P05102 | P051O2 | VivekO27 | 0
P051 | P051-T3 | BOM / commercial approval | Ritu | Kavya | Critical | 2026-09-17 | 2026-10-10 | 12 | In Progress |  | NO | 33 | 92 | 2026-09-09 | P05103 | P051O3 | RituO26 | 0
P051 | P051-T4 | Build / execution | Sanjay | Rohan | High | 2026-10-01 | 2026-10-13 | 42 | In Progress |  | NO | 98 | 104 | 2026-09-09 | P05104 | P051O4 | SanjayO27 | 0
P051 | P051-T5 | Testing / validation | Anil | Deepa | High | 2026-10-15 | 2026-10-25 | 23 | In Progress |  | NO | 35 | 24 | 2026-09-09 | P05105 | P051O5 | AnilO25 | 0
P051 | P051-T6 | Customer acceptance | Kavya | Amit | Low | 2026-10-29 | 2026-11-18 | 43 | In Progress |  | NO | 77 | 19 | 2026-09-09 | P05106 | P051O6 | KavyaO25 | 0
P052 | P052-T1 | Requirements & scope freeze | Vivek | Anil | Critical | 2026-08-21 | 2026-09-11 | 85 | In Progress |  | NO | 63 | 100 | 2026-09-09 | P05201 | P052O1 | VivekO28 | 0
P052 | P052-T2 | Design / solution | Ritu | Kavya | High | 2026-09-04 | 2026-09-13 | 99 | In Progress | Awaiting clarification | NO | 64 | 69 | 2026-09-09 | P05202 | P052O2 | RituO27 | 0
P052 | P052-T3 | BOM / commercial approval | Sanjay | Rohan | Critical | 2026-09-18 | 2026-10-03 | 81 | In Progress | Awaiting clarification | NO | 47 | 91 | 2026-09-09 | P05203 | P052O3 | SanjayO28 | 0
P052 | P052-T4 | Build / execution | Anil | Deepa | Medium | 2026-10-02 | 2026-10-12 | 97 | In Progress | Awaiting clarification | NO | 72 | 45 | 2026-09-09 | P05204 | P052O4 | AnilO26 | 0
P052 | P052-T5 | Testing / validation | Kavya | Amit | Medium | 2026-10-16 | 2026-10-26 | 100 | Completed | Awaiting clarification | NO | 96 | 75 | 2026-09-09 | P05205 |  |  | 0
P052 | P052-T6 | Customer acceptance | Rohan | Priya | Medium | 2026-10-30 | 2026-11-20 | 81 | In Progress | Awaiting clarification | NO | 23 | 42 | 2026-09-09 | P05206 | P052O5 | RohanO24 | 0
P053 | P053-T1 | Requirements & scope freeze | Ritu | Kavya | High | 2026-08-22 | 2026-09-05 | 74 | In Progress | Awaiting clarification | NO | 76 | 32 | 2026-09-09 | P05301 | P053O1 | RituO28 | 0
P053 | P053-T2 | Design / solution | Sanjay | Rohan | Critical | 2026-09-05 | 2026-09-25 | 54 | In Progress |  | NO | 22 | 82 | 2026-09-09 | P05302 | P053O2 | SanjayO29 | 0
P053 | P053-T3 | BOM / commercial approval | Anil | Deepa | High | 2026-09-19 | 2026-10-12 | 77 | In Progress |  | NO | 72 | 105 | 2026-09-09 | P05303 | P053O3 | AnilO27 | 0
P053 | P053-T4 | Build / execution | Kavya | Amit | High | 2026-10-03 | 2026-10-26 | 51 | In Progress |  | YES | 36 | 79 | 2026-09-09 | P05304 | P053O4 | KavyaO26 | 0
P053 | P053-T5 | Testing / validation | Rohan | Priya | Low | 2026-10-17 | 2026-10-28 | 75 | In Progress | Awaiting clarification | YES | 40 | 19 | 2026-09-09 | P05305 | P053O5 | RohanO25 | 0
P053 | P053-T6 | Customer acceptance | Deepa | Rahul | High | 2026-10-31 | 2026-11-21 | 52 | In Progress | Awaiting clarification | YES | 84 | 65 | 2026-09-09 | P05306 | P053O6 | DeepaO25 | 0
P054 | P054-T1 | Requirements & scope freeze | Sanjay | Rohan | Medium | 2026-08-23 | 2026-09-07 | 75 | In Progress |  | NO | 76 | 24 | 2026-09-09 | P05401 | P054O1 | SanjayO30 | 0
P054 | P054-T2 | Design / solution | Anil | Deepa | High | 2026-09-06 | 2026-09-20 | 86 | In Progress |  | NO | 64 | 36 | 2026-09-09 | P05402 | P054O2 | AnilO28 | 0
P054 | P054-T3 | BOM / commercial approval | Kavya | Amit | Medium | 2026-09-20 | 2026-10-14 | 96 | In Progress |  | NO | 44 | 56 | 2026-09-09 | P05403 | P054O3 | KavyaO27 | 0
P054 | P054-T4 | Build / execution | Rohan | Priya | High | 2026-10-04 | 2026-10-20 | 73 | In Progress |  | YES | 57 | 78 | 2026-09-09 | P05404 | P054O4 | RohanO26 | 0
P054 | P054-T5 | Testing / validation | Deepa | Rahul | High | 2026-10-18 | 2026-11-05 | 91 | In Progress |  | YES | 46 | 80 | 2026-09-09 | P05405 | P054O5 | DeepaO26 | 0
P054 | P054-T6 | Customer acceptance | Amit | Karan | High | 2026-11-01 | 2026-11-23 | 89 | In Progress |  | YES | 32 | 22 | 2026-09-09 | P05406 | P054O6 | AmitO25 | 0
P055 | P055-T1 | Requirements & scope freeze | Anil | Deepa | Low | 2026-08-24 | 2026-09-10 | 49 | In Progress |  | NO | 40 | 91 | 2026-09-09 | P05501 | P055O1 | AnilO29 | 0
P055 | P055-T2 | Design / solution | Kavya | Amit | High | 2026-09-07 | 2026-09-27 | 55 | In Progress |  | NO | 31 | 86 | 2026-09-09 | P05502 | P055O2 | KavyaO28 | 0
P055 | P055-T3 | BOM / commercial approval | Rohan | Priya | Critical | 2026-09-21 | 2026-10-11 | 40 | In Progress |  | NO | 29 | 29 | 2026-09-09 | P05503 | P055O3 | RohanO27 | 0
P055 | P055-T4 | Build / execution | Deepa | Rahul | High | 2026-10-05 | 2026-10-21 | 48 | In Progress |  | NO | 81 | 33 | 2026-09-09 | P05504 | P055O4 | DeepaO27 | 0
P055 | P055-T5 | Testing / validation | Amit | Karan | Low | 2026-10-19 | 2026-11-12 | 64 | In Progress | Awaiting clarification | NO | 49 | 88 | 2026-09-09 | P05505 | P055O5 | AmitO26 | 0
P055 | P055-T6 | Customer acceptance | Priya | Meera | Medium | 2026-11-02 | 2026-11-26 | 48 | In Progress |  | NO | 38 | 49 | 2026-09-09 | P05506 | P055O6 | PriyaO25 | 0
P056 | P056-T1 | Requirements & scope freeze | Kavya | Amit | Low | 2026-08-25 | 2026-09-03 | 45 | In Progress |  | NO | 48 | 37 | 2026-09-09 | P05601 | P056O1 | KavyaO29 | 0
P056 | P056-T2 | Design / solution | Rohan | Priya | Medium | 2026-09-08 | 2026-10-02 | 60 | In Progress |  | NO | 82 | 38 | 2026-09-09 | P05602 | P056O2 | RohanO28 | 0
P056 | P056-T3 | BOM / commercial approval | Deepa | Rahul | High | 2026-09-22 | 2026-10-03 | 61 | In Progress | Awaiting clarification | NO | 94 | 104 | 2026-09-09 | P05603 | P056O3 | DeepaO28 | 0
P056 | P056-T4 | Build / execution | Amit | Karan | Medium | 2026-10-06 | 2026-10-19 | 56 | In Progress |  | NO | 77 | 103 | 2026-09-09 | P05604 | P056O4 | AmitO27 | 0
P056 | P056-T5 | Testing / validation | Priya | Meera | Low | 2026-10-20 | 2026-11-04 | 41 | In Progress |  | NO | 55 | 103 | 2026-09-09 | P05605 | P056O5 | PriyaO26 | 0
P056 | P056-T6 | Customer acceptance | Rahul | Vivek | Medium | 2026-11-03 | 2026-11-26 | 73 | In Progress |  | NO | 78 | 56 | 2026-09-09 | P05606 | P056O6 | RahulO25 | 0
P057 | P057-T1 | Requirements & scope freeze | Rohan | Priya | Critical | 2026-08-26 | 2026-09-10 | 63 | In Progress |  | NO | 52 | 65 | 2026-09-09 | P05701 | P057O1 | RohanO29 | 0
P057 | P057-T2 | Design / solution | Deepa | Rahul | Critical | 2026-09-09 | 2026-09-22 | 62 | In Progress |  | NO | 79 | 48 | 2026-09-09 | P05702 | P057O2 | DeepaO29 | 0
P057 | P057-T3 | BOM / commercial approval | Amit | Karan | Medium | 2026-09-23 | 2026-10-11 | 60 | In Progress |  | NO | 53 | 54 | 2026-09-09 | P05703 | P057O3 | AmitO28 | 0
P057 | P057-T4 | Build / execution | Priya | Meera | Medium | 2026-10-07 | 2026-10-25 | 60 | In Progress |  | NO | 41 | 29 | 2026-09-09 | P05704 | P057O4 | PriyaO27 | 0
P057 | P057-T5 | Testing / validation | Rahul | Vivek | Low | 2026-10-21 | 2026-11-14 | 55 | In Progress | Awaiting clarification | NO | 68 | 58 | 2026-09-09 | P05705 | P057O5 | RahulO26 | 0
P057 | P057-T6 | Customer acceptance | Karan | Ritu | Critical | 2026-11-04 | 2026-11-17 | 49 | In Progress | Awaiting clarification | NO | 84 | 48 | 2026-09-09 | P05706 | P057O6 | KaranO27 | 0
P058 | P058-T1 | Requirements & scope freeze | Deepa | Rahul | High | 2026-08-27 | 2026-09-06 | 77 | In Progress |  | NO | 22 | 45 | 2026-09-09 | P05801 | P058O1 | DeepaO30 | 0
P058 | P058-T2 | Design / solution | Amit | Karan | High | 2026-09-10 | 2026-09-22 | 66 | In Progress | Awaiting clarification | NO | 57 | 53 | 2026-09-09 | P05802 | P058O2 | AmitO29 | 0
P058 | P058-T3 | BOM / commercial approval | Priya | Meera | High | 2026-09-24 | 2026-10-04 | 62 | In Progress |  | NO | 49 | 27 | 2026-09-09 | P05803 | P058O3 | PriyaO28 | 0
P058 | P058-T4 | Build / execution | Rahul | Vivek | Critical | 2026-10-08 | 2026-10-18 | 63 | In Progress | Awaiting clarification | NO | 80 | 27 | 2026-09-09 | P05804 | P058O4 | RahulO27 | 0
P058 | P058-T5 | Testing / validation | Karan | Ritu | Critical | 2026-10-22 | 2026-11-10 | 42 | In Progress |  | NO | 21 | 102 | 2026-09-09 | P05805 | P058O5 | KaranO28 | 0
P058 | P058-T6 | Customer acceptance | Meera | Sanjay | Critical | 2026-11-05 | 2026-11-20 | 49 | In Progress | Awaiting clarification | NO | 22 | 78 | 2026-09-09 | P05806 | P058O6 | MeeraO28 | 0
P059 | P059-T1 | Requirements & scope freeze | Amit | Karan | Critical | 2026-08-28 | 2026-09-13 | 56 | In Progress |  | NO | 48 | 100 | 2026-09-09 | P05901 | P059O1 | AmitO30 | 0
P059 | P059-T2 | Design / solution | Priya | Meera | High | 2026-09-11 | 2026-09-29 | 27 | In Progress |  | NO | 43 | 35 | 2026-09-09 | P05902 | P059O2 | PriyaO29 | 0
P059 | P059-T3 | BOM / commercial approval | Rahul | Vivek | Critical | 2026-09-25 | 2026-10-08 | 54 | In Progress |  | NO | 28 | 96 | 2026-09-09 | P05903 | P059O3 | RahulO28 | 0
P059 | P059-T4 | Build / execution | Karan | Ritu | Low | 2026-10-09 | 2026-11-01 | 41 | Blocked | Supplier / cross-functional dependency | YES | 30 | 69 | 2026-09-09 | P05904 | P059O4 | KaranO29 | 0
P059 | P059-T5 | Testing / validation | Meera | Sanjay | Medium | 2026-10-23 | 2026-11-03 | 35 | Blocked | Supplier / cross-functional dependency | YES | 58 | 89 | 2026-09-09 | P05905 | P059O5 | MeeraO29 | 0
P059 | P059-T6 | Customer acceptance | Vivek | Anil | Critical | 2026-11-06 | 2026-11-21 | 44 | Blocked | Supplier / cross-functional dependency | YES | 26 | 16 | 2026-09-09 | P05906 | P059O6 | VivekO29 | 0
P060 | P060-T1 | Requirements & scope freeze | Priya | Meera | High | 2026-08-29 | 2026-09-21 | 15 | In Progress |  | NO | 48 | 41 | 2026-09-09 | P06001 | P060O1 | PriyaO30 | 0
P060 | P060-T2 | Design / solution | Rahul | Vivek | Low | 2026-09-12 | 2026-09-23 | 38 | In Progress | Awaiting clarification | NO | 36 | 17 | 2026-09-09 | P06002 | P060O2 | RahulO29 | 0
P060 | P060-T3 | BOM / commercial approval | Karan | Ritu | High | 2026-09-26 | 2026-10-07 | 15 | In Progress |  | NO | 91 | 95 | 2026-09-09 | P06003 | P060O3 | KaranO30 | 0
P060 | P060-T4 | Build / execution | Meera | Sanjay | Critical | 2026-10-10 | 2026-10-30 | 16 | In Progress |  | NO | 31 | 104 | 2026-09-09 | P06004 | P060O4 | MeeraO30 | 0
P060 | P060-T5 | Testing / validation | Vivek | Anil | Medium | 2026-10-24 | 2026-11-12 | 15 | In Progress |  | NO | 76 | 43 | 2026-09-09 | P06005 | P060O5 | VivekO30 | 0
P060 | P060-T6 | Customer acceptance | Ritu | Kavya | Low | 2026-11-07 | 2026-11-20 | 27 | In Progress |  | NO | 58 | 100 | 2026-09-09 | P06006 | P060O6 | RituO29 | 0
P061 | P061-T1 | Requirements & scope freeze | Rahul | Vivek | Medium | 2026-08-30 | 2026-09-12 | 28 | In Progress |  | NO | 22 | 28 | 2026-09-09 | P06101 | P061O1 | RahulO30 | 0
P061 | P061-T2 | Design / solution | Karan | Ritu | Medium | 2026-09-13 | 2026-10-04 | 42 | In Progress |  | NO | 36 | 77 | 2026-09-09 | P06102 | P061O2 | KaranO31 | 0
P061 | P061-T3 | BOM / commercial approval | Meera | Sanjay | Medium | 2026-09-27 | 2026-10-07 | 24 | In Progress |  | NO | 27 | 20 | 2026-09-09 | P06103 | P061O3 | MeeraO31 | 0
P061 | P061-T4 | Build / execution | Vivek | Anil | Medium | 2026-10-11 | 2026-10-30 | 21 | In Progress |  | NO | 91 | 94 | 2026-09-09 | P06104 | P061O4 | VivekO31 | 0
P061 | P061-T5 | Testing / validation | Ritu | Kavya | Critical | 2026-10-25 | 2026-11-08 | 30 | In Progress | Awaiting clarification | NO | 60 | 25 | 2026-09-09 | P06105 | P061O5 | RituO30 | 0
P061 | P061-T6 | Customer acceptance | Sanjay | Rohan | Low | 2026-11-08 | 2026-11-19 | 23 | In Progress |  | NO | 53 | 26 | 2026-09-09 | P06106 | P061O6 | SanjayO31 | 0
P062 | P062-T1 | Requirements & scope freeze | Karan | Ritu | Critical | 2026-08-31 | 2026-09-21 | 57 | In Progress |  | NO | 96 | 23 | 2026-09-09 | P06201 | P062O1 | KaranO32 | 0
P062 | P062-T2 | Design / solution | Meera | Sanjay | High | 2026-09-14 | 2026-09-29 | 26 | In Progress |  | NO | 66 | 93 | 2026-09-09 | P06202 | P062O2 | MeeraO32 | 0
P062 | P062-T3 | BOM / commercial approval | Vivek | Anil | Low | 2026-09-28 | 2026-10-11 | 52 | In Progress | Awaiting clarification | NO | 59 | 41 | 2026-09-09 | P06203 | P062O3 | VivekO32 | 0
P062 | P062-T4 | Build / execution | Ritu | Kavya | High | 2026-10-12 | 2026-10-26 | 38 | In Progress |  | NO | 32 | 88 | 2026-09-09 | P06204 | P062O4 | RituO31 | 0
P062 | P062-T5 | Testing / validation | Sanjay | Rohan | Medium | 2026-10-26 | 2026-11-07 | 30 | In Progress | Awaiting clarification | NO | 90 | 100 | 2026-09-09 | P06205 | P062O5 | SanjayO32 | 0
P062 | P062-T6 | Customer acceptance | Anil | Deepa | Critical | 2026-11-09 | 2026-11-25 | 39 | In Progress |  | NO | 56 | 30 | 2026-09-09 | P06206 | P062O6 | AnilO30 | 0
P063 | P063-T1 | Requirements & scope freeze | Meera | Sanjay | Low | 2026-09-01 | 2026-09-21 | 48 | In Progress |  | NO | 32 | 57 | 2026-09-09 | P06301 | P063O1 | MeeraO33 | 0
P063 | P063-T2 | Design / solution | Vivek | Anil | High | 2026-09-15 | 2026-09-29 | 53 | In Progress |  | NO | 78 | 52 | 2026-09-09 | P06302 | P063O2 | VivekO33 | 0
P063 | P063-T3 | BOM / commercial approval | Ritu | Kavya | Low | 2026-09-29 | 2026-10-20 | 55 | In Progress |  | NO | 73 | 21 | 2026-09-09 | P06303 | P063O3 | RituO32 | 0
P063 | P063-T4 | Build / execution | Sanjay | Rohan | Low | 2026-10-13 | 2026-10-23 | 44 | In Progress |  | NO | 49 | 32 | 2026-09-09 | P06304 | P063O4 | SanjayO33 | 0
P063 | P063-T5 | Testing / validation | Anil | Deepa | Low | 2026-10-27 | 2026-11-10 | 46 | In Progress |  | NO | 83 | 46 | 2026-09-09 | P06305 | P063O5 | AnilO31 | 0
P063 | P063-T6 | Customer acceptance | Kavya | Amit | Medium | 2026-11-10 | 2026-11-26 | 52 | In Progress |  | NO | 56 | 68 | 2026-09-09 | P06306 | P063O6 | KavyaO30 | 0
P064 | P064-T1 | Requirements & scope freeze | Vivek | Anil | High | 2026-09-02 | 2026-09-12 | 55 | In Progress | Awaiting clarification | NO | 26 | 28 | 2026-09-09 | P06401 | P064O1 | VivekO34 | 0
P064 | P064-T2 | Design / solution | Ritu | Kavya | Critical | 2026-09-16 | 2026-09-30 | 58 | In Progress |  | NO | 62 | 21 | 2026-09-09 | P06402 | P064O2 | RituO33 | 0
P064 | P064-T3 | BOM / commercial approval | Sanjay | Rohan | Low | 2026-09-30 | 2026-10-10 | 20 | In Progress | Awaiting clarification | NO | 37 | 88 | 2026-09-09 | P06403 | P064O3 | SanjayO34 | 0
P064 | P064-T4 | Build / execution | Anil | Deepa | Low | 2026-10-14 | 2026-11-04 | 24 | In Progress |  | NO | 28 | 60 | 2026-09-09 | P06404 | P064O4 | AnilO32 | 0
P064 | P064-T5 | Testing / validation | Kavya | Amit | Medium | 2026-10-28 | 2026-11-10 | 55 | In Progress |  | NO | 57 | 35 | 2026-09-09 | P06405 | P064O5 | KavyaO31 | 0
P064 | P064-T6 | Customer acceptance | Rohan | Priya | High | 2026-11-11 | 2026-12-05 | 51 | In Progress | Awaiting clarification | NO | 86 | 43 | 2026-09-09 | P06406 | P064O6 | RohanO30 | 0
P065 | P065-T1 | Requirements & scope freeze | Ritu | Kavya | Critical | 2026-09-03 | 2026-09-20 | 40 | In Progress |  | NO | 27 | 88 | 2026-09-09 | P06501 | P065O1 | RituO34 | 0
P065 | P065-T2 | Design / solution | Sanjay | Rohan | High | 2026-09-17 | 2026-09-26 | 26 | In Progress |  | NO | 64 | 80 | 2026-09-09 | P06502 | P065O2 | SanjayO35 | 0
P065 | P065-T3 | BOM / commercial approval | Anil | Deepa | Low | 2026-10-01 | 2026-10-20 | 23 | In Progress | Awaiting clarification | NO | 60 | 20 | 2026-09-09 | P06503 | P065O3 | AnilO33 | 0
P065 | P065-T4 | Build / execution | Kavya | Amit | Critical | 2026-10-15 | 2026-10-30 | 36 | In Progress |  | NO | 48 | 58 | 2026-09-09 | P06504 | P065O4 | KavyaO32 | 0
P065 | P065-T5 | Testing / validation | Rohan | Priya | Low | 2026-10-29 | 2026-11-19 | 38 | In Progress |  | NO | 68 | 40 | 2026-09-09 | P06505 | P065O5 | RohanO31 | 0
P065 | P065-T6 | Customer acceptance | Deepa | Rahul | Medium | 2026-11-12 | 2026-11-25 | 58 | In Progress |  | NO | 58 | 81 | 2026-09-09 | P06506 | P065O6 | DeepaO31 | 0
P066 | P066-T1 | Requirements & scope freeze | Sanjay | Rohan | Low | 2026-09-04 | 2026-09-15 | 37 | In Progress | Awaiting clarification | NO | 98 | 88 | 2026-09-09 | P06601 | P066O1 | SanjayO36 | 0
P066 | P066-T2 | Design / solution | Anil | Deepa | Medium | 2026-09-18 | 2026-09-29 | 31 | In Progress |  | NO | 86 | 20 | 2026-09-09 | P06602 | P066O2 | AnilO34 | 0
P066 | P066-T3 | BOM / commercial approval | Kavya | Amit | Low | 2026-10-02 | 2026-10-20 | 65 | In Progress | Awaiting clarification | NO | 48 | 83 | 2026-09-09 | P06603 | P066O3 | KavyaO33 | 0
P066 | P066-T4 | Build / execution | Rohan | Priya | Medium | 2026-10-16 | 2026-11-04 | 58 | In Progress | Awaiting clarification | NO | 96 | 30 | 2026-09-09 | P06604 | P066O4 | RohanO32 | 0
P066 | P066-T5 | Testing / validation | Deepa | Rahul | Medium | 2026-10-30 | 2026-11-14 | 48 | In Progress |  | NO | 26 | 15 | 2026-09-09 | P06605 | P066O5 | DeepaO32 | 0
P066 | P066-T6 | Customer acceptance | Amit | Karan | High | 2026-11-13 | 2026-11-22 | 65 | In Progress |  | NO | 57 | 23 | 2026-09-09 | P06606 | P066O6 | AmitO31 | 0
P067 | P067-T1 | Requirements & scope freeze | Anil | Deepa | High | 2026-09-05 | 2026-09-25 | 100 | Completed |  | NO | 42 | 91 | 2026-09-09 | P06701 |  |  | 0
P067 | P067-T2 | Design / solution | Kavya | Amit | Critical | 2026-09-19 | 2026-10-07 | 81 | In Progress | Awaiting clarification | NO | 84 | 104 | 2026-09-09 | P06702 | P067O1 | KavyaO34 | 0
P067 | P067-T3 | BOM / commercial approval | Rohan | Priya | Medium | 2026-10-03 | 2026-10-19 | 79 | In Progress |  | NO | 48 | 86 | 2026-09-09 | P06703 | P067O2 | RohanO33 | 0
P067 | P067-T4 | Build / execution | Deepa | Rahul | Critical | 2026-10-17 | 2026-10-30 | 87 | In Progress | Awaiting clarification | NO | 45 | 57 | 2026-09-09 | P06704 | P067O3 | DeepaO33 | 0
P067 | P067-T5 | Testing / validation | Amit | Karan | Critical | 2026-10-31 | 2026-11-12 | 100 | Completed | Awaiting clarification | NO | 45 | 91 | 2026-09-09 | P06705 |  |  | 0
P067 | P067-T6 | Customer acceptance | Priya | Meera | Low | 2026-11-14 | 2026-12-01 | 100 | Completed |  | NO | 55 | 50 | 2026-09-09 | P06706 |  |  | 0
P068 | P068-T1 | Requirements & scope freeze | Kavya | Amit | Low | 2026-09-06 | 2026-09-25 | 66 | In Progress | Awaiting clarification | NO | 62 | 35 | 2026-09-09 | P06801 | P068O1 | KavyaO35 | 0
P068 | P068-T2 | Design / solution | Rohan | Priya | Medium | 2026-09-20 | 2026-10-14 | 83 | In Progress | Awaiting clarification | NO | 20 | 38 | 2026-09-09 | P06802 | P068O2 | RohanO34 | 0
P068 | P068-T3 | BOM / commercial approval | Deepa | Rahul | Medium | 2026-10-04 | 2026-10-13 | 89 | In Progress | Awaiting clarification | NO | 64 | 93 | 2026-09-09 | P06803 | P068O3 | DeepaO34 | 0
P068 | P068-T4 | Build / execution | Amit | Karan | Critical | 2026-10-18 | 2026-11-01 | 100 | Completed |  | NO | 88 | 51 | 2026-09-09 | P06804 |  |  | 0
P068 | P068-T5 | Testing / validation | Priya | Meera | High | 2026-11-01 | 2026-11-17 | 84 | In Progress | Awaiting clarification | NO | 77 | 19 | 2026-09-09 | P06805 | P068O4 | PriyaO31 | 0
P068 | P068-T6 | Customer acceptance | Rahul | Vivek | Medium | 2026-11-15 | 2026-11-29 | 100 | Completed | Awaiting clarification | NO | 49 | 80 | 2026-09-09 | P06806 |  |  | 0
P069 | P069-T1 | Requirements & scope freeze | Rohan | Priya | Medium | 2026-09-07 | 2026-09-19 | 77 | In Progress |  | NO | 26 | 29 | 2026-09-09 | P06901 | P069O1 | RohanO35 | 0
P069 | P069-T2 | Design / solution | Deepa | Rahul | Critical | 2026-09-21 | 2026-10-06 | 65 | In Progress |  | NO | 55 | 45 | 2026-09-09 | P06902 | P069O2 | DeepaO35 | 0
P069 | P069-T3 | BOM / commercial approval | Amit | Karan | Medium | 2026-10-05 | 2026-10-25 | 76 | In Progress |  | NO | 50 | 99 | 2026-09-09 | P06903 | P069O3 | AmitO32 | 0
P069 | P069-T4 | Build / execution | Priya | Meera | Low | 2026-10-19 | 2026-11-02 | 70 | In Progress |  | NO | 93 | 88 | 2026-09-09 | P06904 | P069O4 | PriyaO32 | 0
P069 | P069-T5 | Testing / validation | Rahul | Vivek | Critical | 2026-11-02 | 2026-11-24 | 100 | Completed |  | NO | 33 | 46 | 2026-09-09 | P06905 |  |  | 0
P069 | P069-T6 | Customer acceptance | Karan | Ritu | High | 2026-11-16 | 2026-12-06 | 93 | In Progress |  | NO | 79 | 89 | 2026-09-09 | P06906 | P069O5 | KaranO33 | 0
P070 | P070-T1 | Requirements & scope freeze | Deepa | Rahul | Low | 2026-09-08 | 2026-09-20 | 26 | In Progress |  | NO | 71 | 34 | 2026-09-09 | P07001 | P070O1 | DeepaO36 | 0
P070 | P070-T2 | Design / solution | Amit | Karan | Low | 2026-09-22 | 2026-10-01 | 52 | In Progress |  | NO | 33 | 42 | 2026-09-09 | P07002 | P070O2 | AmitO33 | 0
P070 | P070-T3 | BOM / commercial approval | Priya | Meera | Low | 2026-10-06 | 2026-10-16 | 21 | In Progress |  | NO | 53 | 92 | 2026-09-09 | P07003 | P070O3 | PriyaO33 | 0
P070 | P070-T4 | Build / execution | Rahul | Vivek | High | 2026-10-20 | 2026-11-12 | 43 | In Progress |  | NO | 73 | 102 | 2026-09-09 | P07004 | P070O4 | RahulO31 | 0
P070 | P070-T5 | Testing / validation | Karan | Ritu | Medium | 2026-11-03 | 2026-11-25 | 34 | In Progress |  | NO | 94 | 32 | 2026-09-09 | P07005 | P070O5 | KaranO34 | 0
P070 | P070-T6 | Customer acceptance | Meera | Sanjay | High | 2026-11-17 | 2026-11-30 | 35 | In Progress |  | NO | 81 | 85 | 2026-09-09 | P07006 | P070O6 | MeeraO34 | 0
P071 | P071-T1 | Requirements & scope freeze | Amit | Karan | Medium | 2026-09-09 | 2026-09-25 | 76 | In Progress | Awaiting clarification | NO | 44 | 58 | 2026-09-09 | P07101 | P071O1 | AmitO34 | 0
P071 | P071-T2 | Design / solution | Priya | Meera | High | 2026-09-23 | 2026-10-16 | 100 | Completed |  | NO | 56 | 105 | 2026-09-09 | P07102 |  |  | 0
P071 | P071-T3 | BOM / commercial approval | Rahul | Vivek | Critical | 2026-10-07 | 2026-10-28 | 82 | In Progress |  | NO | 24 | 29 | 2026-09-09 | P07103 | P071O2 | RahulO32 | 0
P071 | P071-T4 | Build / execution | Karan | Ritu | Critical | 2026-10-21 | 2026-11-12 | 95 | In Progress |  | NO | 55 | 73 | 2026-09-09 | P07104 | P071O3 | KaranO35 | 0
P071 | P071-T5 | Testing / validation | Meera | Sanjay | Medium | 2026-11-04 | 2026-11-27 | 82 | In Progress | Awaiting clarification | NO | 93 | 28 | 2026-09-09 | P07105 | P071O4 | MeeraO35 | 0
P071 | P071-T6 | Customer acceptance | Vivek | Anil | Medium | 2026-11-18 | 2026-11-29 | 93 | In Progress |  | NO | 32 | 93 | 2026-09-09 | P07106 | P071O5 | VivekO35 | 0
P072 | P072-T1 | Requirements & scope freeze | Priya | Meera | High | 2026-09-10 | 2026-09-30 | 32 | In Progress |  | NO | 99 | 85 | 2026-09-09 | P07201 | P072O1 | PriyaO34 | 0
P072 | P072-T2 | Design / solution | Rahul | Vivek | High | 2026-09-24 | 2026-10-07 | 35 | In Progress | Awaiting clarification | NO | 57 | 20 | 2026-09-09 | P07202 | P072O2 | RahulO33 | 0
P072 | P072-T3 | BOM / commercial approval | Karan | Ritu | High | 2026-10-08 | 2026-10-31 | 28 | In Progress |  | NO | 43 | 83 | 2026-09-09 | P07203 | P072O3 | KaranO36 | 0
P072 | P072-T4 | Build / execution | Meera | Sanjay | Medium | 2026-10-22 | 2026-11-11 | 23 | Blocked | Supplier / cross-functional dependency | YES | 36 | 20 | 2026-09-09 | P07204 | P072O4 | MeeraO36 | 0
P072 | P072-T5 | Testing / validation | Vivek | Anil | Medium | 2026-11-05 | 2026-11-17 | 18 | Blocked | Supplier / cross-functional dependency | YES | 44 | 36 | 2026-09-09 | P07205 | P072O5 | VivekO36 | 0
P072 | P072-T6 | Customer acceptance | Ritu | Kavya | Low | 2026-11-19 | 2026-12-09 | 43 | Blocked | Supplier / cross-functional dependency | YES | 33 | 59 | 2026-09-09 | P07206 | P072O6 | RituO35 | 0
P073 | P073-T1 | Requirements & scope freeze | Rahul | Vivek | High | 2026-09-11 | 2026-10-04 | 87 | In Progress | Awaiting clarification | NO | 56 | 91 | 2026-09-09 | P07301 | P073O1 | RahulO34 | 0
P073 | P073-T2 | Design / solution | Karan | Ritu | Low | 2026-09-25 | 2026-10-11 | 84 | In Progress |  | NO | 51 | 41 | 2026-09-09 | P07302 | P073O2 | KaranO37 | 0
P073 | P073-T3 | BOM / commercial approval | Meera | Sanjay | Critical | 2026-10-09 | 2026-10-23 | 82 | In Progress |  | NO | 62 | 90 | 2026-09-09 | P07303 | P073O3 | MeeraO37 | 0
P073 | P073-T4 | Build / execution | Vivek | Anil | Critical | 2026-10-23 | 2026-11-08 | 81 | In Progress | Awaiting clarification | NO | 82 | 85 | 2026-09-09 | P07304 | P073O4 | VivekO37 | 0
P073 | P073-T5 | Testing / validation | Ritu | Kavya | Medium | 2026-11-06 | 2026-11-19 | 94 | In Progress |  | NO | 66 | 29 | 2026-09-09 | P07305 | P073O5 | RituO36 | 0
P073 | P073-T6 | Customer acceptance | Sanjay | Rohan | High | 2026-11-20 | 2026-12-04 | 100 | Completed | Awaiting clarification | NO | 38 | 83 | 2026-09-09 | P07306 |  |  | 0
P074 | P074-T1 | Requirements & scope freeze | Karan | Ritu | Medium | 2026-09-12 | 2026-09-27 | 64 | In Progress |  | NO | 32 | 48 | 2026-09-09 | P07401 | P074O1 | KaranO38 | 0
P074 | P074-T2 | Design / solution | Meera | Sanjay | Low | 2026-09-26 | 2026-10-18 | 52 | In Progress |  | NO | 83 | 32 | 2026-09-09 | P07402 | P074O2 | MeeraO38 | 0
P074 | P074-T3 | BOM / commercial approval | Vivek | Anil | High | 2026-10-10 | 2026-10-24 | 64 | In Progress |  | NO | 91 | 65 | 2026-09-09 | P07403 | P074O3 | VivekO38 | 0
P074 | P074-T4 | Build / execution | Ritu | Kavya | High | 2026-10-24 | 2026-11-08 | 59 | In Progress |  | NO | 83 | 57 | 2026-09-09 | P07404 | P074O4 | RituO37 | 0
P074 | P074-T5 | Testing / validation | Sanjay | Rohan | Low | 2026-11-07 | 2026-12-01 | 69 | In Progress |  | NO | 70 | 100 | 2026-09-09 | P07405 | P074O5 | SanjayO37 | 0
P074 | P074-T6 | Customer acceptance | Anil | Deepa | Critical | 2026-11-21 | 2026-12-09 | 73 | In Progress |  | NO | 52 | 32 | 2026-09-09 | P07406 | P074O6 | AnilO35 | 0
P075 | P075-T1 | Requirements & scope freeze | Meera | Sanjay | Medium | 2026-09-13 | 2026-09-27 | 24 | In Progress |  | NO | 76 | 81 | 2026-09-09 | P07501 | P075O1 | MeeraO39 | 0
P075 | P075-T2 | Design / solution | Vivek | Anil | Critical | 2026-09-27 | 2026-10-20 | 49 | In Progress |  | NO | 93 | 46 | 2026-09-09 | P07502 | P075O2 | VivekO39 | 0
P075 | P075-T3 | BOM / commercial approval | Ritu | Kavya | Low | 2026-10-11 | 2026-10-22 | 50 | In Progress | Awaiting clarification | NO | 67 | 101 | 2026-09-09 | P07503 | P075O3 | RituO38 | 0
P075 | P075-T4 | Build / execution | Sanjay | Rohan | Medium | 2026-10-25 | 2026-11-08 | 44 | Blocked | Supplier / cross-functional dependency | YES | 46 | 54 | 2026-09-09 | P07504 | P075O4 | SanjayO38 | 0
P075 | P075-T5 | Testing / validation | Anil | Deepa | Low | 2026-11-08 | 2026-11-30 | 24 | Blocked | Supplier / cross-functional dependency | YES | 48 | 104 | 2026-09-09 | P07505 | P075O5 | AnilO36 | 0
P075 | P075-T6 | Customer acceptance | Kavya | Amit | Medium | 2026-11-22 | 2026-12-09 | 46 | Blocked | Supplier / cross-functional dependency | YES | 51 | 32 | 2026-09-09 | P07506 | P075O6 | KavyaO36 | 0
P076 | P076-T1 | Requirements & scope freeze | Vivek | Anil | Low | 2026-09-14 | 2026-10-06 | 69 | In Progress |  | NO | 90 | 96 | 2026-09-09 | P07601 | P076O1 | VivekO40 | 0
P076 | P076-T2 | Design / solution | Ritu | Kavya | Low | 2026-09-28 | 2026-10-10 | 100 | Completed |  | NO | 99 | 50 | 2026-09-09 | P07602 |  |  | 0
P076 | P076-T3 | BOM / commercial approval | Sanjay | Rohan | Medium | 2026-10-12 | 2026-10-22 | 78 | In Progress |  | NO | 30 | 76 | 2026-09-09 | P07603 | P076O2 | SanjayO39 | 0
P076 | P076-T4 | Build / execution | Anil | Deepa | Low | 2026-10-26 | 2026-11-14 | 85 | In Progress | Awaiting clarification | NO | 75 | 74 | 2026-09-09 | P07604 | P076O3 | AnilO37 | 0
P076 | P076-T5 | Testing / validation | Kavya | Amit | Low | 2026-11-09 | 2026-11-29 | 100 | Completed |  | NO | 63 | 100 | 2026-09-09 | P07605 |  |  | 0
P076 | P076-T6 | Customer acceptance | Rohan | Priya | Critical | 2026-11-23 | 2026-12-05 | 96 | In Progress |  | NO | 29 | 34 | 2026-09-09 | P07606 | P076O4 | RohanO36 | 0
P077 | P077-T1 | Requirements & scope freeze | Ritu | Kavya | Critical | 2026-09-15 | 2026-09-26 | 65 | In Progress |  | NO | 89 | 24 | 2026-09-09 | P07701 | P077O1 | RituO39 | 0
P077 | P077-T2 | Design / solution | Sanjay | Rohan | Low | 2026-09-29 | 2026-10-13 | 83 | In Progress |  | NO | 72 | 50 | 2026-09-09 | P07702 | P077O2 | SanjayO40 | 0
P077 | P077-T3 | BOM / commercial approval | Anil | Deepa | Critical | 2026-10-13 | 2026-10-26 | 65 | In Progress |  | NO | 92 | 31 | 2026-09-09 | P07703 | P077O3 | AnilO38 | 0
P077 | P077-T4 | Build / execution | Kavya | Amit | High | 2026-10-27 | 2026-11-19 | 79 | In Progress |  | NO | 47 | 102 | 2026-09-09 | P07704 | P077O4 | KavyaO37 | 0
P077 | P077-T5 | Testing / validation | Rohan | Priya | High | 2026-11-10 | 2026-11-27 | 75 | In Progress |  | NO | 90 | 80 | 2026-09-09 | P07705 | P077O5 | RohanO37 | 0
P077 | P077-T6 | Customer acceptance | Deepa | Rahul | Low | 2026-11-24 | 2026-12-07 | 88 | In Progress |  | NO | 96 | 31 | 2026-09-09 | P07706 | P077O6 | DeepaO37 | 0
P078 | P078-T1 | Requirements & scope freeze | Sanjay | Rohan | Low | 2026-09-16 | 2026-10-03 | 72 | In Progress |  | NO | 81 | 48 | 2026-09-09 | P07801 | P078O1 | SanjayO41 | 0
P078 | P078-T2 | Design / solution | Anil | Deepa | Medium | 2026-09-30 | 2026-10-23 | 83 | In Progress | Awaiting clarification | NO | 53 | 36 | 2026-09-09 | P07802 | P078O2 | AnilO39 | 0
P078 | P078-T3 | BOM / commercial approval | Kavya | Amit | Low | 2026-10-14 | 2026-10-26 | 86 | In Progress |  | NO | 22 | 92 | 2026-09-09 | P07803 | P078O3 | KavyaO38 | 0
P078 | P078-T4 | Build / execution | Rohan | Priya | Critical | 2026-10-28 | 2026-11-08 | 75 | In Progress |  | NO | 24 | 46 | 2026-09-09 | P07804 | P078O4 | RohanO38 | 0
P078 | P078-T5 | Testing / validation | Deepa | Rahul | Medium | 2026-11-11 | 2026-12-01 | 75 | In Progress |  | NO | 94 | 74 | 2026-09-09 | P07805 | P078O5 | DeepaO38 | 0
P078 | P078-T6 | Customer acceptance | Amit | Karan | Low | 2026-11-25 | 2026-12-10 | 64 | In Progress | Awaiting clarification | NO | 99 | 34 | 2026-09-09 | P07806 | P078O6 | AmitO35 | 0
P079 | P079-T1 | Requirements & scope freeze | Anil | Deepa | Medium | 2026-09-17 | 2026-10-04 | 18 | In Progress |  | NO | 70 | 63 | 2026-09-09 | P07901 | P079O1 | AnilO40 | 0
P079 | P079-T2 | Design / solution | Kavya | Amit | Low | 2026-10-01 | 2026-10-17 | 26 | In Progress |  | NO | 73 | 71 | 2026-09-09 | P07902 | P079O2 | KavyaO39 | 0
P079 | P079-T3 | BOM / commercial approval | Rohan | Priya | Medium | 2026-10-15 | 2026-11-01 | 26 | In Progress |  | NO | 23 | 93 | 2026-09-09 | P07903 | P079O3 | RohanO39 | 0
P079 | P079-T4 | Build / execution | Deepa | Rahul | Low | 2026-10-29 | 2026-11-08 | 7 | Blocked | Supplier / cross-functional dependency | YES | 46 | 24 | 2026-09-09 | P07904 | P079O4 | DeepaO39 | 0
P079 | P079-T5 | Testing / validation | Amit | Karan | Medium | 2026-11-12 | 2026-11-25 | 35 | Blocked | Supplier / cross-functional dependency | YES | 76 | 25 | 2026-09-09 | P07905 | P079O5 | AmitO36 | 0
P079 | P079-T6 | Customer acceptance | Priya | Meera | Low | 2026-11-26 | 2026-12-09 | 27 | Blocked | Supplier / cross-functional dependency | YES | 63 | 94 | 2026-09-09 | P07906 | P079O6 | PriyaO35 | 0
P080 | P080-T1 | Requirements & scope freeze | Kavya | Amit | Critical | 2026-09-18 | 2026-10-06 | 91 | In Progress |  | NO | 100 | 61 | 2026-09-09 | P08001 | P080O1 | KavyaO40 | 0
P080 | P080-T2 | Design / solution | Rohan | Priya | Critical | 2026-10-02 | 2026-10-17 | 82 | In Progress |  | NO | 71 | 17 | 2026-09-09 | P08002 | P080O2 | RohanO40 | 0
P080 | P080-T3 | BOM / commercial approval | Deepa | Rahul | Medium | 2026-10-16 | 2026-11-03 | 88 | In Progress |  | NO | 92 | 61 | 2026-09-09 | P08003 | P080O3 | DeepaO40 | 0
P080 | P080-T4 | Build / execution | Amit | Karan | Critical | 2026-10-30 | 2026-11-16 | 58 | In Progress |  | NO | 98 | 62 | 2026-09-09 | P08004 | P080O4 | AmitO37 | 0
P080 | P080-T5 | Testing / validation | Priya | Meera | Medium | 2026-11-13 | 2026-12-02 | 80 | In Progress |  | NO | 55 | 68 | 2026-09-09 | P08005 | P080O5 | PriyaO36 | 0
P080 | P080-T6 | Customer acceptance | Rahul | Vivek | Critical | 2026-11-27 | 2026-12-21 | 88 | In Progress |  | NO | 71 | 69 | 2026-09-09 | P08006 | P080O6 | RahulO35 | 0
P081 | P081-T1 | Requirements & scope freeze | Rohan | Priya | Low | 2026-09-19 | 2026-10-11 | 22 | In Progress |  | NO | 66 | 39 | 2026-09-09 | P08101 | P081O1 | RohanO41 | 0
P081 | P081-T2 | Design / solution | Deepa | Rahul | Medium | 2026-10-03 | 2026-10-18 | 49 | In Progress |  | NO | 82 | 67 | 2026-09-09 | P08102 | P081O2 | DeepaO41 | 0
P081 | P081-T3 | BOM / commercial approval | Amit | Karan | Low | 2026-10-17 | 2026-11-01 | 57 | In Progress |  | NO | 43 | 67 | 2026-09-09 | P08103 | P081O3 | AmitO38 | 0
P081 | P081-T4 | Build / execution | Priya | Meera | Medium | 2026-10-31 | 2026-11-16 | 34 | In Progress | Awaiting clarification | NO | 22 | 66 | 2026-09-09 | P08104 | P081O4 | PriyaO37 | 0
P081 | P081-T5 | Testing / validation | Rahul | Vivek | Low | 2026-11-14 | 2026-12-07 | 53 | In Progress |  | NO | 83 | 56 | 2026-09-09 | P08105 | P081O5 | RahulO36 | 0
P081 | P081-T6 | Customer acceptance | Karan | Ritu | Low | 2026-11-28 | 2026-12-18 | 41 | In Progress |  | NO | 32 | 57 | 2026-09-09 | P08106 | P081O6 | KaranO39 | 0
P082 | P082-T1 | Requirements & scope freeze | Deepa | Rahul | Low | 2026-09-20 | 2026-10-03 | 47 | In Progress |  | NO | 50 | 61 | 2026-09-09 | P08201 | P082O1 | DeepaO42 | 0
P082 | P082-T2 | Design / solution | Amit | Karan | High | 2026-10-04 | 2026-10-24 | 29 | In Progress |  | NO | 86 | 82 | 2026-09-09 | P08202 | P082O2 | AmitO39 | 0
P082 | P082-T3 | BOM / commercial approval | Priya | Meera | Critical | 2026-10-18 | 2026-11-06 | 36 | In Progress |  | NO | 56 | 56 | 2026-09-09 | P08203 | P082O3 | PriyaO38 | 0
P082 | P082-T4 | Build / execution | Rahul | Vivek | High | 2026-11-01 | 2026-11-17 | 30 | In Progress |  | NO | 94 | 38 | 2026-09-09 | P08204 | P082O4 | RahulO37 | 0
P082 | P082-T5 | Testing / validation | Karan | Ritu | Critical | 2026-11-15 | 2026-11-27 | 49 | In Progress |  | NO | 67 | 97 | 2026-09-09 | P08205 | P082O5 | KaranO40 | 0
P082 | P082-T6 | Customer acceptance | Meera | Sanjay | Low | 2026-11-29 | 2026-12-15 | 31 | In Progress | Awaiting clarification | NO | 77 | 15 | 2026-09-09 | P08206 | P082O6 | MeeraO40 | 0
P083 | P083-T1 | Requirements & scope freeze | Amit | Karan | High | 2026-09-21 | 2026-10-11 | 27 | In Progress |  | NO | 53 | 20 | 2026-09-09 | P08301 | P083O1 | AmitO40 | 0
P083 | P083-T2 | Design / solution | Priya | Meera | Low | 2026-10-05 | 2026-10-21 | 47 | In Progress |  | NO | 30 | 93 | 2026-09-09 | P08302 | P083O2 | PriyaO39 | 0
P083 | P083-T3 | BOM / commercial approval | Rahul | Vivek | Critical | 2026-10-19 | 2026-11-01 | 64 | In Progress | Awaiting clarification | NO | 60 | 48 | 2026-09-09 | P08303 | P083O3 | RahulO38 | 0
P083 | P083-T4 | Build / execution | Karan | Ritu | Medium | 2026-11-02 | 2026-11-17 | 52 | In Progress |  | NO | 94 | 42 | 2026-09-09 | P08304 | P083O4 | KaranO41 | 0
P083 | P083-T5 | Testing / validation | Meera | Sanjay | Low | 2026-11-16 | 2026-11-25 | 35 | Blocked | Supplier / cross-functional dependency | YES | 85 | 59 | 2026-09-09 | P08305 | P083O5 | MeeraO41 | 0
P083 | P083-T6 | Customer acceptance | Vivek | Anil | Low | 2026-11-30 | 2026-12-15 | 51 | In Progress | Awaiting clarification | NO | 34 | 16 | 2026-09-09 | P08306 | P083O6 | VivekO41 | 0
P084 | P084-T1 | Requirements & scope freeze | Priya | Meera | Critical | 2026-09-22 | 2026-10-09 | 90 | In Progress | Awaiting clarification | NO | 82 | 93 | 2026-09-09 | P08401 | P084O1 | PriyaO40 | 0
P084 | P084-T2 | Design / solution | Rahul | Vivek | Critical | 2026-10-06 | 2026-10-15 | 91 | In Progress |  | NO | 69 | 24 | 2026-09-09 | P08402 | P084O2 | RahulO39 | 0
P084 | P084-T3 | BOM / commercial approval | Karan | Ritu | Critical | 2026-10-20 | 2026-11-11 | 67 | In Progress | Awaiting clarification | NO | 51 | 88 | 2026-09-09 | P08403 | P084O3 | KaranO42 | 0
P084 | P084-T4 | Build / execution | Meera | Sanjay | Low | 2026-11-03 | 2026-11-23 | 66 | In Progress |  | NO | 79 | 75 | 2026-09-09 | P08404 | P084O4 | MeeraO42 | 0
P084 | P084-T5 | Testing / validation | Vivek | Anil | Critical | 2026-11-17 | 2026-12-11 | 81 | In Progress |  | NO | 39 | 69 | 2026-09-09 | P08405 | P084O5 | VivekO42 | 0
P084 | P084-T6 | Customer acceptance | Ritu | Kavya | High | 2026-12-01 | 2026-12-20 | 57 | In Progress |  | NO | 22 | 84 | 2026-09-09 | P08406 | P084O6 | RituO40 | 0
P085 | P085-T1 | Requirements & scope freeze | Rahul | Vivek | High | 2026-09-23 | 2026-10-14 | 65 | In Progress |  | NO | 47 | 21 | 2026-09-09 | P08501 | P085O1 | RahulO40 | 0
P085 | P085-T2 | Design / solution | Karan | Ritu | Critical | 2026-10-07 | 2026-10-19 | 65 | In Progress | Awaiting clarification | NO | 33 | 15 | 2026-09-09 | P08502 | P085O2 | KaranO43 | 0
P085 | P085-T3 | BOM / commercial approval | Meera | Sanjay | Medium | 2026-10-21 | 2026-11-14 | 64 | In Progress |  | NO | 57 | 81 | 2026-09-09 | P08503 | P085O3 | MeeraO43 | 0
P085 | P085-T4 | Build / execution | Vivek | Anil | High | 2026-11-04 | 2026-11-16 | 97 | In Progress |  | YES | 87 | 88 | 2026-09-09 | P08504 | P085O4 | VivekO43 | 0
P085 | P085-T5 | Testing / validation | Ritu | Kavya | Low | 2026-11-18 | 2026-12-04 | 80 | In Progress |  | YES | 84 | 44 | 2026-09-09 | P08505 | P085O5 | RituO41 | 0
P085 | P085-T6 | Customer acceptance | Sanjay | Rohan | High | 2026-12-02 | 2026-12-20 | 63 | In Progress |  | YES | 26 | 29 | 2026-09-09 | P08506 | P085O6 | SanjayO42 | 0
P086 | P086-T1 | Requirements & scope freeze | Karan | Ritu | Medium | 2026-09-24 | 2026-10-11 | 40 | In Progress |  | NO | 88 | 26 | 2026-09-09 | P08601 | P086O1 | KaranO44 | 0
P086 | P086-T2 | Design / solution | Meera | Sanjay | Medium | 2026-10-08 | 2026-10-30 | 61 | In Progress | Awaiting clarification | NO | 59 | 72 | 2026-09-09 | P08602 | P086O2 | MeeraO44 | 0
P086 | P086-T3 | BOM / commercial approval | Vivek | Anil | High | 2026-10-22 | 2026-11-14 | 30 | In Progress | Awaiting clarification | NO | 87 | 52 | 2026-09-09 | P08603 | P086O3 | VivekO44 | 0
P086 | P086-T4 | Build / execution | Ritu | Kavya | Medium | 2026-11-05 | 2026-11-25 | 53 | In Progress | Awaiting clarification | NO | 44 | 35 | 2026-09-09 | P08604 | P086O4 | RituO42 | 0
P086 | P086-T5 | Testing / validation | Sanjay | Rohan | Low | 2026-11-19 | 2026-12-04 | 40 | Blocked | Supplier / cross-functional dependency | YES | 99 | 81 | 2026-09-09 | P08605 | P086O5 | SanjayO43 | 0
P086 | P086-T6 | Customer acceptance | Anil | Deepa | Medium | 2026-12-03 | 2026-12-26 | 59 | In Progress |  | NO | 67 | 104 | 2026-09-09 | P08606 | P086O6 | AnilO41 | 0
P087 | P087-T1 | Requirements & scope freeze | Meera | Sanjay | High | 2026-09-25 | 2026-10-12 | 63 | In Progress |  | NO | 24 | 59 | 2026-09-09 | P08701 | P087O1 | MeeraO45 | 0
P087 | P087-T2 | Design / solution | Vivek | Anil | Low | 2026-10-09 | 2026-10-21 | 87 | In Progress |  | NO | 55 | 15 | 2026-09-09 | P08702 | P087O2 | VivekO45 | 0
P087 | P087-T3 | BOM / commercial approval | Ritu | Kavya | Critical | 2026-10-23 | 2026-11-13 | 61 | In Progress |  | NO | 50 | 105 | 2026-09-09 | P08703 | P087O3 | RituO43 | 0
P087 | P087-T4 | Build / execution | Sanjay | Rohan | High | 2026-11-06 | 2026-11-15 | 56 | In Progress |  | NO | 72 | 49 | 2026-09-09 | P08704 | P087O4 | SanjayO44 | 0
P087 | P087-T5 | Testing / validation | Anil | Deepa | Low | 2026-11-20 | 2026-12-03 | 69 | In Progress |  | NO | 84 | 17 | 2026-09-09 | P08705 | P087O5 | AnilO42 | 0
P087 | P087-T6 | Customer acceptance | Kavya | Amit | Medium | 2026-12-04 | 2026-12-19 | 90 | In Progress |  | NO | 45 | 20 | 2026-09-09 | P08706 | P087O6 | KavyaO41 | 0
P088 | P088-T1 | Requirements & scope freeze | Vivek | Anil | Medium | 2026-09-26 | 2026-10-13 | 75 | In Progress |  | NO | 67 | 73 | 2026-09-09 | P08801 | P088O1 | VivekO46 | 0
P088 | P088-T2 | Design / solution | Ritu | Kavya | High | 2026-10-10 | 2026-10-26 | 67 | In Progress |  | NO | 54 | 30 | 2026-09-09 | P08802 | P088O2 | RituO44 | 0
P088 | P088-T3 | BOM / commercial approval | Sanjay | Rohan | High | 2026-10-24 | 2026-11-12 | 85 | In Progress |  | NO | 54 | 72 | 2026-09-09 | P08803 | P088O3 | SanjayO45 | 0
P088 | P088-T4 | Build / execution | Anil | Deepa | High | 2026-11-07 | 2026-11-30 | 65 | In Progress |  | YES | 52 | 23 | 2026-09-09 | P08804 | P088O4 | AnilO43 | 0
P088 | P088-T5 | Testing / validation | Kavya | Amit | Critical | 2026-11-21 | 2026-12-05 | 74 | In Progress |  | YES | 89 | 50 | 2026-09-09 | P08805 | P088O5 | KavyaO42 | 0
P088 | P088-T6 | Customer acceptance | Rohan | Priya | High | 2026-12-05 | 2026-12-23 | 62 | In Progress |  | YES | 39 | 17 | 2026-09-09 | P08806 | P088O6 | RohanO42 | 0
P089 | P089-T1 | Requirements & scope freeze | Ritu | Kavya | High | 2026-09-27 | 2026-10-17 | 85 | In Progress |  | NO | 96 | 64 | 2026-09-09 | P08901 | P089O1 | RituO45 | 0
P089 | P089-T2 | Design / solution | Sanjay | Rohan | Critical | 2026-10-11 | 2026-10-23 | 75 | In Progress |  | NO | 91 | 51 | 2026-09-09 | P08902 | P089O2 | SanjayO46 | 0
P089 | P089-T3 | BOM / commercial approval | Anil | Deepa | Medium | 2026-10-25 | 2026-11-16 | 82 | In Progress |  | NO | 75 | 38 | 2026-09-09 | P08903 | P089O3 | AnilO44 | 0
P089 | P089-T4 | Build / execution | Kavya | Amit | Critical | 2026-11-08 | 2026-11-17 | 84 | In Progress | Awaiting clarification | YES | 60 | 93 | 2026-09-09 | P08904 | P089O4 | KavyaO43 | 0
P089 | P089-T5 | Testing / validation | Rohan | Priya | Critical | 2026-11-22 | 2026-12-09 | 86 | In Progress | Awaiting clarification | YES | 28 | 46 | 2026-09-09 | P08905 | P089O5 | RohanO43 | 0
P089 | P089-T6 | Customer acceptance | Deepa | Rahul | Medium | 2026-12-06 | 2026-12-15 | 78 | In Progress |  | YES | 40 | 105 | 2026-09-09 | P08906 | P089O6 | DeepaO43 | 0
P090 | P090-T1 | Requirements & scope freeze | Sanjay | Rohan | Medium | 2026-09-28 | 2026-10-20 | 98 | In Progress |  | NO | 32 | 63 | 2026-09-09 | P09001 | P090O1 | SanjayO47 | 0
P090 | P090-T2 | Design / solution | Anil | Deepa | Medium | 2026-10-12 | 2026-10-28 | 82 | In Progress |  | NO | 97 | 76 | 2026-09-09 | P09002 | P090O2 | AnilO45 | 0
P090 | P090-T3 | BOM / commercial approval | Kavya | Amit | High | 2026-10-26 | 2026-11-12 | 93 | In Progress |  | NO | 39 | 105 | 2026-09-09 | P09003 | P090O3 | KavyaO44 | 0
P090 | P090-T4 | Build / execution | Rohan | Priya | Critical | 2026-11-09 | 2026-12-02 | 87 | In Progress |  | NO | 93 | 39 | 2026-09-09 | P09004 | P090O4 | RohanO44 | 0
P090 | P090-T5 | Testing / validation | Deepa | Rahul | High | 2026-11-23 | 2026-12-16 | 73 | In Progress |  | NO | 87 | 56 | 2026-09-09 | P09005 | P090O5 | DeepaO44 | 0
P090 | P090-T6 | Customer acceptance | Amit | Karan | Low | 2026-12-07 | 2026-12-17 | 65 | In Progress |  | NO | 89 | 80 | 2026-09-09 | P09006 | P090O6 | AmitO41 | 0
P091 | P091-T1 | Requirements & scope freeze | Anil | Deepa | Critical | 2026-09-29 | 2026-10-08 | 34 | In Progress |  | NO | 35 | 36 | 2026-09-09 | P09101 | P091O1 | AnilO46 | 0
P091 | P091-T2 | Design / solution | Kavya | Amit | Low | 2026-10-13 | 2026-11-04 | 24 | In Progress |  | NO | 32 | 76 | 2026-09-09 | P09102 | P091O2 | KavyaO45 | 0
P091 | P091-T3 | BOM / commercial approval | Rohan | Priya | High | 2026-10-27 | 2026-11-16 | 31 | In Progress |  | NO | 46 | 80 | 2026-09-09 | P09103 | P091O3 | RohanO45 | 0
P091 | P091-T4 | Build / execution | Deepa | Rahul | Low | 2026-11-10 | 2026-11-26 | 18 | Blocked | Supplier / cross-functional dependency | YES | 39 | 22 | 2026-09-09 | P09104 | P091O4 | DeepaO45 | 0
P091 | P091-T5 | Testing / validation | Amit | Karan | Medium | 2026-11-24 | 2026-12-18 | 42 | Blocked | Supplier / cross-functional dependency | YES | 69 | 33 | 2026-09-09 | P09105 | P091O5 | AmitO42 | 0
P091 | P091-T6 | Customer acceptance | Priya | Meera | High | 2026-12-08 | 2026-12-26 | 20 | Blocked | Supplier / cross-functional dependency | YES | 22 | 65 | 2026-09-09 | P09106 | P091O6 | PriyaO41 | 0
P092 | P092-T1 | Requirements & scope freeze | Kavya | Amit | Low | 2026-09-30 | 2026-10-16 | 72 | In Progress | Awaiting clarification | NO | 52 | 41 | 2026-09-09 | P09201 | P092O1 | KavyaO46 | 0
P092 | P092-T2 | Design / solution | Rohan | Priya | Medium | 2026-10-14 | 2026-10-28 | 87 | In Progress |  | NO | 96 | 72 | 2026-09-09 | P09202 | P092O2 | RohanO46 | 0
P092 | P092-T3 | BOM / commercial approval | Deepa | Rahul | Medium | 2026-10-28 | 2026-11-08 | 66 | In Progress |  | NO | 66 | 60 | 2026-09-09 | P09203 | P092O3 | DeepaO46 | 0
P092 | P092-T4 | Build / execution | Amit | Karan | Low | 2026-11-11 | 2026-11-25 | 70 | In Progress |  | NO | 68 | 19 | 2026-09-09 | P09204 | P092O4 | AmitO43 | 0
P092 | P092-T5 | Testing / validation | Priya | Meera | Critical | 2026-11-25 | 2026-12-12 | 85 | In Progress |  | NO | 32 | 81 | 2026-09-09 | P09205 | P092O5 | PriyaO42 | 0
P092 | P092-T6 | Customer acceptance | Rahul | Vivek | Critical | 2026-12-09 | 2026-12-29 | 92 | In Progress |  | NO | 45 | 79 | 2026-09-09 | P09206 | P092O6 | RahulO41 | 0
P093 | P093-T1 | Requirements & scope freeze | Rohan | Priya | High | 2026-10-01 | 2026-10-13 | 45 | In Progress |  | NO | 28 | 57 | 2026-09-09 | P09301 | P093O1 | RohanO47 | 0
P093 | P093-T2 | Design / solution | Deepa | Rahul | Low | 2026-10-15 | 2026-10-29 | 28 | In Progress | Awaiting clarification | NO | 71 | 59 | 2026-09-09 | P09302 | P093O2 | DeepaO47 | 0
P093 | P093-T3 | BOM / commercial approval | Amit | Karan | Medium | 2026-10-29 | 2026-11-13 | 22 | In Progress |  | NO | 90 | 91 | 2026-09-09 | P09303 | P093O3 | AmitO44 | 0
P093 | P093-T4 | Build / execution | Priya | Meera | Medium | 2026-11-12 | 2026-12-06 | 44 | In Progress |  | NO | 88 | 38 | 2026-09-09 | P09304 | P093O4 | PriyaO43 | 0
P093 | P093-T5 | Testing / validation | Rahul | Vivek | Medium | 2026-11-26 | 2026-12-12 | 14 | In Progress |  | NO | 90 | 47 | 2026-09-09 | P09305 | P093O5 | RahulO42 | 0
P093 | P093-T6 | Customer acceptance | Karan | Ritu | High | 2026-12-10 | 2026-12-23 | 32 | In Progress |  | NO | 35 | 68 | 2026-09-09 | P09306 | P093O6 | KaranO45 | 0
P094 | P094-T1 | Requirements & scope freeze | Deepa | Rahul | Low | 2026-10-02 | 2026-10-17 | 76 | In Progress |  | NO | 56 | 85 | 2026-09-09 | P09401 | P094O1 | DeepaO48 | 0
P094 | P094-T2 | Design / solution | Amit | Karan | Low | 2026-10-16 | 2026-10-30 | 94 | In Progress | Awaiting clarification | NO | 86 | 40 | 2026-09-09 | P09402 | P094O2 | AmitO45 | 0
P094 | P094-T3 | BOM / commercial approval | Priya | Meera | High | 2026-10-30 | 2026-11-10 | 88 | In Progress | Awaiting clarification | NO | 29 | 87 | 2026-09-09 | P09403 | P094O3 | PriyaO44 | 0
P094 | P094-T4 | Build / execution | Rahul | Vivek | Low | 2026-11-13 | 2026-12-04 | 75 | In Progress |  | NO | 53 | 96 | 2026-09-09 | P09404 | P094O4 | RahulO43 | 0
P094 | P094-T5 | Testing / validation | Karan | Ritu | Low | 2026-11-27 | 2026-12-12 | 96 | In Progress |  | NO | 93 | 84 | 2026-09-09 | P09405 | P094O5 | KaranO46 | 0
P094 | P094-T6 | Customer acceptance | Meera | Sanjay | Critical | 2026-12-11 | 2026-12-22 | 83 | In Progress |  | NO | 84 | 56 | 2026-09-09 | P09406 | P094O6 | MeeraO46 | 0
P095 | P095-T1 | Requirements & scope freeze | Amit | Karan | High | 2026-10-03 | 2026-10-23 | 90 | In Progress | Awaiting clarification | NO | 83 | 64 | 2026-09-09 | P09501 | P095O1 | AmitO46 | 0
P095 | P095-T2 | Design / solution | Priya | Meera | High | 2026-10-17 | 2026-11-03 | 77 | In Progress |  | NO | 90 | 95 | 2026-09-09 | P09502 | P095O2 | PriyaO45 | 0
P095 | P095-T3 | BOM / commercial approval | Rahul | Vivek | Critical | 2026-10-31 | 2026-11-23 | 91 | In Progress | Awaiting clarification | NO | 42 | 103 | 2026-09-09 | P09503 | P095O3 | RahulO44 | 0
P095 | P095-T4 | Build / execution | Karan | Ritu | High | 2026-11-14 | 2026-12-05 | 78 | In Progress |  | NO | 48 | 82 | 2026-09-09 | P09504 | P095O4 | KaranO47 | 0
P095 | P095-T5 | Testing / validation | Meera | Sanjay | Critical | 2026-11-28 | 2026-12-19 | 97 | In Progress | Awaiting clarification | NO | 88 | 88 | 2026-09-09 | P09505 | P095O5 | MeeraO47 | 0
P095 | P095-T6 | Customer acceptance | Vivek | Anil | Medium | 2026-12-12 | 2026-12-29 | 98 | In Progress |  | NO | 100 | 63 | 2026-09-09 | P09506 | P095O6 | VivekO47 | 0
P096 | P096-T1 | Requirements & scope freeze | Priya | Meera | Low | 2026-10-04 | 2026-10-19 | 32 | In Progress |  | NO | 70 | 75 | 2026-09-09 | P09601 | P096O1 | PriyaO46 | 0
P096 | P096-T2 | Design / solution | Rahul | Vivek | Medium | 2026-10-18 | 2026-10-31 | 36 | In Progress |  | NO | 61 | 54 | 2026-09-09 | P09602 | P096O2 | RahulO45 | 0
P096 | P096-T3 | BOM / commercial approval | Karan | Ritu | Low | 2026-11-01 | 2026-11-13 | 27 | In Progress |  | NO | 22 | 33 | 2026-09-09 | P09603 | P096O3 | KaranO48 | 0
P096 | P096-T4 | Build / execution | Meera | Sanjay | High | 2026-11-15 | 2026-11-30 | 34 | Blocked | Supplier / cross-functional dependency | YES | 49 | 59 | 2026-09-09 | P09604 | P096O4 | MeeraO48 | 0
P096 | P096-T5 | Testing / validation | Vivek | Anil | Critical | 2026-11-29 | 2026-12-13 | 31 | Blocked | Supplier / cross-functional dependency | YES | 22 | 26 | 2026-09-09 | P09605 | P096O5 | VivekO48 | 0
P096 | P096-T6 | Customer acceptance | Ritu | Kavya | High | 2026-12-13 | 2026-12-27 | 8 | Blocked | Supplier / cross-functional dependency | YES | 79 | 77 | 2026-09-09 | P09606 | P096O6 | RituO46 | 0
P097 | P097-T1 | Requirements & scope freeze | Rahul | Vivek | Medium | 2026-10-05 | 2026-10-22 | 30 | In Progress |  | NO | 48 | 33 | 2026-09-09 | P09701 | P097O1 | RahulO46 | 0
P097 | P097-T2 | Design / solution | Karan | Ritu | High | 2026-10-19 | 2026-11-03 | 46 | In Progress | Awaiting clarification | NO | 91 | 66 | 2026-09-09 | P09702 | P097O2 | KaranO49 | 0
P097 | P097-T3 | BOM / commercial approval | Meera | Sanjay | Medium | 2026-11-02 | 2026-11-21 | 47 | In Progress |  | NO | 68 | 29 | 2026-09-09 | P09703 | P097O3 | MeeraO49 | 0
P097 | P097-T4 | Build / execution | Vivek | Anil | Low | 2026-11-16 | 2026-12-04 | 64 | In Progress |  | NO | 69 | 51 | 2026-09-09 | P09704 | P097O4 | VivekO49 | 0
P097 | P097-T5 | Testing / validation | Ritu | Kavya | Low | 2026-11-30 | 2026-12-10 | 28 | In Progress |  | NO | 65 | 103 | 2026-09-09 | P09705 | P097O5 | RituO47 | 0
P097 | P097-T6 | Customer acceptance | Sanjay | Rohan | Critical | 2026-12-14 | 2027-01-06 | 55 | In Progress |  | NO | 71 | 99 | 2026-09-09 | P09706 | P097O6 | SanjayO48 | 0
P098 | P098-T1 | Requirements & scope freeze | Karan | Ritu | Medium | 2026-10-06 | 2026-10-22 | 90 | In Progress |  | NO | 31 | 66 | 2026-09-09 | P09801 | P098O1 | KaranO50 | 0
P098 | P098-T2 | Design / solution | Meera | Sanjay | High | 2026-10-20 | 2026-11-09 | 93 | In Progress |  | NO | 50 | 16 | 2026-09-09 | P09802 | P098O2 | MeeraO50 | 0
P098 | P098-T3 | BOM / commercial approval | Vivek | Anil | Low | 2026-11-03 | 2026-11-22 | 90 | In Progress |  | NO | 99 | 59 | 2026-09-09 | P09803 | P098O3 | VivekO50 | 0
P098 | P098-T4 | Build / execution | Ritu | Kavya | High | 2026-11-17 | 2026-11-28 | 100 | Completed |  | NO | 94 | 103 | 2026-09-09 | P09804 |  |  | 0
P098 | P098-T5 | Testing / validation | Sanjay | Rohan | Medium | 2026-12-01 | 2026-12-20 | 100 | Completed |  | NO | 53 | 64 | 2026-09-09 | P09805 |  |  | 0
P098 | P098-T6 | Customer acceptance | Anil | Deepa | Medium | 2026-12-15 | 2026-12-25 | 96 | In Progress |  | NO | 97 | 38 | 2026-09-09 | P09806 | P098O4 | AnilO47 | 0
P099 | P099-T1 | Requirements & scope freeze | Meera | Sanjay | Low | 2026-10-07 | 2026-10-21 | 20 | In Progress | Awaiting clarification | NO | 71 | 33 | 2026-09-09 | P09901 | P099O1 | MeeraO51 | 0
P099 | P099-T2 | Design / solution | Vivek | Anil | High | 2026-10-21 | 2026-11-09 | 36 | In Progress |  | NO | 39 | 37 | 2026-09-09 | P09902 | P099O2 | VivekO51 | 0
P099 | P099-T3 | BOM / commercial approval | Ritu | Kavya | Medium | 2026-11-04 | 2026-11-18 | 47 | In Progress | Awaiting clarification | NO | 86 | 22 | 2026-09-09 | P09903 | P099O3 | RituO48 | 0
P099 | P099-T4 | Build / execution | Sanjay | Rohan | Medium | 2026-11-18 | 2026-12-12 | 21 | In Progress |  | NO | 73 | 95 | 2026-09-09 | P09904 | P099O4 | SanjayO49 | 0
P099 | P099-T5 | Testing / validation | Anil | Deepa | Medium | 2026-12-02 | 2026-12-23 | 34 | In Progress |  | NO | 65 | 67 | 2026-09-09 | P09905 | P099O5 | AnilO48 | 0
P099 | P099-T6 | Customer acceptance | Kavya | Amit | Medium | 2026-12-16 | 2027-01-03 | 15 | In Progress |  | NO | 38 | 81 | 2026-09-09 | P09906 | P099O6 | KavyaO47 | 0
P100 | P100-T1 | Requirements & scope freeze | Vivek | Anil | Medium | 2026-10-08 | 2026-10-21 | 83 | In Progress | Awaiting clarification | NO | 29 | 56 | 2026-09-09 | P10001 | P100O1 | VivekO52 | 0
P100 | P100-T2 | Design / solution | Ritu | Kavya | Critical | 2026-10-22 | 2026-11-05 | 50 | In Progress | Awaiting clarification | NO | 100 | 52 | 2026-09-09 | P10002 | P100O2 | RituO49 | 0
P100 | P100-T3 | BOM / commercial approval | Sanjay | Rohan | High | 2026-11-05 | 2026-11-18 | 66 | In Progress |  | NO | 78 | 51 | 2026-09-09 | P10003 | P100O3 | SanjayO50 | 0
P100 | P100-T4 | Build / execution | Anil | Deepa | Critical | 2026-11-19 | 2026-12-13 | 64 | In Progress | Awaiting clarification | NO | 85 | 71 | 2026-09-09 | P10004 | P100O4 | AnilO49 | 0
P100 | P100-T5 | Testing / validation | Kavya | Amit | Medium | 2026-12-03 | 2026-12-22 | 64 | In Progress |  | NO | 43 | 67 | 2026-09-09 | P10005 | P100O5 | KavyaO48 | 0
P100 | P100-T6 | Customer acceptance | Rohan | Priya | Critical | 2026-12-17 | 2027-01-02 | 80 | In Progress |  | NO | 77 | 74 | 2026-09-09 | P10006 | P100O6 | RohanO48 | 0

## 12_Integrity
DATA INTEGRITY ¦ CONTROL CHECKS
Visible quality gate: every core dashboard number should trace back to the data engine.
HOME | SPONSOR | PROGRAM | PROJECT 360 | PM CONTROL | TEAM | GANTT | DECISIONS | DEPENDENCIES | CHANGES | DATA | TASKS | INTEGRITY
CONTROL CHECKS
Project records | 100 | 100 expected
Task records | 600 | 600 expected
Duplicate project IDs | 0 | 0 expected
Duplicate task IDs | 0 | 0 expected
Tasks without project | 0 | 0 expected
Invalid progress values | 0 | 0 expected
Blank required task status | 0 | 0 expected
Project rows failing baseline check | 0 | 0 expected
Design standard: dashboards use white canvas, navy structure, one consistent status palette, and enough whitespace to keep executive attention on exceptions.

## 13_Read_Me
SYNERGY ¦ DESIGN & OPERATING STANDARD
What changed in V2: cleaner canvas, stable layouts, populated visuals, complete Gantt, traceable data.
01 | Executive-first | Sponsor page leads with Revenue, Profit, Pipeline, Resources, Risk and Health.
02 | White / plain canvas | White canvas with light grey structure keeps charts readable and avoids visual displacement.
03 | Consistent status standard | GREEN = healthy, AMBER = watch, RED = intervention. Status is also written as text, not color-only.
04 | Complete Gantt | Portfolio Gantt contains all 100 projects across 27 weekly columns. Selected-project Gantt contains task-level bars.
05 | Data integrity | Project and task engines include controlled inputs, validation, calculated roll-ups and a visible Integrity page.
06 | Drill-down | Sponsor → Project 360 → Gantt / Decision / Dependency / PM / Team.
07 | Logo | SYNERGY logo is placed top-right on every management page.
08 | No blank executive cards | Dashboard KPIs and charts are formula-linked to the data engine and recalculate on open.
09 | Editable input layer | Yellow cells in Project Data, Task Data and control pages are the intended operating inputs.
10 | Design discipline | Visual hierarchy follows common dashboard guidance: one-screen story, important information first, consistent scales and restrained colors.
DEMO DATA ASSUMPTIONS
6-month value timing | Jul-Dec 2026 | 12% / 15% / 18% / 20% / 18% / 17% allocation of portfolio revenue & profit
Dummy portfolio | 100 projects / 600 tasks | Values are illustrative for prototype demonstration and should be replaced with live project data.
Data quality rule | No duplicate Project IDs / Task IDs | Integrity sheet should remain at zero exceptions before executive use.

## 14_Config
CONFIGURATION & STANDARDS |  |  |  |  | SYNERGY VISUAL STANDARD |  |  | 6-Month Value Timing Assumption | Weight
Controlled lists and visual standards for the prototype. |  |  |  |  | Primary | #17324D | Amit | 2026-07-01 | 12%
[5 empty] | Secondary | #2F75B5 | Anil | 2026-08-01 | 15%
Status | RAG | Priority | Phase | Decision | Positive | #2E9B5B | Deepa | 2026-09-01 | 18%
Not Started | GREEN | Critical | Initiation | Pending | Watch | #E5A400 | Karan | 2026-10-01 | 20%
In Progress | AMBER | High | Planning | Approved | Critical | #D9534F | Kavya | 2026-11-01 | 18%
Blocked | RED | Medium | Design | Rejected | Accent | #20B8C8 | Meera | 2026-12-01 | 17%
Completed |  | Low | Build | Escalated | Neutral | #667085 | Priya
On Hold |  |  | Testing |  | Canvas | #F5F7FA | Rahul
|  |  | Deployment |  |  |  | Ritu
|  |  | Closure |  |  |  | Rohan
Sanjay
Vivek